2015/2016

XHARIEP DISTRICT MUNICIPALITY

# CONTENTS

CONTENTS	2

PROPOSED REVISED ANNUAL REPORT TEMPLATE	5

CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY	6

COMPONENT A: MAYOR’S FOREWORD	6

COMPONENT B: EXECUTIVE SUMMARY	7

1.1.	MUNICIPAL MANAGER’S OVERVIEW	7

1.2.	MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW	8

1.3.	SERVICE DELIVERY OVERVIEW	10

1.4.	FINANCIAL HEALTH OVERVIEW	11

1.5.	ORGANISATIONAL DEVELOPMENT OVERVIEW	12

1.6.	AUDITOR GENERAL REPORT	12

1.7.	STATUTORY ANNUAL REPORT PROCESS	13

CHAPTER 2 – GOVERNANCE	15

COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE	15

2.1	POLITICAL GOVERNANCE	16

2.2	ADMINISTRATIVE GOVERNANCE	18

COMPONENT B: INTERGOVERNMENTAL RELATIONS	20

2.3	INTERGOVERNMENTAL RELATIONS	20

COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION	21

2.4	PUBLIC MEETINGS	21

2.5	IDP PARTICIPATION AND ALIGNMENT	24

COMPONENT D: CORPORATE GOVERNANCE	25

2.6	RISK MANAGEMENT	26

2.7	ANTI-CORRUPTION AND FRAUD	27

2.8	SUPPLY CHAIN MANAGEMENT	27

2.10	WEBSITES	28

CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)	30

COMPONENT A: BASIC SERVICES	31

3.11	LOCAL ECONOMIC DEVELOPMENT (INCLUDING TOURISM AND MARKET PLACES)	31

3.64	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC	34

3.67	OTHER (DISASTER MANAGEMENT)	35

COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES	37

3.69	EXECUTIVE AND COUNCIL	37

3.70	FINANCIAL SERVICES	39

3.71	HUMAN RESOURCE SERVICES	41

3.72	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES	43

COMPONENT K: ORGANISATIONAL PERFORMANCE SCORECARD	45

CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE	68

(PERFORMANCE REPORT PART II)	68

COMPONENT A: INTRODUCTION TO THE MUNICIPAL PERSONNEL	69

4.1	EMPLOYEE TOTALS, TURNOVER AND VACANCIES	69

COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE	70

4.2	POLICIES	71

4.3	INJURIES, SICKNESS AND SUSPENSIONS	72

COMPONENT C: CAPACITATING THE MUNICIPAL WORKFORCE	74

4.5	SKILLS DEVELOPMENT AND TRAINING	75

COMPONENT D: MANAGING THE WORKFORCE EXPENDITURE	78

CHAPTER 5 – FINANCIAL PERFORMANCE	79

5.3	ASSET MANAGEMENT	79

COMPONENT D: OTHER FINANCIAL MATTERS	80

5.12	SUPPLY CHAIN MANAGEMENT	80

5.13	GRAP COMPLIANCE	80

CHAPTER 6 – AUDITOR GENERAL AUDIT FIND	81

COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS 2014/2015	81

6.1 AUDITOR GENERAL REPORT 2014/2015(Previous year)	81

COMPONENT B: AUDITOR-GENERAL OPINION 2015/2016 (CURRENT YEAR)	85

6.2 AUDITOR GENERAL REPORT 2015/2016	85

Report of the auditor-general to the Free State Provincial Legislature and the council on the Xhariep District Municipality	85

Report on the financial statements	85

GLOSSARY	92

APPENDICES	95

APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE	95

APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES	97

APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY	98

APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE 2015/2016	100

APPENDIX H(i) – Long Term Contracts (20 Largest Contracts Entered into during 2015/2016	101

APPENDIX I –SERVICE PROVIDER PERFORMANCE SCHEDULE	103

APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS	104

APPENDIX K (i): REVENUE COLLECTION PERFORMANCE BY Source	105

APPENDIX T – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT	106

VOLUME II: ANNUAL FINANCIAL STATEMENTS	107

Management Action Plan……..…………………………………………………………………………………………………………………167

# PROPOSED REVISED ANNUAL REPORT TEMPLATE

The purpose of this revised Annual Report template is to address the need expressed by a number of municipalities for assistance in the preparation and development of improved content and quality of Municipal Annual Reports. It replaces a template dating back to August 2003.

This template gives effect to the legal framework requirement, concepts and principals espoused in the White Paper on Local Government and Improving Government Performance.  It reflects the ethos of public accountability.  The content gives effect to information required for better monitoring and evaluation of government programmes in support of policy decision making. The template provides an improved overview of municipal affairs by combining the performance report data required under Municipal Systems Act Section 46 with annual report data referred to in that Act and in the MFMA.

The revised template makes its contribution by forging linkages with the Integrated Development Plan, Service Delivery and Budget Implementation Plan, Budget Reforms, In-year Reports, Annual Financial Statements and Performance Management information in municipalities.  This coverage and coherence is achieved by the use of interlocking processes and formats.

The revised template relates to the Medium Term Strategic Framework particularly through the IDP strategic objectives; cross cutting nature of services offered by different spheres of government, municipal service outcome indicators; and the contextual material as set out in Chapters 3, 4 & 5.  It also provides information on good management practice in Chapter 4; risk management in Chapter 2; and Supply Chain Management in Chapter 5; and addresses the Auditor-General’s Report, dealing with Financial and Performance Management arrangements in Chapter 6.  This opens up greater possibilities for financial and nonfinancial comparisons between municipalities and improved value for money.

The revised template provides information on probity, including: anti-corruption strategies; disclosure of financial interests by officials and councillors; disclosure of grants by external parties, disclosure of loans and grants by municipalities.  The appendices talk to greater detail including disaggregated information on municipal wards, among others.

Notes are included throughout the format to assist the compiler to understand the various information requirements. Once the draft has been finalised, training will be provided to facilitate the implementation of this initiative, and separate additional guidance may be issued if necessary.

We wish to express our gratitude to the members of the Annual Report Reference Group, consisting of national, provincial and municipal officials for their inputs and support throughout the development of this document.

MFMA Implementation Unit, National Treasury                                                                                           October 2009

# CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY

## COMPONENT A: MAYOR’S FOREWORD

MAYOR’S FOREWORD In our quest to augment accelerated growth and better service delivery within our society, and thus instilling a better destiny for the current and future generations in the municipality, we have taken upon ourselves the responsibilities of strengthening our service delivery model through proper managed partnerships with our stakeholders around the district and the province, including neighbouring other municipalities in other provinces. We have continued to have inter-governmental partnerships through the IGR structures headed by the district and focused on all areas of focus for the district as guided by the powers and functions allocated to the District of Xhariep, to ensure that we reinforce the authenticity of a democratic government whithin our communities together with the Local Municipalities. By so doing we are fully committed to the fulfilment of the mandates of The White Paper on Local government, 1998 and the Municipal Systems Act of 2000. In order to deal with the developmental challenges that are faced by the municipality and improving the service delivery backlogs, the need for capable workforce was well addressed through the occupancy key vacancies We have also infused programmes on the evaluation of SMME development to assess the impact that municipality has had on the development of small businesses and job creation and sustainability in that arena. Co-operatives, SMME developments, together with projects on Extended Public Works Programmes, are instrumental to creation of jobs within the District. We note the achievements made by the Municipality in both capable planning and improved financial management and should strengthen our achievement of set targets This annual report is therefore, a synopsis of our challenges, achievements and progress throughout the 2015/2016 period on the Council IDP`s objectives and goals. The challenges that the municipality has had to endure, the expenditure incurred, the successes and the impact of these factors to the community are the main objectives that are brought to the fore in the mission to accomplish the constitutional service delivery mandate. Local Government continues to be everyone's business, let's make it all our business. T 1.0.1

## COMPONENT B: EXECUTIVE SUMMARY

### MUNICIPAL MANAGER’S OVERVIEW

MUNICIPAL MANAGER’S OVERVIEW In many respects 2015/16 was an eventful financial year for the municipality. Whereas the municipality faced a considerable number of obstacles and challenges, in the same token, recognizable milestones have been achieved and significant strides have been taken in addressing some of the perennial challenges that still beset the municipality. At the beginning of this financial year, there was recognition that whereas we have already laid down a solid foundation for effective operational systems over the past two years, it is important to consolidate our successes and achievements more from an explicit strategic approach. The municipality took note of the fact that legislation gives effect to local government systems that place greater service delivery responsibilities on managers and make them more accountable for performance, and in response to these, we had to gear all our administrative departments and units towards gradual improvement to ensure better performance at all levels. The operating strategies and programmes as set out in the Integrated Development Plan, the Budget and the Budget Implementation Plan (SDBIP), which constitutes the basis for performance and reporting, were formulated and developed from a forward looking perspective, aimed at not only consolidating on our previous achievements, but also taking into account critical challenges that we still have to overcome. Xhariep District Municipality believes that this approach did not only bring about the desired performance results in this financial year, but has also strengthened our ability to exercise proper accountability to council, stakeholders and communities. Confidently, Xhariep District Municipality is a completely different organization today compared to the same period last year and any other year before. There is a vast scale of improvements in different key performance areas T1.1.1

### MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW

INTRODUCTION TO BACKGROUND DATA

Out of 16 district functions, Xhariep district municipality is performing 3(18.75%) of these functions.

Xhariep District was estimated at a population of approximately 164 000 people in 2007. According to the 2011 Census statistics, its population size has declined with a lesser average of 2.21% per annum since 2007 to 2011,). The current district’s populations is at 145 742 people as per the 2011 census survey statistics.

T 1.2.1

| Population Details |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Population '000 |  |  |
| Age | 2013/2014 |  |  | 2014/2015 |  |  | 2015/2016 |  |  |  |
|  | Male | Female | Total | Male | Female | Total | Male | Female |  | Total |
| Age: 0 – 14 | 25 189 | 25 022 | 50 211 | 26 189 | 26 241 | 52430 | 22 734 | 22 250 |  | 44 984 |
| Age: 15-64 | 42 333 | 43 860 | 86 193 | 49 859 | 50 762 | 100 621 | 45 309 | 46 692 |  | 92 001 |
| Age: 65+ | 3 304 | 5 117 | 8 421 | 3 699 | 5 976 | 9 676 | 3 615 | 5 658 |  | 9 273 |
| Total | 70 826 | 74 000 | 144 826 | 79 747 | 82 990 | 162 727 | 71 658 | 74 600 |  | 146 259 |
| Source: Statistics SA T1.2.2 |  |  |  |  |  |  |  |  |  |  |

SOCIO ECONOMIC STATUS: Economically Active Population per local municipality

| Local Municipality | Number | Percentage (%) |
| --- | --- | --- |
| Kopanong | 19472 | 29.54 |
| Letsemeng | 16639 | 30.53 |
| Mohokare | 12110 | 32.63 |
| Naledi | 8067 | 27.38 |

Data Source: STATSSA (Census 2011 Survey)

OVERVIEW OF NEIGHBOURHOODS WITHIN (NAME OF MUNICIPALITY

| Type of dwellings | FS161: Letsemeng | FS162: Kopanong | FS163: Mohokare | FS164: Naledi |
| --- | --- | --- | --- | --- |
| House or brick/concrete block structure on a separate stand or yard or on a farm | 9016 | 13904 | 9027 | 6309 |
| Traditional dwelling/hut/structure made of traditional materials | 17 | 57 | 74 | 34 |
| Flat or apartment in a block of flats | 63 | 80 | 62 | 35 |
| Cluster house in complex | 12 | 11 | 5 | 42 |
| Townhouse (semi-detached house in a complex) | 36 | 31 | 1 | 9 |
| Semi-detached house | 76 | 20 | 97 | 106 |
| House/flat/room in backyard | 133 | 197 | 103 | 15 |
| Informal dwelling (shack; in backyard) | 634 | 475 | 838 | 662 |
| Informal dwelling (shack; not in backyard; e.g. in an informal/squatter settlement or on a farm) | 1179 | 739 | 483 | 436 |
| Room/flat let on a property or larger dwelling/servants quarters/granny flat | 22 | 51 | 55 | 10 |
| Caravan/tent | 5 | 6 | 9 | - |
| T 1.2.6 |  |  |  |  |

| Natural Resources |  |
| --- | --- |
| Major Natural Resource | Relevance to Community |
| Water (Gariep Dam) | Supply of water to households and generation of electricity. |
| Diamonds (Jaggersfontein and Koffiefontein) | Job creation, Revenue enhancement, Economic development, human settlement. |
| Uranium (Edenburg) | Job creation, Revenue enhance, Economic development, human settlement |
| Land | Job creation through farming and settlement of communities |
| Sun (Radiation energy) | Job creation through erection of solar hubs |
|  | T1.2.7 |

COMMENT ON BACKGROUND DATA:

The District faces various challenges ranging from widespread poverty to service delivery and infrastructure backlogs. It is estimated that almost 80% of the District residents live in poverty; worsened by a high unemployment rate of approximately 26.80%. Backlogs in service delivery are experienced in the following areas: water delivery and sanitation. The main contributors to the area’s economy are agriculture, which generates approximately 28% of Gross Value Added; public service and administration 26%; services and retail 17%; and construction 8%.

T1.2.8

### SERVICE DELIVERY OVERVIEW

SERVICE DELIVERY INTRODUCTION

The district municipality has started to perform the functions of Environmental Health and Disaster Management with effect from December 2009. Critically, the Municipal Structures Amendment Act (Act 33 of 2000) provides for an extensive annual review of the division of powers and functions between Category B and Category C to ensure effective implementation of these assigned powers following an advice provided by the Municipal Demarcation Boarding emanating from the Boards’ annual capacity assessment report.

T 1.3.1

### FINANCIAL HEALTH OVERVIEW

FINANCIAL OVERVIEW

The municipality at large does not have a revenue base as it solely depends on grants from other spheres of government and that is putting a strain on the finances of the municipality as only a few projects can be carried out in a financial year

T1.4.1

| Financial Overview - 2015/2016 |  |  |  |
| --- | --- | --- | --- |
|  |  |  | R' 000 |
| Details | Original budget | Adjustment Budget | Actual |
| Income |  |  |  |
| Grants | 51 774 | 51 774 | 52 564 |
| Taxes, Levies and tariffs | 461 | 461 | 435 |
| Other | 101 | 144 | 446 |
| Sub Total | 52 336 | 52 379 | 53 446 |
| Less Expenditure | (55 637) | (55 679) | (60 559) |
| Net Total* | (3 300) | (3 300) | (7 112) |
| * Note: surplus/(defecit) |  |  | T1.4.2 |

| Operating Ratios |  |
| --- | --- |
| Detail | % |
| Employee Cost | 64% |
| Repairs & Maintenance | 0.5% |
| Finance Charges & Impairment | 0.7% |
|  | T 1.4.3 |

COMMENT ON OPERATING RATIOS:

Employee cost is excessively above the expected norm of 30%, repairs and maintenance significantly lower than the 20% norm and finance charges considerably lower than the 10% benchmark

T1.4.3

### ORGANISATIONAL DEVELOPMENT OVERVIEW

ORGANISATIONAL DEVELOPMENT PERFORMANCE

Organization Development (OD) is about improving performance at the individual, group, and Municipal organizational levels. It is about improving the organization's ability to effectively respond to changes in its external environment, and it’s about increasing internal capabilities by ensuring the Xhariep District Municipal structures, human resources systems, job designs, communication systems, and leadership/managerial processes fully harness human motivation and help people function to their full potential.

Done well, such improvement can be transformational—producing fundamental changes in the way individuals, groups, and organizations functions.

T1.5.1

### AUDITOR GENERAL REPORT

AUDITOR GENERAL REPORT 2014/2015

Qualified opinion

The Auditor General was unable to obtain sufficient appropriate audit evidence that other payables and trade payables had been properly reconciled and accounted for. The district municipality did not maintain adequate records of outstanding invoices for goods and services received but not yet paid at year-end. The Auditor General was unable to confirm other creditors and trade payables by alternative means. Consequently, the Auditor General was unable to determine whether any adjustment to other creditors of R4 813 307 and trade payables of R1 202 012, as disclosed in note 11 to the financial statements, was necessary.

T 1.6.1

### STATUTORY ANNUAL REPORT PROCESS

| No. | Activity | Timeframe |
| --- | --- | --- |
| 1 | Consideration of next financial year’s Budget and IDP process plan. Except for the legislative content, the process plan should confirm in-year reporting formats to ensure that reporting and monitoring feeds seamlessly into the Annual Report process at the end of the Budget/IDP implementation period | July |
| 2 | Implementation and monitoring of approved Budget and IDP commences (In-year financial reporting). |  |
| 3 | Finalise the 4th quarter Report for previous financial year |  |
| 4 | Submit draft 2015/2016 Annual Report to Internal Audit and Auditor-General |  |
| 5 | Municipal entities submit draft annual reports to MM |  |
| 6 | Audit/Performance committee considers draft Annual Report of municipality and entities (where relevant) | August |
| 8 | Mayor tables the unaudited Annual Report |  |
| 9 | Municipality submits draft Annual Report including consolidated annual financial statements and performance report to Auditor General |  |
| 10 | Annual Performance Report as submitted to Auditor General to be provided as input to the IDP Analysis Phase |  |
| 11 | Auditor General audits Annual Report including consolidated Annual Financial Statements and Performance data | September – October |
| 12 | Municipalities receive and start to address the Auditor General’s comments | November |
| 13 | Mayor tables Annual Report and audited Financial Statements to Council complete with the Auditor- General’s Report |  |
| 14 | Audited Annual Report is made public and representation is invited |  |
| 15 | Oversight Committee assesses Annual Report |  |
| 16 | Council adopts Oversight report | December |
| 17 | Oversight report is made public |  |
| 18 | Oversight report is submitted to relevant provincial councils |  |
| 19 | Commencement of draft Budget/ IDP finalisation for next financial year. Annual Report and Oversight Reports to be used as input | January |
| T1.7.1 |  |  |

# CHAPTER 2 – GOVERNANCE

INTRODUCTION TO GOVERNANCE

The Municipal Council uses a governance system that applies executive mayoral system. It is consisted of fourteen (14) Councillors with an Executive Mayor, Speaker and three (3) Mayoral Committee members are full time.

The Speaker presides over Ordinary and Special Council meetings and is also designated as a full time Councillor. The administration dispatch notices and agendas to Councillors forty eight (48) hours before the commencement of the council meeting as determined in the Standard Rule and Orders.

The Executive Mayor has executive powers and attends to day to day duties of the Municipal Council; and the three Mayoral Committee Members assist him in executing some of his responsibilities. One of the responsibilities of the Executive Mayor is to present the Mayoral Committee reports before Council.

The Municipality has appointed the Municipal Manager who is the head of the administration. He is responsible for day to day operations of the organization and accounts to the Executive Mayor. . Other managers who have been appointed in terms of section 56 of the Municipal Systems Act, 2000 reports directly to the Municipal Manager. It is important to highlight that the Municipality is composed of three departments, excluding the office of the Municipal Manager i.e. Corporate Services, Budget and Treasury Office and Planning and Social Development. These departments are headed by the section 56 Managers.

T2.0.1

## COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE

INTRODUCTION TO POLITICAL AND ADMINISTRATIVE GOVERNANCE

The Municipal Council is an executive mayoral system that was proclaimed in the Free State Provincial Gazette by the Minister of Cooperative Governance and Human Settlement. It consists of Sixteen (16) Councillors with an Executive Mayor, Speaker and three (3) Mayoral Committee members as full time Councillors

The Municipal Manager and managers directly accountable to the municipal manager organize administration in a manner that enables the Municipality to be responsive to the needs of the community within its jurisdiction. The Municipal Manager is the accounting officer who accounts to the political head, Executive Mayor as well as Council.  He further provides guidance and advice to the political structures and manages the administration of the institution

T2.1.0

### POLITICAL GOVERNANCE

INTRODUCTION TO POLITICAL GOVERNANCE

The Council has established the following Committees in terms of the Municipal Structures Act and the Municipal Finance Management Act:

Three Section 80 Committees that process items before they could be forwarded to the Mayoral Committee and eventually to Council i.e. Corporate Services Committee, Planning and Development Committee and Budget and Treasury Committee. Three Section 80 Committees that process items before they could be forwarded to the Mayoral Committee and eventually to Council i.e. Corporate Services Committee, Planning and Development Committee and Budget and Treasury Committee.

The different Departments of the Municipality prepare reports that are then submitted to the Section 80 Committees for deliberation. After the aforementioned Committees have processed the reports presented before them, they are forwarded to the Mayoral Committee for further processing. Thereafter these reports are taken to Council for consideration and adoption. Important to note is that the Section 80 Committees, Mayoral Committee and Council sit as per schedule of Council meetings that was adopted by the Council.

The Municipal Council has an Oversight Committee, which is composed of three members, one non-executive Councillor, one community member and one member of the Internal Audit Committee; and the Council by playing an Oversight role in the activities that are performed by the Municipality.

The Annual Report is prepared by the Performance Management Unit in collaboration with other departments. When the management is satisfied with this report it is then submitted to the Council for noting before the 31st of January of each year. Subsequent to this process it is forwarded to the Oversight Committee before the 31st March of each year for assessment and thereafter it is presented before the Council with the Committee comments and recommendations. The Annual Report and the Oversight Committee report are submitted to Departments of Treasury and Cooperative Governance and Traditional Affairs for comments. Furthermore, these reports are separately   published to the community for comments.

The Internal Audit Unit conducts audit throughout the year in terms of their audit plan and prepares Audit packs/reports that are then submitted to the Internal Audit Committee. After consideration of these reports the Audit Committee forwards its recommendations to Council for considerations. Council then resolves on the findings of the Shared Audit and Performance Committee with the intention to order the administration to remedy the findings revealed by the aforesaid Committee.

Note: MFMA S52 (a): The Mayor must provide general political guidance over the fiscal and financial affairs of the municipality

T2.1.1

|  | POLITICAL STRUCTURE MAYOR Cllr M.G Ntwanambi Exercises powers delegated to the Mayor by Council or the Executive Committee |  |  |
| --- | --- | --- | --- |
|  | SPEAKER Cllr M.J Sehanka Presides at Council meetings and exercises powers delegated to the Speaker in terms of section 59 of the Local Government: Municipal Systems Act, Act 32 of 2000. |  |  |
|  | CHIEF WHIP Cllr V.A Mona To ensure political mandates are executed |  |  |
|  | MAYORAL COMMITTEE/ EXECUTIVE COMMITTEE Cllr V.A Mona: Chairperson of the Budget and Treasury Committee Cllr MG Modise: Chairperson of the Corporate Services Committee Cllr NI Mehlomakhulu: Chairperson of Planning &Social Development Committee |  | T2.1.1 |

COUNCILLORS

The Municipal Council of Xhariep District Municipality is consisted of sixteen (16) Councilors. Six of the fourteen Councilors are directly elected and ten (10) are seconded from the three local municipalities. Five Councilors are full time i.e the Executive Mayor, Speaker and three (3) Mayoral Committee members. Three members of the Mayoral Committee are designated as Chairpersons of Section 80 Committees. Both Budget and Treasury Committee and Planning and Social Development Committee are composed of four (4) members which includes the Chairperson of the Committee. And Corporate Services Committee is composed of four (4) members. Furthermore, it has established an oversight committee which is composed of five members, i.e. three Council members, one Community member and the Chairperson of the Shared and Performance Audit Committee.

T2.1.2

POLITICAL DECISION-TAKING

The Section 80 Committees sit as per schedule of Council meeting to process the items placed before them and make recommendations to the Mayoral Committee. These items are further processed by the Mayoral Committee and forwarded to the full sitting of Council with recommendations. Then the Council pronounces itself on the issues presented before it. The decisions are taken by majority of members present at the meeting. Where members share a different view on an item under consideration, they vote on the matter, either by show of hands or through a secret ballot as stipulated in the Standing Rules and Orders of Council. All the Resolutions passed by the Council are implemented by the administration.

T2.1.3

### 2.2	ADMINISTRATIVE GOVERNANCE

INTRODUCTION TO ADMINISTRATIVE GOVERNANCE

The Municipal Manager and managers directly accountable to the municipal manager organize administration in a manner that enables the Municipality to be responsive to the needs of the community within its jurisdiction. The Municipal Manager is the accounting officer who accounts to the political head, Executive Mayor as well as Council.  He further provides guidance and advice to the political structures; also manage the administration of the institution.

The Director: Corporate Services administer the Department of Corporate Services and advice the Municipal Manager with issues relating to administration, human resources and information technology. The Chief Financial Officer administers Budget and treasury Office and advice the Municipal Manager on matters that relate to the finances of the Municipality. The Director: Planning and Social Development is responsible for the affairs of the Department of Planning and Social Development, advices and assists the Municipal Manager on all matters that relates to this department, i.e. planning, local economic development and municipal health services.

T2.2.1

|  | TOP ADMINISTRATIVE STRUCTURE TIER 1 MUNICIPAL MANAGER Mr Mazondi Martiens Kubeka |  |
| --- | --- | --- |
| Directors | EXECUTIVE DIRECTOR: Title Mbuyiselo Khapha(Acting) DIRECTOR: Corporate Services EXECUTIVE DIRECTOR: Title Montjane Clive Mogoale Chief Financial Officer(Acting) EXECUTIVE DIRECTOR: Title Mr Mopedi Sam Mohale Director: Planning & Social Development |  |
|  |  | T2.2.2 |

## COMPONENT B: INTERGOVERNMENTAL RELATIONS

INTRODUCTION TO CO-OPERATIVE GOVERNANCE AND INTERGOVERNMENTAL RELATIONS

Intergovernmental relations are mainly informal, making the system flexible to respond to changing circumstances. The approach of the Act is therefore that it does not seek to govern intergovernmental relations in its totality but provides only the broad framework in terms of which spheres of government interact with one another.

T 2.3.0

### 2.3	INTERGOVERNMENTAL RELATIONS

PROVINCIAL INTERGOVERNMENTAL STRUCTURE

The District is part of the Premiers’ Coordinating Forum which is used to facilitate intergovernmental relations between the province and local government in the province. The District also participates in Provincial Forums which include Provincial IDP Forum, Provincial Energy Forum, Provincial AIDS Forum as well as South African Local Government Association (SALGA).

T2.3.2

DISTRICT INTERGOVERNMENTAL STRUCTURES

Meetings are been held once in a quarter, whereby the District Municipality is responsible for ensuring the co-ordination of intergovernmental relations within the district municipality with local municipalities in the district. District Coordinating Forum: Forum consists of the Executive Mayor and 3 primary members of which is the Local Mayors.

Technical Support Committee

Forum consists of the District Municipal Manager and 3 primary members (Local Municipal Manager). The forum must meet at least once per year with service providers and other role players concerned with the development in the district to co-ordinate effective provision of services and planning in the district.

T2.3.4

## COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION

OVERVIEW OF PUBLIC ACCOUNTABILITY AND PARTICIPATION

The municipality has developed a comprehensive public participation strategy which is integrated in the development of the IDP and the Budget, the Municipal website if often used to publicise all the developments in the municipality including calls for public participation and comments on the IDP and Budget. After the adoption of the annual report the municipality also avail this document for public scrutiny as recommended by the MSA act 32 of 2000.

T 2.4.0

### 2.4	PUBLIC MEETINGS

COMMUNICATION, PARTICIPATION AND FORUMS In consideration with the mechanisms of effective public participation, the following processes and aspects were taken in consideration and were implemented as required. CONTEXT OF PUBLIC PARTICIPATION AS IMPLEMENTED Four major functions can be aligned with the public participation process namely: - Needs identification; - Identification of appropriateness of proposed solutions; - Community ownership and buy-in; and - Empowerment. MECHANISMS FOR PARTICIPATION The following mechanisms for participation were utilized: - IDP Representative Forum (IDP RF) This forum will represent all stakeholders and will be as inclusive as possible. Efforts will be made to bring additional organizations into the IDP RF and ensure their continued participation throughout the process. - Media Local newspapers were used to inform the community of the progress of the IDP and the Community consultation dates. - Information sheets These were prepared in English and be distributed to communities prier the start of all the meetings The DM’s Website The DM’s website was also utilized to communicate and inform the community. Copies of the IDP and Budget were placed on the website for people to download T2.4.1

| Public Meetings |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Nature and purpose of meeting | Date of events | Number of Participating Municipal Councillors | Number of Participating Municipal Administrators | Number of Community members attending | Manner of feedback given to community |
| IDP and Budget Public Participation | 20-03-2015 | 1 | 5 | 46 | IDP and Budget presentations |
| IDP and Budget Public Participation | 23-03-2015 | 0 | 9 | 39 | IDP and Budget presentations |
| IDP and Budget Public Participation | 19-05-2015 | 0 | 4 | 43 | IDP and Budget presentations |
| IDP and Budget Public Participation | 20-05-2015 | 1 | 5 | 27 | IDP and Budget presentations |
| T2.4.3 |  |  |  |  |  |

COMMENT ON THE EFFECTIVENESS OF THE PUBLIC MEETINGS HELD:

As per the requirements of the Municipal Systems act and the Municipal Finance Management Act the municipality has a series of outreach consultations including the IDP and Budget consultative sessions with the communities of the Xhariep District. The Municipal council has also adopted public participation strategy

The Local Government Municipal Management Act (MFMA, Act 56 of 2003) puts at the Centre of this process the voice of the people. The MFMA calls for active participation and input from the public in the budgeting process as well as the alignment of the budget to the IDP

In order to ensure public participation in local governance, government has over time put in place various pieces of legislation and policies. The following are some of the legislative and policy provisions aimed at fostering public participation at local government level:

The Constitution – 1996

Municipal Structures Act &White Paper on Local Government – 1998

Municipal Systems Act-2000

Municipal Finance Management Act-2003

Municipal Property Rates Act-2004

Municipal Finance Management Act-2003

Guidelines for Operation of Ward Committees-2005

T2.4.3.1

### 2.5	IDP PARTICIPATION AND ALIGNMENT

| IDP Participation and Alignment Criteria* | Yes/No |
| --- | --- |
| Does the municipality have impact, outcome, input, output indicators? | Yes |
| Does the IDP have priorities, objectives, KPIs, development strategies? | Yes |
| Does the IDP have multi-year targets? | Yes |
| Are the above aligned and can they calculate into a score? | Yes |
| Does the budget align directly to the KPIs in the strategic plan? | Yes |
| Do the IDP KPIs align to the Section 57 Managers | Yes |
| Do the IDP KPIs lead to functional area KPIs as per the SDBIP? | Yes |
| Do the IDP KPIs align with the provincial KPIs on the 12 Outcomes | Yes |
| Were the indicators communicated to the public? | Yes |
| Were the four quarter aligned reports submitted within stipulated time frames? | Yes |
| * Section 26 Municipal Systems Act 2000 | T2.5.1 |

## COMPONENT D: CORPORATE GOVERNANCE

OVERVIEW OF CORPORATE GOVERNANCE

As the Head of Administration the Municipal Manager is responsible for the following tasks:

-The formation and development of an economical, effective, efficient and accountable administration.

- The management of the municipality’s administration in accordance with legislation applicable to the municipality.

-The implementation of the municipality’s integrated development plan.

-The management and provision of services to the local communities in a sustainable and equitable manner.      -The appointment of staff subject to the Employment Equity Act, 1998.

-The management and effective utilisation and training of staff.

-The maintenance of discipline of staff.

-The promotion of sound labour relations and compliance with labour legislation.

- Advising the political structures and political office bearers of the municipality.

-Managing communications between the municipality’s administration and its political structures and political office bearers.

-Carrying out the decisions of the political structures and political office bearers of the municipality.

-The administration and implementation of the municipality’s by-laws and other legislation.

-The exercise of any powers and the performance of any duties delegated by the municipal council.

-Facilitating participation by the local community in the affairs of the municipality.

-The implementation of national and provincial legislation.

T2.6.0

### 2.6	RISK MANAGEMENT

RISK MANAGEMENT

The Xhariep District Municipality is committed to the effective risk management and treatment of risk in order to achieve its objectives. Management of risk is the responsibility of all Executive, Senior Management and employees and Section 62 (1) (c) (i) of the MFMA requires that:

“The municipality has and maintains: Effective, efficient and transparent systems of financial and risk management and internal control.”

Treasury Regulations S3.2.1 further prescribes that the Accounting Officer must ensure that a risk assessment is conducted regularly to identify emerging risks of the institution. A risk management strategy, which must include a fraud prevention plan, must be used to direct internal audit effort and priority, and to determine the skills required of managers and staff to improve controls and to manage these risks. The strategy must be clearly communicated to all officials to ensure that the risk management strategy is incorporated into the language and culture of the institution and thus creating an environment of working together in a consistent and integrated manner, with the overall objective of reducing risk, as far as reasonably practicable.

The embedding of risk management within the municipality is a proactive approach in mitigation of events that will have a negative impact in the achievement of municipal goals and objectives; risk management thus assists Xhariep District Municipality in:

1. Supporting the efficient use of resources (Risk Based decision making)

2. Promoting continuous improvement

3. Minimizing surprises,

4. Reassuring stakeholders,

5. Rationalization of capital and financial issues,

6. Helps internal audit to comply with Internal Audit Framework and IIA Standards

7. Continuity of service delivery

The Accounting Officer commits the Xhariep District Municipality to a process of risk management that is aligned to the principles of good corporate governance, as supported by:

Municipal Finance Management Act (MFMA), Act 56 of 2003;

Municipal Systems Act (MSA) Act 32 of 2000);

Municipal Structures Act (MSA) Act 117 of 1998); and

Treasury Regulations 3.2.1                                                                                                                                             T2.6.1

### 2.7	ANTI-CORRUPTION AND FRAUD

FRAUD AND ANTI-CORRUPTION STRATEGY

Fraud is defined as the intentional, false representation or concealment of a material fact for the purpose of inducing another to act upon it to his or her injury.

Xhariep District Municipality has a ZERO TOLERANCE to Fraud and Corruption and thus has the intent to promote consistent organizational behavior by providing guidelines and assigning responsibilities for the development of controls and conduction of investigations relating to fraud and corruption.

The fraud prevention strategy and policy are such documents designed to align Xhariep District Municipality with Municipal Finance Management Act which states that each municipality must develop an effective, efficient and transparent system of financial, risk management and internal control. Fighting against corruption is a national priority and Xhariep District Municipality positions itself to combat the scourge of fraud and corruption.

The fraud and corruption strategy demonstrates the stance of the municipality in preventing and detecting fraudulent and corrupt activities as well as corrective action when fraud has been committed

T2.7.1

### 2.8	SUPPLY CHAIN MANAGEMENT

OVERVIEW SUPPLY CHAIN MANAGEMENT

As far as the processes are concerned, a MEMO for DEMAND and ACQUISITION has been developed by the municipality to manage, control and monitor procurement of goods and services. The MEMO is signed by the responsible manager to confirm the need of the service or product, the manager for Budget and Reporting Unit confirms the budget availability, relevant HOD recommends as well as the CFO and the Accounting Officer/Municipal Manager or a Senior Manager designated to act in the capacity of the Municipal Manager, finally approves the MEMO for DEMAND and ACQUISITION. During 2015/2016 financial year, Supply Chain Management Policy of the Municipality went for a review and a workshop was conducted to employees of the municipality in February 2016. The policy was adopted by council on the 7th of June 2016 for implementation in the 2016/2017 financial year. The municipality also uses the Procurement Procedure Manual to help it in achieving its policy objectives.

T2.8.1

### 2.10	WEBSITES

| Municipal Website : Content and Currency of Material |  |  |
| --- | --- | --- |
| Documents published on the Municipality's / Entity's Website | Yes / No | Publishing Date |
| Current annual and adjustments budgets and all budget-related documents | Yes |  |
| All current budget-related policies | Yes |  |
| The previous annual report (2014/2015) | Yes |  |
| The annual report (2015/2016) published/to be published | - |  |
| All current performance agreements required in terms of section 57(1)(b) of the Municipal Systems Act (2015/2016) and resulting scorecards | Yes |  |
| All service delivery agreements (2015/2016) | No (documents were not submitted to IT for upload on the municipal website) |  |
| All long-term borrowing contracts (2015/2016) | No (documents were not submitted to IT for upload on the municipal website) |  |
| All supply chain management contracts above a prescribed value (give value) for 2015/2016 | Yes (contract register) |  |
| An information statement containing a list of assets over a prescribed value that have been disposed of in terms of section 14 (2) or (4) during 2015/2016 | No (documents were not submitted to IT for upload on the municipal website) |  |
| Contracts agreed in 2015/2016 to which subsection (1) of section 33 apply, subject to subsection (3) of that section | No (documents were not submitted to IT for upload on the municipal website) |  |
| Public-private partnership agreements referred to in section 120 made in 2015/2016 | No (documents were not submitted to IT for upload on the municipal website) |  |
| All quarterly reports tabled in the council in terms of section 52 (d) during 2015/2016 | yes |  |
| *The municipal website does not show the dates of uploading of the documents. |  | T2.10.1 |

COMMENT MUNICIPAL WEBSITE CONTENT AND ACCESS

The website of the Municipality is fully functional, all documents that were requested by user departments to be uploaded on the municipal website have been loaded in the 2015/16 financial year.

T2.10.1.1

# CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)

INTRODUCTION

The district municipality is performing the functions of Municipal Health Services and Disaster Management with effect from December 2009. Critically, the Municipal Structures Amendment Act (Act 33 of 2000) provides for an extensive annual review of the division of powers and functions between Category B and Category C to ensure effective implementation of these assigned powers following an advice provided by the Municipal Demarcation Board emanating from the Boards’ annual capacity assessment report.

T3.0.1

## COMPONENT A: BASIC SERVICES

| Financial Performance 2015/2016: Planning Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2014/2015 | 2015/2016 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 11 549 | 12 811 | 12 757 | 11 549 | 1 208 |
| Expenditure: |  |  |  |  |  |
| Employees | 7 207 | 7 957 | 7 957 | 7 195 | 762 |
| Repairs and Maintenance |  |  |  |  |  |
| Other | 4 602 | 4 854 | 4 800 | 4 869 | (69) |
| Total Operational Expenditure | 11 809 | 12 811 | 12 757 | 12 064 | 693 |
| Net Operational Expenditure | (260) | 0 | 0 | (515) | (515) |
|  |  |  |  |  | T3.10.5 |

### 3.11	LOCAL ECONOMIC DEVELOPMENT (INCLUDING TOURISM AND MARKET PLACES)

INTRODUCTION OF ECONOMIC DEVELOPMENT

Tourism is expected to grow through the construction of major Projects that are currently underway like Trompsburg Hospital, Gariepdam Fish Demonstration Centre, shoe production at Arts and Craft Centre.

A new strategy for marketing the Free State was developed and launched at the Tourism Indaba that took place in May 2013. Tourism Awareness Campaigns are conducted bi-annually with the aim to educate and provide knowledge of opportunities within the tourism industry

T3.11.1

| Jobs Created during 2015/2016 by LED Initiatives (Excluding EPWP projects) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Total Jobs created / Top 3 initiatives | Jobs created | Jobs lost/displaced by other initiatives | Net total jobs created in year | Method of validating jobs created/lost |
|  | No. | No. | No. |  |
| Total (all initiatives) |  |  |  |  |
| 2014/2015 | 16 |  | 16 |  |
| 2015/2016 | 35 |  | 270 000 | Identify beneficiaries, reporting, monitoring and implementing |
| Initiative A (2015/2016)Reddersburg Irrigation Project | 25 |  | 270 000 | Identify beneficiaries, reporting, monitoring and implementing |
| Initiative B (2015/2016) | 10 |  | 270 000 | Identify beneficiaries, reporting, monitoring and implementing |
| Initiative C (2015/2016) | - | - | - | - |
|  |  |  |  | T3.11.5 |

| Job creation through EPWP* projects |  |  |
| --- | --- | --- |
| Details | EPWP Projects | Jobs created through EPWP projects |
|  | No. | No. |
| 2013/2014 | 4 | 275 |
| 2014/2015 | 1 | 123 |
| 2015/2016 | 4 | 189 |
| * - Extended Public Works Programme |  | T3.11.6 |

| Employees: Local Economic Development Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2014/2015 | 2015/2016 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 0 | 0% |
| 4 – 6 | 2 | 2 | 2 | 0 | 0% |
| 7 – 9 | 0 | 0 | 0 | 0 | 0% |
| 10 – 12 | 0 | 0 | 0 | 0 | 0% |
| 13 – 15 | 0 | 0 | 0 | 0 | 0% |
| 16 – 18 | 0 | 0 | 0 | 0 | 0% |
| 19 – 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 3 | 3 | 3 | 0 | 0% |
| T3.11.8 |  |  |  |  |  |

| Financial Performance 2015/2016: Local Economic Development Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2014/2015 | 2015/2016 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue |  |  |  |  |  |
| Expenditure: |  |  |  |  |  |
| Employees |  |  |  |  |  |
| Repairs and Maintenance |  |  |  |  |  |
| Other |  |  |  |  |  |
| Total Operational Expenditure |  |  |  |  |  |
| Net Operational Expenditure |  |  |  |  |  |
|  |  |  |  |  | T3.11.9 |

### 3.64	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC

INTRODUCTION TO HEALTH INSPECTIONS; FOOD AND ABATTOIR LICENCING AND INSPECTIONS, ETC

A key role responsibility in rendering an effective Municipal Health Services is the monitoring of  food and government premises in order to ensure compliance with R926, Foodstuffs, Cosmetics and Disinfectants act 1972 (Act no. 54 of 1972) and the National health act, 2003 (Act no 63 of 2003).

District Environmental Health Practitioners conduct health inspections of premises and issue out compliance notices to food premises which are found to be non-compliant with the set legislation. A certificate of acceptability (COA) is issued in accordance with the legislation to compliant premises.  Certificate of health are issued to compliant ECD’s and old age homes. Operational licences are the competency of the local municipality and other stakeholders.

Surveillance of premises is also conducted to insure vector control and to monitor health and hygiene standards of premises.

The following activities are measured:  These ensure that there is constant monitoring of compliance.

No. of COA’s issued

No. of non-compliance notices issued

No. of health inspections conducted.

Bimonthly raids are conducted with the assistance of SAPS to curb non -compliance by shop owners and seize expired foods. Monthly monitoring of all premises is conducted by the Environmental Health Practitioners.

T3.64.1

### 3.67	OTHER (DISASTER MANAGEMENT)

INTRODUCTION TO DISASTER MANAGEMENT

Disaster Management is a continuous and integrated multi-sectoral and multi-disciplinary process of planning and implementation of measures aimed at disaster prevention, -mitigation, -preparedness, -response, -recovery and –rehabilitation

Top Four Service Delivery Priorities:

1. Community Safety

2. Preparedness

3. Recovery and Rehabilitation

4. Educational Program

The DM Unit main role is to ensure a safe and unwavering environment to the Xhariep district community. Through proper planning the Unit will be able to build resilient communities through the Disaster Management Activities within the district Municipality. A budget for the review of the DM Plan, DM training and DM relief was approved to enhance the previous achievements and to implement the plan for mitigation through education, awareness and training. The DM Unit played a vital role to assist disaster stricken victims throughout the district in rebuilding of houses and rehabilitation.                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                    T3.67.1

| Employees: Disaster Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2014/2015 | 2015/2016 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 1 | 1 | 1 | 0 | 0% |
| 4 - 6 | 0 | 2 | 2 | 0 | 0% |
| 7 - 9 | 2 | 1 | 1 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 3 | 4 | 4 | 0 | 0% |
| T3.67.4 |  |  |  |  |  |

COMMENT ON THE PERFORMANCE OF DISASTER MANAGEMENT

The Disaster Management Plan and Disaster Management Framework were reviewed as compelled by the Disaster Management Act (57/2002). Regular Disaster Management Advisory Forum meetings are held. Assistance with Disaster Management in general is given to all Local Municipalities in the District. The Municipality is trying to educate the communities through awareness campaigns and with Disaster Management Programs at the primary schools. This, in a way will help us to prepare for and minimizes the impact of disastrous incidents in the area. Training and workshop for Councillors, Ward Committees, Disaster Management Forums and Volunteer Groups are planned to enhance our Disaster Management educational program.

The Disaster Management Unit attends to most of the incidents within the District to record the incident and report to the authorities and the respective relevant parties. Due to financial constraints, the Unit cannot support all the victims financially.

T3.67.7

## COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES

This component includes: corporate policy offices, financial services, human resource services, ICT services

INTRODUCTION TO CORPORATE POLICY OFFICES

The Municipality has developed required policies as per directive of legislations that govern the local sphere of government for all aspects of the Municipality, i.e. financial services, Human Resources, performance management, risk management, disaster management, Local Economic Development strategy, Expanded Public Works Programme Policy and Internal audit Charter.

T3.69.0

### 3.69	EXECUTIVE AND COUNCIL

This component includes: Executive office (mayor; councilors; and municipal manager).

INTRODUCTION TO EXECUTIVE AND COUNCIL

Municipality is currently executing three service delivery related matters, i.e. local economic development,   Disaster Management and Municipal Health Services. The Local Economic Development Division that is located within the Department of Planning and Social Development has made strides in providing financial assistance and providing training to Small Micro and Medium Enterprises. The Municipality has assisted interested individuals or group of people to establish their own businesses, in particular cooperatives.

The Environmental Health Services Division that is also located within the Department of Planning and Social Development is monitoring the quality of drinking water and final waste water effluent from different local municipalities that fall within its jurisdiction on frequent intervals as required by applicable legislations and policies. Furthermore this division insures compliance of food premises and local municipalities’ landfill sites.

The Disaster Management Division is located in the Office of the Municipal Manager. The division is responsible to ensure a safe and unwavering environment to the Xhariep district community.                                                                                                                                                                                           T3.69.1

| Financial Performance 2015/2016: The Executive and Council |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2014/2015 | 2015/2016 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 7 966 | 11 993 | 12 113 | 8 216 | 3 897 |
| Expenditure: |  |  |  |  |  |
| Employees | 10 384 | 8 531 | 8 731 | 9 679 | (948) |
| Repairs and Maintenance | 0 |  |  |  |  |
| Other | 5 759 | 6 762 | 3 382 | 11693 | (8 311) |
| Total Operational Expenditure | 16 143 | 15 293 | 15 413 | 21 372 | (5 959) |
| Net Operational Expenditure | (8 177) | (3 300) | 0 | (13 156) | (13 156) |
|  |  |  |  |  | T3.69.5 |

### 3.70	FINANCIAL SERVICES

INTRODUCTION FINANCIAL SERVICES

The Budget and Treasury Office is responsible for the financial administration and management of the municipality.

T3.70.1

| Employees: Financial Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2014/2015 | 2015/2016 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 4 | 4 | 4 | 0 | 0% |
| 4 - 6 | 5 | 6 | 6 | 0 | 0% |
| 7 - 9 | 8 | 6 | 6 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 17 | 16 | 16 | 0 | 0% |
| . T3.70.4 |  |  |  |  |  |

| Financial Performance 2015/2016: Financial Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2014/2015 | 2015/2016 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 14 120 | 11 337 | 11 217 | 14 280 | (3 063) |
| Expenditure: |  |  |  |  |  |
| Employees | 8 289 | 9 506 | 9 226 | 8 023 | 1 203 |
| Repairs and Maintenance | 0 |  |  |  |  |
| Other | 2 899 | 1 831 | 1 991 | 3 127 | (1 136) |
| Total Operational Expenditure | 11 188 | 11 337 | 11 217 | 11 150 | 67 |
| Net Operational Expenditure | 2 932 | 0 | 0 | 3 130 | 3 130 |
|  |  |  |  |  | T3.70.5 |

### 3.71	HUMAN RESOURCE SERVICES

INTRODUCTION TO HUMAN RESOURCE SERVICES

The purpose of Human Resources Services at the institution is cater for human resource development needs of the employees, remuneration and benefits of employees, labour relations and human resources information that relates to leave management and employee personal information.

The management set itself priorities to overhaul the services the institution provides to its internal clients, the key three amongst them were;

Purify leave management

Provide accurate inputs- information to payroll

Recruit people with required competencies

So far this division has made major strides in insuring that leave of employees is managed in accordance with Municipal Human Resources Policy Manual. Every week there is reconciliation of attendance registers, VIP register with completed leave forms; and follow-ups on employees who did not sign registers or completed leave forms. The principle of no work no pay is applied on employees who are found not to have followed proper procedure in absenting themselves from work.

The official providing information to employees in payroll on remuneration and benefits of employees work s closely with the payroll division in order to ensure that accurate information is forwarded to division before processing the salaries of councillors and employees. The inputs are compiled, checked, approved by different individuals in order to ensure that correct information is provided to payroll. Such information is forwarded to payroll on or before the 15th of each month in order to give officials in payroll an ample time to process the remuneration and benefits of both councillors and officials

The Human Resources Division advertises all vacant positions as required by the Human Resources Policy Manual and set competencies that are needed from the interested individuals. It is important to highlight that the Municipality appoints only incumbents who meets minimum competency requirements as placed on the advertisement.

T3.71.1

| Employees: Human Resource Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2014/2015 | 2015/2016 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 2 | 1 | 1 | 0 | 0% |
| 4 - 6 | 5 | 3 | 3 | 0 | 0% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 8 | 5 | 5 | 0 | 0% |
| T3.71.4 |  |  |  |  |  |

| Financial Performance 2015/2016: Corporate service |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2014/2015 | 2015/2016 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 19 401 | 16 195 | 16 292 | 19 401 | (3 109) |
| Expenditure: |  |  |  |  |  |
| Employees | 13 887 | 14 818 | 14 600 | 13 684 | 916 |
| Repairs and Maintenance | 307 |  | 218 | 298 | (80) |
| Other | 1 148 | 1 377 | 1 474 | 1829 | (355) |
| Total Operational Expenditure | 15 342 | 16 195 | 16 292 | 15 797 | 495 |
| Net Operational Expenditure | 4 059 | 0 | 0 | 3 604 | 3604 |
|  |  |  |  |  | T3.71.5 |

### 3.72	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

This component includes: Information and Communication Technology (ICT) services.

INTRODUCTION TO INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

The IT Unit is an integral part of Xhariep District Municipality and plays a vital role as an abler of the institution. Our main aim as a unit is to ensure that the business needs of the municipality in relation to IT are prioritised and that the IT Strategy is aligned to those needs.

The ICT division wants to ensure that the municipality implements IT solutions that will help with the smooth operation of the municipality, by identifying gabs in the systems, processes, IT Infrastructure etc. to ensure proper solutions are implemented in response to the identified gaps.

The Municipality also want to ensure that the institution gets value for money for its investment in the IT

As the ICT unit the focus in the 2015/2016 financial year was to further improve on the IT Infrastructure and to implement relevant solutions. The municipality was hoping to get Microsoft License for Offices Suite, MS Operating System and Email Exchanger

Serviced the fire extinguisher in the server room

T3.72.1

| Employees: ICT Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2014/2015 | 2015/2016 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 1 | 1 | 1 | 0 | 0% |
| 4 - 6 | 1 | 1 | 1 | 0 | 0% |
| 7 - 9 | 0 | 0 | 0 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 2 | 2 | 2 | 0 | 0% |
| T3.72.4 |  |  |  |  |  |

PERFORMANCE OF ICT SERVICES OVERALL:

The IT Unit has achieved so many successes in the 2015/2016 Financial Year to bring the IT environment to a stable position. There is stability with our Financial Information Systems. Documents are uploaded regularly and within acceptable time on the municipal Website. The environment is pretty much stable. The challenges where experienced with the License that could not be purchased as budget was shifted to other projects and budget that was insufficient

T3.72.5

## COMPONENT K: ORGANISATIONAL PERFORMANCE SCORECARD

This component includes:  Annual Performance Scorecard Report for the current year.

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE | REAON FOR DEVIATION |  | CORRECTIVE MEASURE | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Municipal Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D1 | To provide open transparent corruption free governance | MT&ID | Implementation anti-fraud, anti-corruption and risk prevention initiatives | No of initiatives implemented to create awareness amongst Councillors and Staff | 1 | 0 | (1) | This is due to the resignation of the Chief Risk Officer | The municipality filled the position of the Chief Risk Officer 0n the 01st March 2016. The newly appointed Chief Risk Officer got released from his duties to non-performance |  | 30-06-15 | 29-06-15 |  | 1 day |
| D2 | To provide open transparent corruption free governance | MT&ID | Advise Management and report to Risk Management Committee and SAPC on Risk Management processes | No of reports submitted to Risk Management Committee and SAPC on Risk Management processes | 4 | 0 | (4) | This is due to the non-sitting of the Risk Management Committee and the resignation of the Chief Risk Officer | The municipality filled the position of the Chief Risk Officer 0n the 01st March 2016. The newly appointed Chief Risk Officer got released from his duties to non-performance |  | New KPI | - |  | - |
| D3 | To create an efficient, effective and accountable administration | MT&ID | Annual Risk assessment and Fraud Risk assessment conducted on 31 July 2015 | Final Risk assessment report and Risk register | 31-07-16 | 0 | (31-07-16) | Risk Register was compiled but not approved by the Risk Management Committee | Chief Risk Officer to stick to timeframes determined by the municipality to meet target dates |  | New KPI | - |  | - |
| D4 | To create an efficient, effective and accountable administration | MT&ID | Quarterly reports to Management | No of progress reports on Risk Implementation Plan | 4 | 0 | (4) | This is due to the non-sitting of the Risk Management Committee and the resignation of the Chief Risk Officer | The municipality filled the position of the Chief Risk Officer 0n the 01st March 2016. The newly appointed Chief Risk Officer got released from his duties to non-performance |  | New KPI | - |  | - |
| D5 | To create an efficient, effective and accountable administration | MT&ID | Review the antifraud and corruption policy by 30 June 2016 | Approved antifraud and corruption policy | 31-08-15 | 0 | (31-08-15) | This is due to the resignation of the Chief Risk Officer | The municipality filled the position of the Chief Risk Officer on the 01st March 2016. The newly appointed Chief Risk Officer got released from his duties to non-performance |  | 30-03-15 | 29-08-14 |  | 7 months |
| D6 | To create an efficient, effective and accountable administration | MT&ID | Advise the accounting officer and report to the audit committee on the implementation of the internal audit plan and related matters (MFMA, Act 56 of 2003, Section 165(2)(b). | No of quarterly reports prepared for Audit Committee | 4 | 4 | 0 | - | - |  | 4 | 4 |  | 0 |
| D7 | To create an efficient, effective and accountable administration | MT&ID | Functional Internal Audit Unit (MFMA 62(1)) | Risk based audit plan approved by Audit Committee by 31 August 2015 | 31-08-15 | 30-11-15 | 3 months | This is due to the suspension of the Internal Audit employees | The municipality filled the vacancies of the Internal Audit on the 01st March 2016 |  | 31-08-14 | 25-08-14 |  | 6 days |
| D8 | To implement effective performance management system by 30 June 2016 | MT&ID | Compile draft Annual Report for submission to Council by 31 January 2016 | Draft Annual Report approved by Council | 31-01-16 | 28-01-16 | 03 days | - | - |  | 31-01-15 | 30-01-16 |  | 01 day |
| D9 | To implement effective performance management system by 30 June 2016 | MT&ID | Compile Oversight Report on Annual Report and submit to Council by 31 March 2016 (MFMA 129(1) and MSA 46(2) | Oversight Report adopted by Council | 31-03-16 | 30-03-16 | 1 day | - | - |  | 31-03-15 | 31-03-15 |  | 0 |
| D10 | To implement effective performance management system by 30 June 2016 | MT&ID | Compile the Mid- Year budget and Performance Report by 25 January 2016 (MFMA S72) | Mid-year report submissions (Mayor, Provincial and National Treasury) by 25 January 2016 | 25-01-16 | 25-01-16 | 0 | - | - |  | 25-01-15 | 26-01-15 |  | (1) |
| D11 | To implement effective performance management system by 30 June 2016 | GGPP | Implement Council Resolutions within prescribed timeframe stipulated on system | % resolutions implemented within timeframe | 95% | 63% | (32%) | The outturning resolution is implemented over a period of time due to project requirements | Follow up on all outstanding resolutions and report progress thereof |  | 95% | 86.96% |  | (13.04%) |
| D12 | To create an efficient, effective and accountable administration | BSD | To ensure access to services delivery across the Municipal area in order to improve the livelihood of communities | No of municipal disaster management advisory forum meetings held (section 51 of the Disaster Management Act 2002) | 4 | 4 | 0 | - | - |  | 4 | 4 |  | 0 |
| D13 | To create an efficient, effective and accountable administration | BSD | To ensure access to services delivery across the Municipal area in order to improve the livelihood of communities | No of disaster management reports submitted to management/Council | 4 | 3 | (1) | This is due to the non-sitting of Council in the second quarter | Council to sit as per the approved schedule of Council meetings to consider reports |  | 4 | 2 |  | (2) |
| D14 | To create an efficient, effective and accountable administration | BSD | To ensure access to services delivery across the Municipal area in order to improve the livelihood of communities | No of Disaster Management basic awareness sessions held in the District | 2 | 1 | (1) | The budget allocated to conduct awareness sessions is not sufficient to mobilise communities, purchasing of banners and awareness raising material | These campaigns will be conducted when the financial position of municipality improves |  | 3 | 3 |  | 0 |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT |  | ANNUAL TARGET | ACTUAL | VARIANCE |  | REASON FOR DEVIATION | CORRECTIVE MEASURE |  | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Financial Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D15 | To improve financial viability of the municipality | MFV&M | Production of annual Audit file by mid-August | No of Audit files produced | 1 |  | 1 |  | 0 | - |  | - | 1 | 1 | 0 |
| D16 | To improve financial viability of the municipality | MFV&M | Closing of all municipal financial accounts at the end of each month in terms of sec 65 of the MFMA | No of monthly reports | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D17 | To improve financial viability of the municipality | MFV&M | No of creditors reconciliations done monthly (30 days) | No of creditors reconciliation reports submitted | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D18 | To improve financial viability of the municipality | MFV&M | Financial Viability: Cost coverage (Reg 796) | Cost coverage ((Available cash+ investments)/ Monthly fixed operating expenditure (SA8) | >1 |  | 0.02 |  | (0.98) | Available cash and investment is less than the monthly operating expenditure due to R14.2 million cut from financial assistance |  | Improve on the cash management of the municipality | >1 | 0.17 | (0.83) |
| D19 | To improve financial viability of the municipality | MFV&M | Financial Viability: Debt coverage (Reg 796) | Debt coverage (Total operating revenue-operating grants received)/debt service payments due within the year) (SA8) | >1 |  | (22.80) |  | No probability of recovering debt | Total operating revenue excluding grants contributes only to less than 5% of the revenue total |  | Municipality to engage COGTA and Treasury in finding other sources of funding | >1 | (46.55) | (45.55) |
| D20 | To improve financial viability of the municipality | MFV&M | Monthly notification of awards over R 100 000 | List of awards | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D21 | To improve financial viability of the municipality | GGPP | Annual advertisement for updating supplier data base by 31 March 2016 | Advertisement placed in local newspaper | 31-03-16 |  | 29-02-16 |  | 1 month | - |  | - | 31-03-2015 | 20-03-2015 | 11 days |
| D22 | To improve financial viability of the municipality | MFV&M | Effective management of payroll by providing the section 66 payroll report on a monthly basis | Monthly reports to management ito sec 66 of the MFMA | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D23 | To improve financial viability of the municipality | MFV&M | Ensure the submission of IRP5's | IRP5's submitted not later than 30 May 2016 to SARS | 30-05-16 |  | 25-05-16 |  | 5 days | - |  | - | 30-05-2015 | 19-05-2015 | 11 days |
| D24 | To improve financial viability of the municipality | MFV&M | Monthly salary reconciliations | No of reconciliations done | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D25 | To improve financial viability of the municipality | GGPP | Implement Council Resolutions within prescribed timeframe stipulated on system | % resolutions implemented within timeframe | 95% |  | 77% |  | (18%) | The outturning resolution is implemented over a period of time due to project requirements |  | Follow up on all outstanding resolutions and report progress thereof | 95% | 87.93% | (12.07%) |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE |  | REASON FOR DEVIATION | CORRECTIVE MEASURE | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Directorate: Corporate Services |  |  |  |  |  |  |  |  |  |  |  |  |
| D26 | To implement effective performance management system by June 2016 | MT&ID | Draw quarterly resolution execution report for all directorates | No of reports | 4 | 4 |  | 0 | - | - | 4 | 4 | 0 |
| D27 | To create an efficient, effective and accountable administration | MT&ID | Implement Council resolutions within required timeframe | % of Council resolutions implementation within required timeframe | 95% | 71.25% |  | (23.75) | The outturning resolution is implemented over a period of time due to project requirements | Follow up on all outstanding resolutions and report progress thereof | 95% | 62.38% | (37.62%) |
| D28 | To create an efficient, effective and accountable administration | MT&ID | Distribute agendas for all scheduled meetings to all relevant Councillors and officials | Agendas for the scheduled meetings distributed at least 2 days before the meeting | 2 days before the meeting | 0 |  | (2 days) | This is due to non-availability of a Councillor in the fourth quarter | The Administration to check availability of Councillors before delivery of agenda | Within 48 hours | Within 48 hours | 0 |
| D29 | To create an efficient, effective and accountable administration | MT&ID | Distribute Council resolutions within 7 working days of each meeting | Resolutions distributed within prescribed timeframe (7 working days) | 7 working days | 7 working days |  | 0 | - | - | 7 working days | 0 | (7 working days) |
| D30 | To create an efficient, effective and accountable administration | MT&ID | Training and development of personnel | Total number of training courses attended by 30 June 2016 | (1MFMP) | (1MFMP) |  | 0 | - | - | 23 | 2 | (21) |
| D31 | To create an efficient, effective and accountable administration | MT&ID | Training and development of personnel | % of courses resulting in competency certificates by 30 June 2016. | 95% | 95% |  | 0 | - | - | 95% | 0% | (95%) |
| D32 | To create an efficient, effective and accountable administration | MT&ID | Training and development of personnel | Total number of employees attending training courses by 30 June 2016 | 11 | 11 |  | 0 | - | - | 75 | 10 | (65) |
| D33 | To create an efficient, effective and accountable administration | MT&ID | Training and development of personnel | Total number of skills development forum meetings held on or before 30 June 2016 | 2 | 2 |  | 0 | - | - | New KPI | - | - |
| D34 | To create an efficient, effective and accountable administration | MT&ID | Training and development of personnel | WSP approved by the LLF and submitted to LGSETA on or before 30 April 2016 | 30-04-16 | 29-04-16 |  | 1 day | - | - | 30-04-15 | 30-04-15 | 0 |
| D35 | To create an efficient, effective and accountable administration | MT&ID | Training and development of personnel | % of employees from the designated groups | 95% | 98% |  | 2% | - | - | 95% | 97.7% | 2.7% |
| D36 | To create an efficient, effective and accountable administration | MT&ID | Improve labour relations | No of LLF meetings held as planned by 30 June 2016. | 12 | 2 |  | (10) | This is due to unavailability of members | Appointment of a new Committee in the 2016/2017 financial year | 6 | 3 | (3) |
| D37 | Training and supervision to ensure health and safety of employees in the workplace | MT&ID | Training of employees on Occupational Health and Safety(OHS) | No. of employees trained on OHS before 31-Mar-2016 | 20 | 35 |  | 15 | - | - | New KPI | - | - |
| D38 | Compliance with the Sec.8(2) of the OHS Act | MT&ID | Development of Occupational Health and Safety (OHS)Policy | Approval of the OHS Policy before 31-Mar-2016 | 31-03-16 | 30-03-16 |  | 1 day | - | - | New KPI | - | - |
| D39 | Compliance with the Sec.8(2) of the OHS Act | MT&ID | Training of employees on Disciplinary procedures | Employees trained on Disciplinary procedures before 31March 2016 | 31-03-16 | 28-01-16 |  | 4 days | - | - | New KPI | - | - |
| D40 | To create an efficient, effective and accountable administration | GGPP | Public Participation Plan in place | Review of the Public Participation Plan/Strategy on or before 30 June 2016 | 30-06-16 | 28-01-16 |  | 5 months | - | - | New KPI | - | - |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT |  | ANNUAL TARGET |  | ACTUAL VARIANCE |  | REASON FOR DEVIATION | CORRECTIVE MEASURE |  | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning and Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D41 | To create an efficient, effective and accountable administration | LED | To report on the EPWP progress, grant, staff and wages paid |  | No of monthly reports submitted to the MM/ Council | 12 | 12 |  | 0 | - |  | - | 12 | 5 | (7) |
| D42 | To create an efficient, effective and accountable administration | LED | To review the District EPWP Policy by 30/06/2016 |  | District EPWP Policy reviewed and approved by Council on or before 30 June 2016 | 30-06-16 | 09-02-16 |  | 4 months | - |  | - | 30-06-15 | 0 | (30-06-15) |
| D43 | To create an efficient, effective and accountable administration | LED | To report on the EPWP progress |  | No. of EPWP steering committee meetings held quarterly | 4 | 4 |  | 0 | - |  | - | 4 | 4 | 0 |
| D44 | To create an efficient, effective and accountable administration | LED | 100% expenditure on the EPWP Grant |  | 100% Expenditure by end of June 2016 | 100% | 97.96% |  | (2.04% ) | Some contracts were terminated due to non-attendance, misbehavior and resignations of EPWP labourers |  | A briefing session to be conducted with all labourers to explain acceptable conduct and to replace employees who resigned with new ones | New KPI | - | - |
| D45 | To create an efficient, effective and accountable administration | GGPP | 100% % expenditure on the RRAMS Grant |  | 100% Expenditure by end of June 2016 | 100% | 100% |  | 0 | - |  | - | New KPI | - | - |
| D46 | To create an efficient, effective and accountable administration | GGPP | Public Participation meetings |  | No. of Public Participation meetings held by 30 June 2016 | 3 | 3 |  | 0 | - |  | - | 4 | 4 | 0 |
| D47 | To create an efficient, effective and accountable administration | GGPP | Compile IDP / Budget (Time schedule of key deadlines (Process Plan) by 30 August 2015 (MSA 28 / MFMA 21) |  | Approved IDP Framework and Process Plan on or before 31 Aug 2015 | 31-08-15 | 28-08-15 |  | 3 days | - |  | - | 31-08-14 | 29-08-14 | 2 days |
| D48 | To create an efficient, effective and accountable administration | GGPP | Compile Draft IDP, Review and submit to Council by 31 March 2016 (MSA 34) |  | Draft IDP approved on or before 31 March 2016 | 31-03-16 | 30-03-16 |  | 1 day | - |  | - | 31-03-15 | 31-03-15 | 0 |
| D49 | To continuously prepare, adopt, effectively implement and annually review IDP | GGPP | Compile final IDP and submit to Council 31 May 2016 (MSA 34) |  | Final IDP approved on or before 31 May 2016 | 31-05-16 | 07-07-16 |  | (68 days) | Final IDP was submitted to Council on the 31st May 2016 but was approved on the 07th June 2016( continuation meeting) |  | - | 31-05-15 | 27-05-15 | 4 days |
| D50 | To improve economic growth of the District | LED | Quarterly reports on the implementation of LED to Management/Council |  | No of reports submitted | 4 | 4 |  | 0 | - |  | - | 4 | 4 | 0 |
| D51 | To improve economic growth of the District | LED | Review of the LED Strategy |  | Adopted LED Strategy by 30 June 2016 | 30-06-16 | 30-03-16 |  | 3 months | - |  | - | New KPI | - | - |
| D52 | To contribute to Tourism Development and Marketing | LED | Tourism development |  | No. of tourism awareness campaigns conducted | 2 | 2 |  | 0 | - |  | - | New KPI | - | - |
| D53 | To improve economic growth of the District | LED | Quarterly District LED Forums |  | No. of Quarterly District LED Forums held | 4 | 4 |  | 0 | - |  | - | New KPI | - | - |
| D54 | To improve economic growth of the District | LED | LED Projects |  | No. of LED projects supported | 2 | 2 |  | 0 | - |  | - | New KPI | - | - |
| D55 | To manage and prevent harm of the environment and ensure its sustainability | BSD | Improve service delivery to communities |  | No. of person attending Health Education programmes/projects | 1000 | 2214 |  | 1214 | - |  | - | New KPI | - | - |
| D56 | Facilitate provision of sufficient bulk water supply to all municipalities | BSD | Improve service delivery to communities |  | No of quarterly water quality reports submitted to Council | 4 | 4 |  | 0 | - |  | - | 4 | 4 | 0 |
| D57 |  | BSD | Improve service delivery to communities |  | No of water quality samples collected per local municipality | Mohokare 72 | 87 |  | 15 | - |  | - | New KPI | - | - |
|  |  |  |  |  |  | Letsemeng 108 | 116 |  | 8 |  |  |  |  |  |  |
|  |  |  |  |  |  | Kopanong 218 | 295 |  | 77 |  |  |  |  |  |  |
|  |  |  |  |  |  | Naledi 72 | 84 |  | 12 |  |  |  |  |  |  |
| D58 | Facilitate provision of sustainable basic sanitation all households in the district | BSD | Improve service delivery to communities |  | No of quarterly sanitation quality reports submitted to Management/Council | 4 | 4 |  | 1 | - |  | - | 4 | 4 | 0 |
| D59 | Facilitate provision of sustainable basic sanitation all households in the district | BSD | Improve service delivery to communities |  | No of quarterly waste water samples taken per local municipality | Mohokare 12 | 10 |  | (2) | This due to unavailability of water due to draught. |  | Water samples will be taken in all local Municipalities as soon water becomes available | New KPI | - | - |
|  |  |  |  |  |  | Letsemeng 8 | 6 |  | (2) |  |  |  |  |  |  |
|  |  |  |  |  |  | Kopanong 16 | 7 |  | 9 |  |  |  |  |  |  |
|  |  |  |  |  |  | Naledi 8 | 8 |  | - |  |  |  |  |  |  |
| D60 | To build capacity of the district to perform its municipal health function | BSD | Improve service delivery to communities |  | No. of Environmental Health awareness | Water 5 | 5 |  | 0 | - |  | - | New KPI | - | - |
|  |  |  |  |  |  | Hygiene 5 | 7 |  | 2 |  |  |  |  |  |  |
|  |  |  |  |  |  | Food safety/ control 5 | 6 |  | 1 |  |  |  |  |  |  |
|  |  |  |  |  |  | Waste Management 5 | 5 |  | 0 |  |  |  |  |  |  |
|  |  |  |  |  |  | Communicable diseases 3 | 5 |  | 2 |  |  |  |  |  |  |
|  |  |  |  |  |  | Basa nje ngo Magogo 1 | 1 |  | 0 |  |  |  |  |  |  |
| D61 | Facilitate increased access by all households to electricity service | BSD | Improve service delivery to communities |  | No of quarterly District Energy Forum Meetings held by 30 June 2016 | 4 | 2 |  | (2) | This is due to non-attendance of other stakeholders |  | KPI to be reviewed | 4 | 4 | 0 |
| D62 | To create an efficient, effective and accountable administration | GGPP | Implement Council Resolutions within prescribed timeframe stipulated on system |  | % resolutions implemented within timeframe | 95% | 77% |  | (18) | The outturning resolution is implemented over a period of time due to project requirement |  | Follow up on all outstanding resolutions and report progress thereof | New KPI | - | - |

The following abbreviations are used in the service delivery targets and performance indicators:

KPA 	-	Key Performance Area

KPI	-	Key Performance Indicator

GGPP	-	Good Governance and Public Participation

MFVM	-	Municipal Financial Viability and Management

MTID	-	Municipal Transformation and Institutional Development

LED	-	Local Economic Development

BSD	-	Basic Service Delivery

MFMA	-	Municipal Finance Management Act 56 of 2003

MSA	-	Municipal Systems Act 32 of 2000

EEA	-	Employment Equity Act 55 of 1998

SDA	-	Skills Development Act 97 of 1998

MPPR	-	Local Government: Municipal Planning and Performance Management Regulations, 2001

MPR	-	Local Government: Municipal Performance Regulations for Municipal Managers and Managers Directly Accountable To

Municipal Managers, 2006

# CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE

# (PERFORMANCE REPORT PART II)

INTRODUCTION

The Municipality is constituted of four departments, namely: the Office of the Municipal Manager, Corporate Services, Planning and Social Development and Budget and Treasury. The Office of the Municipal Manager comprises of four divisions i.e. Internal Audit, Risk Management, Performance Management and Disaster Management. The Department of Corporate Services consists of four divisions, i.e. Administration, Human Resources, Information Technology and Labour Relations. The Department of Planning and Social Development is composed of four divisions, namely Local Economic Development, Integrated Development Planning, Municipal Health Services and Expanded Public Works Programme. The Budget and Treasury Office comprises of four divisions namely: Expenditure and Payroll, Supply Chain Management, Budget and Assets and Reporting and Compliance.

T4.0.1

## COMPONENT A: INTRODUCTION TO THE MUNICIPAL PERSONNEL

### 4.1	EMPLOYEE TOTALS, TURNOVER AND VACANCIES

| Vacancy Rate: 2015/2016 |  |  |  |
| --- | --- | --- | --- |
| Designations | *Total Approved Posts | *Vacancies (Total time that vacancies exist using fulltime equivalents) | *Vacancies (as a proportion of total posts in each category) |
|  | No. | No. | % |
| Municipal Manager | 1 | 0 | 0% |
| CFO | 1 | 1 | 100% |
| Other S57 Managers (excluding Finance Posts) | 2 | 1 | 50% |
| Other S57 Managers (Finance posts) | 0 | 0 | 0% |
| Police officers | 0 | 0 | 0% |
| Fire fighters | 0 | 0 | 0% |
| Senior management: Levels 13-15 (excluding Finance Posts) | 0 | 0 | 0% |
| Senior management: Levels 13-15 (Finance posts) | 0 | 0 | 0% |
| Highly skilled supervision: levels 9-12 (excluding Finance posts) | 0 | 0 | 0% |
| Highly skilled supervision: levels 9-12 (Finance posts) | 0 | 0 | 0% |
| Total | 4 | 2 | 50% |
|  |  |  | T 4.1.2 |

| Turn-over Rate |  |  |  |
| --- | --- | --- | --- |
| Details | Total Appointments as of beginning of Financial Year | Terminations during the Financial Year | Turn-over Rate* |
|  | No. | No. |  |
| 2013/2014 | 10 | 15 | 1.06% |
| 2014/2015 | 22 | 19 | 1.1% |
| 2015/2016 | 7 | 6 | 1.04% |
|  |  |  | T 4.1.3 |

COMMENT ON VACANCIES AND TURNOVER:

The low turnover is an indicatation of Xhariep District Municipality`s employees who have a positive working relationship with their direct supervisors and co-workers hence they are likely to stay at their jobs. Another cause of low turnover is having room for for advancement so employees feel like they can move up in their careers if they stay at the municipality. Poor economic conditions can also contribute to low turnover because employees fear not being able to find other work.

T4.1.4

## COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE

INTRODUCTION TO MUNICIPAL WORKFORCE MANAGEMENT

The Municipality has put proper municipal workforce management systems and procedures in place in order to entrench transparent personnel administration. A Human Resources Policy is in place. Furthermore, the Municipality has an Employment Equity Plan which is used to guide the Municipality on how to implement its recruitment strategy. An Employment Equity Report which shows whether the municipality has recruited employees in accordance with its Employment Equity Plan is then compiled and submitted to the Department of Labour on annual basis.

Every year before the end of June, the Municipality conducts skill audit for each employee with the intention to identify skill gaps in the institution. The Skills Report is then submitted to the Local Government Sector Education and Training Authority together with the Works Place Skills Plan (WSP). The Officials are then sent to trainings based on the WSP.

The Municipality has other numerous policies that governs the activities that are taking place within the institution, namely, Records Management Policy, Fraud and Corruption Prevention Policy, Risk Management Policy, Delegation System Policy, Disaster Management Policy, Audit Charter, Performance Management Framework, Integrated Development Framework and budget related policies etc. These policies and procedures are meant to regulate the activities undertaken by the employees of the Municipality.

T4.2.0

### 4.2	POLICIES

| HR Policies and Plans |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Name of Policy | Completed | Reviewed | Date adopted by council or comment on failure to adopt |
|  |  | % | % |  |
| 1 | Affirmative Action | 100% | 100% | 24 April 2012 |
| 2 | Attraction and Retention | 100% | 100% | 24 April 2012 |
| 3 | Code of Conduct for employees |  |  | 24 April 2012 |
| 4 | Delegations, Authorisation & Responsibility | 100% | 100% | 24 April 2012 |
| 5 | Disciplinary Code and Procedures |  |  | 24 April 2012 |
| 6 | Essential Services | 100% | 100% | 24 April 2012 |
| 7 | Employee Assistance / Wellness |  |  | 24 April 2012 |
| 8 | Employment Equity | 100% | 100% | 24 April 2012 |
| 9 | Exit Management |  |  | 24 April 2012 |
| 10 | Grievance Procedures | 100% | 100% | 24 April 2012 |
| 11 | HIV/Aids |  |  | 24 April 2012 |
| 12 | Human Resource and Development | 100% | 100% | 24 April 2012 |
| 13 | Information Technology |  |  | 24 April 2012 |
| 14 | Job Evaluation | 100% | 100% | 24 April 2012 |
| 15 | Leave |  |  | 24 April 2012 |
| 16 | Occupational Health and Safety | 100% | 100% | 24 April 2012 |
| 17 | Official Housing |  |  | 24 April 2012 |
| 18 | Official Journeys | 100% | 100% | 24 April 2012 |
| 19 | Official transport to attend Funerals | 100% | 100% | 24 April 2012 |
| 20 | Official Working Hours and Overtime |  |  | 24 April 2012 |
| 21 | Organisational Rights | 100% | 100% | 24 April 2012 |
| 22 | Payroll Deductions |  |  | 24 April 2012 |
| 23 | Performance Management and Development | 100% | 100% | 24 April 2012 |
| 24 | Recruitment, Selection and Appointments |  |  | 24 April 2012 |
| 25 | Remuneration Scales and Allowances | 100% | 100% | 24 April 2012 |
| 26 | Resettlement |  |  | 24 April 2012 |
| 27 | Sexual Harassment | 100% | 100% | 24 April 2012 |
| 28 | Skills Development |  |  | 24 April 2012 |
| 29 | Smoking |  |  | 24 April 2012 |
| 30 | Special Skills | 100% | 100% | 24 April 2012 |
| 31 | Work Organisation |  |  | 24 April 2012 |
| 32 | Uniforms and Protective Clothing | 100% | 100% | 24 April 2012 |
| 33 | Other: |  |  |  |
| Use name of local policies if different from above and at any other HR policies not listed. |  |  |  | T 4.2.1 |

COMMENT ON WORKFORCE POLICY DEVELOPMENT:

All necessary policies that enable the Municipality to conduct its business in a fair and transparent manner has been developed and submitted before Council for adoption.

T4.2.1.1

### 4.3	INJURIES, SICKNESS AND SUSPENSIONS

| Number and Cost of Injuries on Duty |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Type of injury | Injury Leave Taken | Employees using injury leave | Proportion employees using sick leave | Average Injury Leave per employee | Total Estimated Cost |
|  | Days | No. | % | Days | R'000 |
| Required basic medical attention only | 57 | 1 | 0.84 | 57 | 52 025,61 |
| Temporary total disablement | - | - | - | - | - |
| Permanent disablement | - | - | - | - | - |
| Fatal | - | - | - | - | - |
| Total | 57 | 1 | 0.84 | 57 | 52 025,61 |
|  |  |  |  |  | T 4.3.1 |

| Number of days and Cost of Sick Leave (excluding injuries on duty) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Salary band | Total sick leave | Proportion of sick leave without medical certification | Employees using sick leave | Total employees in post* | *Average sick leave per Employees | Estimated cost |
|  | Days | % | No. | No. | Days | R' 000 |
| Lower skilled (Levels 1-2) | 64 | 0 | 10 | 10 | 6.40 | 39087.48 |
| Skilled (Levels 3-5) | 254 | 0 | 20 | 20 | 12.70 | 166473.11 |
| Highly skilled production (levels 6-8) | 353 | 0 | 29 | 29 | 12.17 | 365521.50 |
| Highly skilled supervision (levels 9-12) | 457 | 0 | 25 | 25 | 18.28 | 591719.97 |
| Senior management (Levels 13-15) | 0 | 0 | 0 | 0 | 0 | 0 |
| MM and S57 | 33 | 0 | 2 | 2 | 16.50 | 1026635.08 |
| Total | 33 | 0% | 86 | 86 | 0.38 | 2189437.14 |
|  |  |  |  |  |  | T4.3.2 |

| Number and Period of Suspensions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Position | Nature of Alleged Misconduct | Date of Suspension | Details of Disciplinary Action taken or Status of Case and Reasons why not Finalised | Date Finalised |
| Internal Auditor | Disclosure of Information | 03-08-2015 | Case withdrawn due to lack of evidence | 01 09-2015 |
| Internal Audit Manager | Insurbodination | 03-08-2015 | Reached settlement agreement | 30-11-2015 |
| IDP Manager | Gross Insurbodination and Dereliction of duty | 30-05-2014 | Suspension without pay for maximum of 10 days | 01-09-2015 |
| Maintenance Assistance | Habitual Abseentism Dishonesty None reporting for duty | 08-04-2016 | Found guilty on all the charges pending finalisation | Pending |
|  |  |  |  | T4.3.5 |

## COMPONENT C: CAPACITATING THE MUNICIPAL WORKFORCE

INTRODUCTION TO WORKFORCE CAPACITY DEVELOPMENT

Every year before the end of June, the Municipality conduct skill audit for employees with the intention to identify skills gaps in the institution. The Skills Report is then submitted to the Local Government Sector Education and Training Authority together with the Works Place Skills Plan (WSP). The Officials are then sent to trainings based on the WSP.

T4.5.0

### 4.5	SKILLS DEVELOPMENT AND TRAINING

| Skills Matrix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Management level | Gender | Employees in post as at 30 June 2015/2016 | Number of skilled employees required and actual as at 30 June 2015/2016 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Learnerships |  |  | Skills programmes & other short courses |  |  | Other forms of training |  |  | Total |  |  |
|  |  | No. | Actual: End of 2014/2015 | Actual: End of 2015/2016 | Target | Actual: End of 2014/2015 | Actual: End of 2015/2016 | Target | Actual: End of 2014/2015 | Actual: End of 2015/2016 | Target | Actual: End of 2014/2015 | Actual: End of 2015/2016 | Target |
| MM and s57 | Female | 0 | 0 | 0 |  |  |  |  |  |  |  |  |  |  |
|  | Male | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |
| Councillors, senior officials and managers | Female | 15 | 8 | 4 |  | 4 |  |  |  |  |  |  |  |  |
|  | Male | 16 | 6 | 6 |  | 4 |  |  |  |  |  |  |  |  |
| Technicians and associate professionals* | Female |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Male |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Professionals | Female | 20 | 20 | 7 |  | 3 |  |  |  |  |  |  |  |  |
|  | Male | 7 | 3 | 3 |  |  |  |  |  |  |  |  |  |  |
| Sub total | Female | 35 | 32 | 11 |  | 7 |  |  |  |  |  |  |  |  |
|  | Male | 24 | 9 | 11 |  | 4 |  |  |  |  |  |  |  |  |
| Total |  | 119 | 80 | 44 |  | 22 |  |  |  |  |  |  |  |  |
| *Registered with professional Associate Body e.g CA (SA) |  |  |  |  |  |  |  |  |  |  |  |  |  | T4.5.1 |

| Financial Competency Development: Progress Report* |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | A. Total number of officials employed by municipality (Regulation 14(4)(a) and (c)) | B. Total number of officials employed by municipal entities (Regulation 14(4)(a) and (c) | Consolidated: Total of A and B | Consolidated: Competency assessments completed for A and B (Regulation 14(4)(b) and (d)) | Consolidated: Total number of officials whose performance agreements comply with Regulation 16 (Regulation 14(4)(f)) | Consolidated: Total number of officials that meet prescribed competency levels (Regulation 14(4)(e)) |
| Financial Officials |  |  |  |  |  |  |
| Accounting officer | 1 | 0 | 0 | 0 | 0 | 0 |
| Chief financial officer | 0 | 0 | 0 | 0 | 0 | 0 |
| Senior managers | 0 | 0 | 0 | 0 | 0 | 0 |
| Any other financial officials | 20 | 0 | 0 | 0 | 0 | 0 |
| Supply Chain Management Officials | 2 | 0 | 0 | 0 | 0 | 0 |
| Heads of supply chain management units | 1 | 0 | 0 | 0 | 0 | 0 |
| Supply chain management senior managers | 0 | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 24 | 0 | 0 | 0 | 0 | 0 |
| * This is a statutory report under the National Treasury: Local Government: MFMA Competency Regulations (June 2007) |  |  |  |  |  | T4.5.2 |

| Skills Development Expenditure |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |  |  |  |  |  |
| Management level | Gender | Employees as at the beginning of the financial year | Original Budget and Actual Expenditure on skills development 2015/2016 |  |  |  |  |  |  |  |
|  |  |  | Learnerships |  | Skills programmes & other short courses |  | Other forms of training |  | Total |  |
|  |  | No. | Original Budget | Actual | Original Budget | Actual | Original Budget | Actual | Original Budget | Actual |
| MM and S57 | Female |  |  |  |  |  |  |  |  |  |
|  | Male | 2 | 200 000 | 84 000 | - | - | - | - | - | - |
| Legislators, senior officials and managers | Female | 3 | 200 000 | 42 000 | - | - | - | - | - | - |
|  | Male | 7 | 200 000 | 126 000 | - | - | - | - | - | - |
| Professionals | Female | 9 | 0 | 0 | - | - | - | - | - | - |
|  | Male | 3 | 0 | 0 | - | - | - | - | - | - |
| Technicians and associate professionals | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Clerks | Female | 4 | 0 | 0 | - | - | - | - | - | - |
|  | Male | 3 | 0 | 0 | - | - | - | - | - | - |
| Service and sales workers | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Plant and machine operators and assemblers | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Elementary occupations | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Sub total | Female | 16 | 0 | 0 | - | - | - | - | - | - |
|  | Male | 15 | 0 | 0 | - | - | - | - | - | - |
| Total |  | 62 | 200000 | 252000 | 0 | 0 | 0 | 0 | 0 | 0 |
| *% and *R value of municipal salaries (original budget) allocated for workplace skills plan. |  |  |  |  |  |  |  |  | %* | *R |
|  |  |  |  |  |  |  |  |  |  | T4.5.3 |

## COMPONENT D: MANAGING THE WORKFORCE EXPENDITURE

INTRODUCTION TO WORKFORCE EXPENDITURE

Before the beginning of the next financial year the Municipality makes necessary estimates for the workforce expenditure. The Municipality then filled only vacant positions that are budgeted for. The Municipality strives all times to appoint only suitably qualified employees for the vacant posts.

T4.6.0

# CHAPTER 5 – FINANCIAL PERFORMANCE

### 5.3	ASSET MANAGEMENT

INTRODUCTION TO ASSET MANAGEMENT

The asset management policy was drafted within the prescripts of the applicable legislations. Asset verifications are done monthly to ensure that assets are safeguarded properly. Stock counts are performed bi-annual by the asset management officials and once a year. In terms of key delegations, the Accounting Officer is the principal custodian who should ensure that the said policy is scrupulously applied and adhered to. The Chief Financial Officer is the assets registrar. The key elements of the asset management policy are classification, recognition, identification, write-off, depreciation, capitalization criteria, amendment of useful lives, and maintenance of assets.

T5.3.1

| Repairs and Maintenance Expenditure: 2015/2016 |  |  |  |  |
| --- | --- | --- | --- | --- |
| R' 000 |  |  |  |  |
|  | Original Budget | Adjustment Budget | Actual | Budget variance |
| Repairs and Maintenance Expenditure | 276 | 218 | 298 | (80) |
|  |  |  |  | T 5.3.4 |

## COMPONENT D: OTHER FINANCIAL MATTERS

### 5.12	SUPPLY CHAIN MANAGEMENT

SUPPLY CHAIN MANAGEMENT

As far as the processes are concerned, a MEMO for DEMAND and ACQUISITION has been developed by the municipality to manage, control and monitor procurement of goods and services. The MEMO is signed by the responsible manager to confirm the need of the service or product, the manager for Budget and Reporting Unit confirms the budget availability, relevant HOD recommends as well as the CFO and the Accounting Officer/Municipal Manager or a Senior Manager designated to act in the capacity of the Municipal Manager, finally approves the MEMO for DEMAND and ACQUISITION. During 2015/2016 financial year, Supply Chain Management Policy of the Municipality went for a review and a workshop was conducted to employees of the municipality in February 2016. The policy was adopted by council on the 7th of June 2016 for implementation in the 2016/2017 financial year. The municipality also uses the Procurement Procedure Manual to help it in achieving its policy objectives.

T5.12.1

### 5.13	GRAP COMPLIANCE

GRAP COMPLIANCE

GRAP is the acronym for Generally Recognized Accounting Practice and it provides the rules by which municipalities are required to maintain their financial accounts. Successful GRAP compliance will ensure that municipal accounts are comparable and more informative for the municipality. It will also ensure that the municipality is more accountable to its citizens and other stakeholders. Information on GRAP compliance is needed to enable National Treasury to assess the pace of progress and consider the implications.

T5.13.1

# CHAPTER 6 – AUDITOR GENERAL AUDIT FIND

## COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS 2014/2015

### 6.1 AUDITOR GENERAL REPORT 2014/2015(Previous year)

| Auditor-General Report on Financial Performance: 2014/2015( 2014/2015) |  |
| --- | --- |
| Audit Report Status*: Qualified |  |
| Non-Compliance Issues | Remedial Action Taken |
| Cash Flow Statement: Incorrect amounts disclosed | The Interim Financial Statements and the Annual Financial Statements will be presented to the AGSA and the Provincial Treasury Task Team timeously prior to commencement of the 2015/16 Audit. |
| Employment Performance Management System | The Municipality is still under financial constraints to be able to implement the assessment on the performance of non-section 56 employees. Management will submit a report to council to request council to place the HR policy of the assessment on lower level employees on a moratorium ( delayed). The HR Manager and DCS will perform a benchmark analysis with other Municipalities within the Free State to establish their system in place for implementation of the Performance Management Systems for all employees. |
| Internal Audit- Quarterly reports not submitted | Internal Audit reports were tabled to Audit Committee as per Section 165(2)(b)(vii) of the MFMA on the 30th November 2015. |
| Unauthorized, irregular and fruitless and wasteful expenditure - No section 32 committee set | Management will ensure the section 32 committee is appointed as prescribed by the MSA and MFAM or recommended by AGSA. Management will ensure Delegation of authority framework is developed and approved by council. Investigation of unauthorized, irregular, fruitless and wasteful expenditure incurred will commence effectively after appointment of the section 32 committee. |
| Procurement and contract Management - No approval of extension of contracts | Management shall ensure that any extension to a contract is reported to the council and approved by the Accounting Officer. Contract extension will only be valid for a period no longer than three (3) months to ensure that competitive bidding is not prohibited. Management should that they developed Guidelines for Contract Management, the Guidelines will be tabled to the Council and will be approved by Council. |
| Procurement and Contract Management : No declaration of interest identified | Management shall ensure that prior to awarding, all awards between R10 000.00 and R30 000.00 are accompanied by signed declaration of interests by suppliers All payment vouchers above R10 000.00 will be accompanied by declaration of interest by supplier |
| Procurement and Contract Management : Competitive bidding - Njunga Construction and Projects tender irregular | The Adjudication Committee shall ensure that it adheres to the SCM policy in instances where it disagrees with the Evaluation Committee recommendations. Management should ensure that TEC recommendations are presented to the BAC prior to BAC Finalisation. |
| Procurement and Contract management : Month to month contracts prohibits competitive bidding | Both Digicoms and Multitech went through a competitive bidding process. As for O2 Information Technology (i.e. Website Maintenance) the municipality has moved to the Province for such a service. Management will ensure that all service contracts coming to an end will be taken through competitive bidding three months prior to expiry of current service contracts. |
| Procurement and Contract Management : No deviations letter attached and no 3 quotations | Management shall ensure that in instances where there are proper and relevant supporting documents, deviations approved by the Accounting Officer are attached The SCM checklist will be effectively implemented and reviewed prior payment is processed. |
| Property, plant and equipment - Valuation of assets could not be confirmed | Management will use the 2014/15 Audited Asset Register as a base for consistency. Management will prepare the asset register as per requirements of GRAP17, Directive 7 and according to the municipality fixed asset policy and correct the financial statements as such. Management should ensure that Asset Unit is performing a spot check on assets on monthly basis and report will be issued to confirm the state of the assets. |
| Expenditure: Payment made later than 30 days after receipt of invoice | Payments will be made within 30 days after receipt of invoice when the municipal financial position permits. |
| Irregular expenditure - Non-compliance | Management shall ensure that all internal controls in place, as well as policies and procedures, are adhered to at all times in order to minimize the incurring of such expenditure. |
| FMG 4th quarter report/annual performance report | Management will ensure that: (a) the requirements of DORA are met when submitting reports to Treasury; and (b) the information on the support plan submitted to treasury agrees to the annual performance report Management should ensure that APR is reviewed by Internal Audit Unit. |
| Receivables- Interest understated | 1. Management will ensure that interest is re-calculated retrospectively. 2. Management will review all trade debtors account to ensure that interest is charged on outstanding invoices. |
| Receivables- Sundry debtors not complete | Management will scrutinize the payroll run to ensure that all deductions that qualify as debt from the payroll input are clearly recorded as debtors. Management will keep a debtors list for sundry debtors and agree the list to the general ledger on a monthly basis. |
| Receivable - Debtors not raised | Management will ensure that all employees of the municipality who are owing the municipality be raised as individual debtors and ensure that the repayments from debtors must be recorded and accounted properly. Management will perform monthly reconciliations on all individual debtors |
| Employee Costs - Non-Compliance (no assessments competencies) | Management will ensure that all Finance and Supply Chain Officials are assessed on their respective competencies. HR to continuously monitor the completion of all employees that have been enrolled for competency skills assessment as required by Municipal Regulation on Minimum competency level reg 6 and 7(GNR 493). Furthermore, all certificates of completion will be filed in each employee’s respective file. |
| Assessment of Senior Management | The Municipality is still under financial constraints to be able to implement the assessment on the performance of non-section 56 employees. However management will make necessary provision in its forthcoming budget that will enable for the appointment and remuneration of the committee that will assess the performance of senior management. |
| Cash & Cash Equivalents - New bank account | Management will submit the list on all bank accounts to Provincial Treasury and AGSA |
| Commitments - No accounting policy | The Chief Financial Officer will ensure that all the applicable tabs on Caseware are selected for fair presentation. |
| Employee costs: Overpayment of allowances to managers | Management acknowledges that the incumbents were paid in excess, and therefore debtors will be raised. Subsequently management will obtain council approval to write the debts off. Furthermore, management will ensure going forward to remunerate the incumbents as per the government regulations on the appointment od senior managers. |
| Employee Related Costs - Non-Compliance key position not filled | The municipality will commence with the recruitment processes of filling the vacant position of Director Corporate Services and ensure compliance with section 56 when a senior manager is appointed. |
| Employee costs: Acting more than 3 months | Management will obtain approval from the MEC for local government to extend acting periods of incumbents if a vacancy of such nature exists. |
| Municipal vacancies increased | All vacant positions were abolished. See attached Council Resolution The municipality will commence with the recruitment processes of filling the vacant position of Director Corporate Services and ensure compliance with section 56 when a senior manager is appointed. All vacant positions will be filled before 01 April 2016. |
| Municipal Public Account Committee not functioning | The Municipal Manager will ensure that the Municipal Public Account Committee sits and review the investigation reports provided by management and accountability should be held. |
| Unspent conditional grants - Quarterly reports not submitted within 30 days | Management will ensure that quarterly monthly Grants reports are submitted to COGTA and Treasury within 30 days. Management will ensure compliance by having a schedule in which quarterly reports are compiled, reviewed, signed and subsequently submitted. |
| Going Concern Assessment | Management will perform a 12 month assessment to include all other risks for going concern purpose. |
| Procurement and contract management - Contract ending within the next 6 months | New appointments have been made through a competitive bidding process except only for Travel Agency and Insurance. New service provider will be appointed for travel agency, while the contract for insurance has been extended for another twelve months. In future, the municipality shall ensure that correct processes are followed when a contract has to be extended, or shall invite competition in time prior to contract coming to an end. |
| Procurement and contract management - Schalk General Trading | Management will liaise with Provincial Treasury to advice the way forward regarding the project. |
| Procurement and Contract Management : Tenders not advertised on the municipal website | Management shall ensure that all transactions above the value of R30 000.00 are placed on the official municipal website. |
| Procurement and contract management - No monthly monitoring | Management shall ensure that all contracts for more than one month are monitored on a monthly basis. A report on a monthly basis will be submitted to the office of the Chief Financial Officer in respect of performance of appointed suppliers |
| Procurement & Contract Management - Contract value exceeded | Management will review all contracts entered by the Municipality to include the terms and conditions for a dispute resolution. Management will develop a controls that will enable the Municipality to measure the performance of service providers. |
| Unspent Conditional Grant - No Roll-over applications | Management will ensure that it implements proper controls to ensure that applications for roll-overs are made timelessly and records are kept. |
| Unspent Conditional Grant - Progress report not complying with DORA ( | Management will ensure that all requirements for the application of roll-over are met. |
| Employee costs - Vetting omitted | Employee vetting will be conducted for all newly appointed candidates. The vetting process will be outsourced and all evidence will be kept for records purposes. The position of the CFO has been advertised and all shortlisted candidates will be subject to the vetting process. |
| - Invoice without VAT numbers | Monthly reports will be reviewed to ensure that all transactions that are inclusive of VAT are accurately recorded |
|  | T 6.1.1 |

## COMPONENT B: AUDITOR-GENERAL OPINION 2015/2016 (CURRENT YEAR)

### 6.2 AUDITOR GENERAL REPORT 2015/2016

AUDITOR GENERAL REPORT ON THE FINANCIAL STATEMENTS: 2015/2016

# Report of the auditor-general to the Free State Provincial Legislature and the council on the Xhariep District Municipality

## Report on the financial statements

Introduction

- I have audited the financial statements of the Xhariep District Municipality set out on pages 108 to166, which comprise the statement of financial position as at 30 June 2016, the statement of financial performance, statement of changes in net assets, cash flow statement and statement of comparison of budget information with actual information for the year then ended, as well as the notes, comprising a summary of significant accounting policies and other explanatory information.

Accounting officer’s responsibility for the financial statements

- The accounting officer is responsible for the preparation and fair presentation of these financial statements in accordance with the South African Standards of Generally Recognised Accounting Practice (SA Standards of GRAP) and the requirements of the Municipal Finance Management Act, 2003 (Act No. 56 of 2003) (MFMA) and the Division of Revenue Act, 2015 (Act No. 1 of 2015) (DoRA), and for such internal control as the accounting officer determines is necessary to enable the preparation of financial statements that are free from material misstatement, whether due to fraud or error.

Auditor-general’s responsibility

- My responsibility is to express an opinion on these financial statements based on my audit. I conducted my audit in accordance with the International Standards on Auditing. Those standards require that I comply with ethical requirements, and plan and perform the audit to obtain reasonable assurance about whether the financial statements are free from material misstatement.

- An audit involves performing procedures to obtain audit evidence about the amounts and disclosures in the financial statements. The procedures selected depend on the auditor’s judgement, including the assessment of the risks of material misstatement of the financial statements, whether due to fraud or error. In making those risk assessments, the auditor considers internal control relevant to the entity’s preparation and fair presentation of the financial

statements in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the entity’s internal control. An audit also includes evaluating the appropriateness of accounting policies used and the reasonableness of accounting estimates made by management, as well as evaluating the overall presentation of the financial statements.

- I believe that the audit evidence I have obtained is sufficient and appropriate to provide a basis for my audit opinion.

Opinion

- In my opinion, the financial statements present fairly, in all material respects, the financial position of the Xhariep District Municipality as at 30 June 2016 and its financial performance and cash flows for the year then ended, in accordance with SA Standards of GRAP and the requirements of the MFMA and DoRA.

Emphasis of matters

- I draw attention to the matters below. My opinion is not modified in respect of these matters.

Restatement of corresponding figures

- As disclosed in note 31 to the financial statements, the corresponding figures for the 30 June 2015 have been restated as a result of errors discovered during 2015-16 in the financial statements of the municipality at, and for the year ended, 30 June 2015.

Irregular Expenditure

- As disclosed in note 37 to the financial statements, the municipality incurred irregular expenditure of R4 653 888 (2015: R3 710 358) in 2015-16 due to non-compliance with supply chain management (SCM) regulations.

Unauthorised Expenditure

- As disclosed in note 35 to the financial statements, the municipality incurred unauthorised expenditure of R2 797 621 (2015: R746 110) during 2015-16 due to expenditure that exceeded the limit of the amount provided for in the main division of the approved budget.

Going concern

- Note 33 to the financial statements indicates that the Xhariep District Municipality incurred a net loss of R6 937 981 during the year ended 30 June 2016 and, as of that date, the municipality’s current liabilities exceeded its current assets by R9 763 148. These conditions, along with other matters as set forth in the note 33, indicate the existence of a material uncertainty that may cast significant doubt on the municipality’s ability to operate as a going concern.

Additional matters

- I draw attention to the matters below. My opinion is not modified in respect of these matters.

Unaudited supplementary schedules

- The supplementary information set out on pages 161 to 163 does not form part of the financial statements and is presented as additional information. I have not audited these schedules and, accordingly, I do not express an opinion on them.

Unaudited disclosure notes

- In terms of section 125(2)(e) of the MFMA, the municipality is required to disclose particulars of non-compliance with the MFMA. This disclosure requirement did not form part of the audit of the financial statements and, accordingly, I do not express an opinion on them.

Report on other legal and regulatory requirements

- In accordance with the Public Audit Act of South Africa, 2004 (Act No. 25 of 2004) and the general notice issued in terms thereof, I have a responsibility to report findings on the reported performance information against predetermined objectives of selected key performance areas presented in the annual performance report, compliance with legislation and internal control. The objective of my tests was to identify reportable findings as described under each subheading, but not to gather evidence to express assurance on these matters. Accordingly, I do not express an opinion or conclusion on these matters.

Predetermined objectives

- I performed procedures to obtain evidence about the usefulness and reliability of the reported performance information of the following selected key performance areas presented in the annual performance report of the Xhariep District Municipality for the year ended 30 June 2016:

- Key performance area : Local economic development on pages 45 to 66

- Key performance area : Basic service delivery on pages 45 to 66

- Key performance area : Public participation and good governance  45 to 66

- I evaluated the usefulness of the reported performance information to determine whether it was presented in accordance with the National Treasury’s annual reporting principles and whether the reported performance was consistent with the planned key performance areas. I further

performed tests to determine whether indicators and targets were well defined, verifiable, specific, measurable, time bound and relevant, as required by the National Treasury’s Framework for Managing Programme Performance Information (FMPPI).

- I assessed the reliability of the reported performance information to determine whether it was valid, accurate and complete.

- I did not identify any material findings on the usefulness and reliability of the reported performance information for  the following key performance areas:

- Basic service delivery

- Local economic development

- Public participation and good governance

Additional matter

- Although I raised no material findings on the usefulness and reliability of the reported performance information for the selected key performance areas, I draw attention to the following matters:

Unaudited supplementary schedules

- The supplementary information set out on pages 1 to 44 does not form part of the annual performance report and is presented as additional information. I have not audited these schedules and, accordingly, I do not report on them.

Compliance with legislation

- I performed procedures to obtain evidence that the Xhariep District Municipality had complied with applicable legislation regarding financial matters, financial management and other related matters. My material findings on compliance with specific matters in key legislation, as set out in the general notice issued in terms of the PAA, are as follows

Annual financial statements

- The financial statements submitted for auditing were not prepared in all material respects in accordance with the requirements of section 122 of the MFMA. Material misstatements of non-current assets, liabilities, expenditures and disclosure items identified by the auditors in the submitted financial statement were subsequently corrected and the supporting records were provided subsequently, resulting in the financial statements receiving an unqualified audit opinion.

Expenditure management

- Money owed by the municipality was not always paid within 30 days, as required by section 65(2)(e) of the MFMA.

- Reasonable steps were not taken to prevent unauthorised expenditure, as required by section 62(1)(d) of the MFMA.

- Reasonable steps were not taken to prevent irregular expenditure, as required by section 62(1)(d) of the MFMA.

- Reasonable steps were not taken to prevent fruitless and wasteful expenditure, as required by section 62(1)(d) of the MFMA.

Asset management

- Capital assets were transferred without the approval of the council as required by section 14(2)(a) of the MFMA.

Conditional grants received

- The provincial infrastructure grant and Motheo disestablishment grant allocation was not spent in accordance with the applicable grant framework, in contravention of section 17(1) of the DoRA.

Human resource management and compensation

- Sufficient appropriate audit evidence could not be obtained that the municipality developed and adopted appropriate systems (policies) and procedures to monitor, measure and evaluate performance of staff as required by section 67(d) of the Municipal Systems Act.

Consequence management

- Unauthorised expenditure by the municipality was not investigated to determine whether any person was liable for the expenditure, as required by section 32(2)(a) of the Municipal Finance Management Act.

- Irregular expenditure by the municipality was not investigated to determine whether any person was liable for the expenditure, as required by section 32(2)(b) of the Municipal Finance Management Act.

- Fruitless and wasteful expenditure by the municipality was not investigated to determine whether any person was liable for the expenditure, as required by section 32(2)(b) of the Municipal Finance Management Act.

Liability management

- An effective system of internal control for liabilities (including a liability register) was not in place, as required by section 63(2)(c) of the MFMA.

Procurement management

- Goods and services with a transaction value of below R200 000 were procured without obtaining the required price quotations, in contravention of by SCM regulation 17(a) and (c).

Internal control

- I considered internal control relevant to my audit of the financial statements, annual performance report and compliance with legislation. The matters reported below are limited to the significant internal control deficiencies that resulted in the basis for unqualified opinion, the findings on the annual performance report and the findings on compliance with legislation included in this report.

Leadership

- There has been a slow response from the leadership in implementing and monitoring the audit action plan to address qualification areas and internal control deficiencies identified during the previous audits and as a result it was again a last minute effort to avoid audit report matters.

- The leadership did not take effective steps to ensure that there were consequences for poor performance and transgressions, as none of the unauthorised, irregular as well as fruitless and wasteful expenditure incurred was investigated during the financial year.

- The leadership did not ensure that vacancies in key positions were filled to facilitate sound financial management, as the position of chief financial officer and director corporate services remained vacant during the financial year under review.

Financial and performance management

- The financial statements were not properly reviewed for completeness and accuracy prior to submission for auditing. This resulted in material adjustments being made to the financial statements. It was also identified through the audit that some officials were not sufficiently skilled to ensure that the daily financial transactions were recorded fully and correctly. Internal reviews and reconciliations of all financial records and transactions were noted to be inadequate.

- The municipality did not always comply with applicable legislation. No formal processes were in place to monitor compliance with legislation, which resulted in the number of reported non-compliance issues. Consequences for poor performance and non-compliance with legislation were lacking.

Governance

- The accounting officer did not ensure that there is an adequately resourced and functioning internal audit unit throughout the year that identifies internal control deficiencies and recommends corrective action effectively.

- Audit committee does not adequately promote accountability and service delivery through evaluating and monitoring responses to risks and providing oversight over the effectiveness of the internal control environment, including financial and performance reporting and compliance with legislations, due to limited reports submitted from the internal audit unit.

Bloemfontein

30 November 2016

GLOSSARY

GLOSSARY

| Accessibility indicators | Explore whether the intended beneficiaries are able to access services or outputs. |
| --- | --- |
| Accountability documents | Documents used by executive authorities to give “full and regular” reports on the matters under their control to Parliament and provincial legislatures as prescribed by the Constitution. This includes plans, budgets, in-year and Annual Reports. |
| Activities | The processes or actions that use a range of inputs to produce the desired outputs and ultimately outcomes. In essence, activities describe "what we do". |
| Adequacy indicators | The quantity of input or output relative to the need or demand. |
| Annual Report | A report to be prepared and submitted annually based on the regulations set out in Section 121 of the Municipal Finance Management Act. Such a report must include annual financial statements as submitted to and approved by the Auditor-General. |
| Approved Budget | The annual financial statements of a municipality as audited by the Auditor General and approved by council or a provincial or national executive. |
| Baseline | Current level of performance that a municipality aims to improve when setting performance targets. The baseline relates to the level of performance recorded in a year prior to the planning period. |
| Basic municipal service | A municipal service that is necessary to ensure an acceptable and reasonable quality of life to citizens within that particular area. If not provided it may endanger the public health and safety or the environment. |
| Budget year | The financial year for which an annual budget is to be approved – means a year ending on 30 June. |
| Cost indicators | The overall cost or expenditure of producing a specified quantity of outputs. |
| Distribution indicators GLOSSARY | The distribution of capacity to deliver services. |
| Financial Statements | Includes at least a statement of financial position, statement of financial performance, cash-flow statement, notes to these statements and any other statements that may be prescribed. |
| General Key performance indicators | After consultation with MECs for local government, the Minister may prescribe general key performance indicators that are appropriate and applicable to local government generally. |
| Impact | The results of achieving specific outcomes, such as reducing poverty and creating jobs. |
| Inputs | All the resources that contribute to the production and delivery of outputs. Inputs are "what we use to do the work". They include finances, personnel, equipment and buildings. |
| Integrated Development Plan (IDP) | Set out municipal goals and development plans. |
| National Key performance areas | - Service delivery & infrastructure - Economic development - Municipal transformation and institutional development - Financial viability and management - Good governance and community participation |
| Outcomes | The medium-term results for specific beneficiaries that are the consequence of achieving specific outputs. Outcomes should relate clearly to an institution's strategic goals and objectives set out in its plans. Outcomes are "what we wish to achieve". |
| Outputs | The final products, or goods and services produced for delivery. Outputs may be defined as "what we produce or deliver". An output is a concrete achievement (i.e. a product such as a passport, an action such as a presentation or immunization, or a service such as processing an application) that contributes to the achievement of a Key Result Area. |
| Performance Indicator | Indicators should be specified to measure performance in relation to input, activities, outputs, outcomes and impacts. An indicator is a type of information used to gauge the extent to which an output has been achieved (policy developed, presentation delivered, service rendered) GLOSSARY |
| Performance Information | Generic term for non-financial information about municipal services and activities. Can also be used interchangeably with performance measure. |
| Performance Standards: | The minimum acceptable level of performance or the level of performance that is generally accepted. Standards are informed by legislative requirements and service-level agreements. Performance standards are mutually agreed criteria to describe how well work must be done in terms of quantity and/or quality and timeliness, to clarify the outputs and related activities of a job by describing what the required result should be. In this EPMDS performance standards are divided into indicators and the time factor. |
| Performance Targets: | The level of performance that municipalities and its employees strive to achieve. Performance Targets relate to current baselines and express a specific level of performance that a municipality aims to achieve within a given time period. |
| Service Delivery Budget Implementation Plan | Detailed plan approved by the mayor for implementing the municipality’s delivery of services; including projections of the revenue collected and operational and capital expenditure by vote for each month. Service delivery targets and performance indicators must also be included. |
| Vote: | One of the main segments into which a budget of a municipality is divided for appropriation of money for the different departments or functional areas of the municipality. The Vote specifies the total amount that is appropriated for the purpose of a specific department or functional area. Section 1 of the MFMA defines a “vote” as: a) one of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned |

APPENDICES

# APPENDICES

## APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE

| Council Members | Full Time / Part Time | Committees Allocated | *Ward and/ or Party Represented | Percentage Council Meetings Attendance |
| --- | --- | --- | --- | --- |
|  | FT/PT |  |  | % |
| CLLR MG NTWANAMBI | FT | Mayoral Committee | - | 100 |
|  |  | Council | ANC | 89 |
| CLLR MG MODISE | FT | Corporate Services |  | 100 |
|  |  | Mayoral Committee |  | 100 |
|  |  | Council | ANC | 44 |
| CLLR JAFTA | PT | Planning & Social Development |  | 60 |
|  |  | Council | ANC | 78 |
| CLLR T MOKHELE | PT | Corporate Services |  | 100 |
|  |  | Council | ANC | 56 |
| CLLR MJ MOHAPI | PT | Budget and Treasury |  | 20 |
|  |  | Council | ANC | 78 |
| CLLR MJ MPHORE | PT | Corporate Services |  | 60 |
|  |  | Council | COPE | 100 |
| CLLR AJJ VAN RENSBURG | PT | Planning & Social Development | DA | 100 |
| APPENDICES |  | Council | DA | 67 |
| CLLR SA SOLA | PT | Budget &Treasury |  | 80 |
|  |  | Council | ANC | 67 |
| CLLR NC SPOCHTER | PT | Corporate Services | ANC | 80 |
|  |  | Council |  | 89 |
| CLLR H SHEBE | PT | Budget &Treasury |  | 100 |
|  |  | Council | DA | 100 |
| CLLR VA MONA | FT | Budget &Treasury | ANC | 80 |
|  |  | Mayoral Committee |  | 100 |
|  |  | Coouncil |  | 89 |
| CLLR P DIBE | PT | Planning & Social Development |  | 100 |
|  |  | Council | ANC | 67 |
| CLLR I MEHLOMAKULU | FT | Planning & Social Development |  | 60 |
|  |  | Mayoral Committee |  | 43 |
|  |  | Council | ANC | 67 |
| CLLR MJ SEHANKA | FT | Speaker – Council | ANC | 89 |
| CLLR JJ MAKITLE | PT | Budget &Treasury | ANC | 40 |
|  |  | Council | ANC | 89 |
| CLLR ML SEHLOHO | PT | Planning & Social Development | ANC | 20 |
|  |  | Council | ANC | 0 |

APPENDICES

## APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES

| Committees (other than Mayoral / Executive Committee) and Purposes of Committees |  |
| --- | --- |
| Municipal Committees | Purpose of Committee |
| Oversight Committee | Playing an oversight Role over the finances and the administration of the Municipality |
| Audit Committee | Performing duties as stipulated in Section 166 of the MFMA |
| MPAC | Playing an oversight Role over the finances and the administration of the Municipality |

APPENDICES

## APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY

| Municipal / Entity Functions |  |  |
| --- | --- | --- |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No)* | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 4, Part B functions: |  |  |
| Air pollution | Yes |  |
| Building regulations | No |  |
| Child care facilities | Yes |  |
| Electricity and gas reticulation | No |  |
| Firefighting services | No |  |
| Local tourism | Yes |  |
| Municipal airports | No |  |
| Municipal planning | Yes |  |
| Municipal health services | Yes |  |
| Municipal public transport | No |  |
| Municipal public works only in respect of the needs of municipalities in the discharge of their responsibilities to administer functions specifically assigned to them under this Constitution or any other law | No |  |
| Pontoons, ferries, jetties, piers and harbours, excluding the regulation of international and national shipping and matters related thereto | No |  |
| Stormwater management systems in built-up areas | No |  |
| Trading regulations | No |  |
| Water and sanitation services limited to potable water supply systems and domestic waste-water and sewage disposal systems | No |  |
| Continued next page |  |  |
| Continued from previous page |  |  |
| Municipal / Entity Functions |  |  |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No)* | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 5, Part B functions: |  |  |
| Beaches and amusement facilities APPENDICES | No |  |
| Billboards and the display of advertisements in public places | No |  |
| Cemeteries, funeral parlours and crematoria | Yes |  |
| Cleansing | No |  |
| Control of public nuisances | No |  |
| Control of undertakings that sell liquor to the public | No |  |
| Facilities for the accommodation, care and burial of animals | No |  |
| Fencing and fences | No |  |
| Licensing of dogs | No |  |
| Licensing and control of undertakings that sell food to the public | No |  |
| Local amenities | No |  |
| Local sport facilities | No |  |
| Markets | No |  |
| Municipal abattoirs | No |  |
| Municipal parks and recreation | No |  |
| Municipal roads | No |  |
| Noise pollution | Yes |  |
| Pounds | No |  |
| Public places | No |  |
| Refuse removal, refuse dumps and solid waste disposal | No |  |
| Street trading | No |  |
| Street lighting | No |  |
| Traffic and parking | No |  |
| * If municipality: indicate (yes or No); * If entity: Provide name of entity |  | T D |

APPENDICES

## APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE 2015/2016

| Municipal Audit Committee Recommendations |  |  |
| --- | --- | --- |
| Date of Committee | Committee recommendations during 2014/2015 | Recommendations adopted (enter Yes) If not adopted (provide explanation) |
| 29 April 2016 | The Audit Committee recommended that the Audit Committee pack be circulated within 7 days as per Internal Audit Charter | Yes – Adopted as per Internal Audit Charter |
|  | The Audit Committee welcomed the New Internal Audit Team to the Xhariep District Municipality and sought clarity from Management the process followed to appoint CAE. | Yes |
|  | Audit Committee noted 2nd Quarter Internal Audit Report and recommend to management that those findings have been recurring and management should ensure that the same finding are not recurring in the 3rd Quarter Internal Audit Report | Yes |
|  | Audit Committee recommended that management should look for minutes of the previous meetings as some issues were discussed there. | No – Management could not locate Minutes of the previous meeting due to the resignation of theprevious internal audit unit and non-handing over of strategic documents. |
|  |  | T G |

APPENDICES

## APPENDIX H(i) – Long Term Contracts (20 Largest Contracts Entered into during 2015/2016

| Long Term Contracts (20 Largest Contracts Entered into during 2015/2016) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R' 000 |  |  |  |  |  |
| Name of Service Provider (Entity or Municipal Department) | Description of Services Rendered by the Service Provider | Start Date of Contract | Expiry date of Contract | Project manager | Contract Value |
| Lateral Unison | Insurance of municipal assets | 01/07/2015 | 30/06/2016 | Office of the Municipal Manager | 568,908.43 |
| Thepa Trading | Supply and Maintenance of Telephone System | 02/10/2015 | 30/09/2018 | ICT Manager/Corporate Services | 539,779.32 |
| Thepa Trading | Supply and Maintenance of Printers/Photocopiers | 01/06/2015 | 31/05/2018 | ICT Manager/Corporate Services | 1,161,390.86 |
| Testit Labs | Water sampling | 01/09/2015 | 31/08/2016 | Environmental Health Manager/Planning & Social Development | 247,035.80 |
| Procon IT Solution | Back up service | 06/01/2016 | 31/12/2016 | 31/12/2016 | 48,000.00 |
| Missao Ponto Investment Holdings APPENDICES | Rural roads asset management grant | 31/10/2015 | 31/10/2016 | IDP Manager/Planning & Social Development | 1,500,000.00 |
| Procon IT Solution | Back up service | 06/01/2016 | 31/12/2016 | 31/12/2016 | 48,000.00 |
| Missao Ponto Investment Holdings | Rural roads asset management grant | 31/10/2015 | 31/10/2016 | IDP Manager/Planning & Social Development | 1,500,000.00 |
|  |  |  |  |  | T H.1 |

## APPENDIX I –SERVICE PROVIDER PERFORMANCE SCHEDULE

| Service Provider | Project Name | Contract Amount | Project Status | End User Remarks |
| --- | --- | --- | --- | --- |
| Lateral Unison | Insurance of municipal assets | 568,908.43 | Complete | Good |
| Thepa Trading | Supply and Maintenance of Telephone System | 539,779.32 | On-going | Good |
| Thepa Trading | Supply and Maintenance of Printers/Photocopiers | 1,161,390.86 | On-going | Good |
| Testit Labs | Water sampling | 247,035.80 | On-going | Good |
| Procon IT Solution | Internet service provision | 64,500.00 | On-going | Good |
| Procon IT Solution | Back up service | 48,000.00 | On-going | Good |
| Missao Ponto Investment Holdings | Rural roads asset management grant | 1,500,000.00 | On-going | Good |

## APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS

| Disclosures of Financial Interests |  |  |
| --- | --- | --- |
| Period 1 July to 30 June of 2015/2016 (Current Year) |  |  |
| Position | Name | Description of Financial interests* (Nil / Or details) |
| (Executive) Mayor | M.G Ntwanambi | Nil |
| Member of MayCo / Exco |  |  |
|  | M.G Modise | Nil |
|  | N.I Mehlomakhulu | Nil |
|  | V. Mona | Nil |
| Councillor | N Jafta | Nil |
|  | H Shebe | Nil |
|  | T Mokhele | Nil |
|  | M.J Mohapi | Nil |
|  | M.J Mphore | Nil |
|  | NC Spochter | Nil |
|  | S. A Sola | Nil |
| Municipal Manager | MM Kubeka | Nil |
| Chief Financial Officer | L Mashiane | Nil |
|  | MC Mogoale | Nil |
| (Executive) Directors | M Khapha | Nil |
|  | MS Mohale | Nil |
| T J |  |  |

## APPENDIX K (i): REVENUE COLLECTION PERFORMANCE BY Source

| Revenue Collection Performance by Source |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| R '000 |  |  |  |  |  |  |
| Description | 2013/2014 | 2014/2015 |  |  | 2015/2016 Variance |  |
|  | Actual | Original Budget | Adjustments Budget | Actual | Original Budget | Adjustments Budget |
| Agency services |  |  |  |  |  |  |
| Transfers recognised - operational | 51 773 | 51 774 | 52 202 | 51 564 | 51 774 | 51 774 |
| Other revenue | 561 | 563 | 836 | 882 | 563 | 563 |
| Total Revenue (excluding capital transfers and contributions) |  |  |  |  |  |  |
| Variances are calculated by dividing the difference between actual and original/adjustments budget by the actual. This table is aligned to MBRR table A4. |  |  |  |  |  | T K.2 |

## APPENDIX T – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT

| National and Provincial Outcomes for Local Government |  |  |
| --- | --- | --- |
| Outcome/Output | Progress to date | Number or Percentage Achieved |
| Output: Improving access to basic services | N/A |  |
| Output: Implementation of the Community Work Programme | N/A |  |
| Output: Deepen democracy through a refined Ward Committee model | N/A |  |
| Output: Administrative and financial capability | Xhariep is doing well in terms of this output. For the past two financial years the municipality made remarkable strides in terms of improving its Audit opinion from a qualification to unqualified. Budget related policies are in place and approved by Council. Financial statements are GRAP Compliant. | 85% |
| T T |  |  |

## VOLUME II: ANNUAL FINANCIAL STATEMENTS

Provide the Annual Financial Statements (AFS) to the respective financial year as submitted to the Auditor-General. The completed AFS will be Volume II of the Annual Report.