2016/2017

XHARIEP DISTRICT MUNICIPALITY

# CONTENTS

CONTENTS	2

PROPOSED REVISED ANNUAL REPORT TEMPLATE	6

CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY	7

COMPONENT A: MAYOR’S FOREWORD	7

COMPONENT B: EXECUTIVE SUMMARY	8

1.1.	MUNICIPAL MANAGER’S OVERVIEW	8

1.2.	MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW	9

1.3.	SERVICE DELIVERY OVERVIEW	12

1.4.	FINANCIAL HEALTH OVERVIEW	12

1.5.	ORGANISATIONAL DEVELOPMENT OVERVIEW	13

1.6.	AUDITOR GENERAL REPORT	14

1.7.	STATUTORY ANNUAL REPORT PROCESS	15

CHAPTER 2 – GOVERNANCE	17

COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE	17

2.1	POLITICAL GOVERNANCE	18

2.2	ADMINISTRATIVE GOVERNANCE	20

COMPONENT B: INTERGOVERNMENTAL RELATIONS	22

2.3	INTERGOVERNMENTAL RELATIONS	22

COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION	23

2.4	PUBLIC MEETINGS	23

2.5	IDP PARTICIPATION AND ALIGNMENT	26

COMPONENT D: CORPORATE GOVERNANCE	27

2.6	RISK MANAGEMENT	28

2.7	ANTI-CORRUPTION AND FRAUD	29

2.8	SUPPLY CHAIN MANAGEMENT	29

2.10	WEBSITES	30

CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)	32

COMPONENT A: BASIC SERVICES	33

3.11	LOCAL ECONOMIC DEVELOPMENT (INCLUDING TOURISM AND MARKET PLACES)	34

3.64	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC	37

3.67	OTHER (DISASTER MANAGEMENT)	38

COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES	40

3.69	EXECUTIVE AND COUNCIL	40

3.70	FINANCIAL SERVICES	42

3.71	HUMAN RESOURCE SERVICES	44

3.72	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES	46

COMPONENT K: ORGANISATIONAL PERFORMANCE SCORECARD	48

CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE	86

(PERFORMANCE REPORT PART II)	86

COMPONENT A: INTRODUCTION TO THE MUNICIPAL PERSONNEL	87

4.1	EMPLOYEE TOTALS, TURNOVER AND VACANCIES	87

COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE	88

4.2	POLICIES	89

4.3	INJURIES, SICKNESS AND SUSPENSIONS	90

COMPONENT C: CAPACITATING THE MUNICIPAL WORKFORCE	92

4.5	SKILLS DEVELOPMENT AND TRAINING	93

COMPONENT D: MANAGING THE WORKFORCE EXPENDITURE	96

CHAPTER 5 – FINANCIAL PERFORMANCE	97

5.3	ASSET MANAGEMENT	97

COMPONENT D: OTHER FINANCIAL MATTERS	98

5.12	SUPPLY CHAIN MANAGEMENT	98

5.13	GRAP COMPLIANCE	98

CHAPTER 6 – AUDITOR GENERAL AUDIT FIND	99

COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS 2014/2015	99

6.1 AUDITOR GENERAL REPORT 2015/2016(Previous year)	99

COMPONENT B: AUDITOR-GENERAL OPINION 2016/2017 (CURRENT YEAR)	103

6.2 AUDITOR GENERAL REPORT 2016/2017	103

Report of the auditor-general to the Free State Legislature and the council on the Xhariep District Municipality	103

Report on the audit of the financial statements	103

Opinion	103

Basis for opinion	103

Material uncertainty related to going concern	103

Emphasis of matters	104

Restatement of corresponding figures	104

Other matter	105

Responsibilities of the accounting officer for the financial statements	105

Auditor-general’s responsibilities for the audit of the financial statements	105

Report on the audit of the annual performance report	105

Introduction and scope	105

Other matters	106

Report on audit of compliance with legislation	107

Introduction and scope	107

Other information	108

Internal control deficiencies	109

Annexure – auditor-general’s responsibility for the audit	111

Financial statements	111

Communication with those charged with governance	112

GLOSSARY	113

APPENDICES	116

APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE	116

APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES	118

APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY	119

APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE 2016/2017	121

APPENDIX H(i) – Long Term Contracts (20 Largest Contracts Entered into during 2016/2017	122

APPENDIX I –SERVICE PROVIDER PERFORMANCE SCHEDULE	123

APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS	125

APPENDIX K (i): REVENUE COLLECTION PERFORMANCE BY Source	126

APPENDIX T – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT	127

VOLUME II: ANNUAL FINANCIAL STATEMENTS( Attached as an Annexure)	128

Management Action Plan……..……………………………………………………………………………………………………………………192

# PROPOSED REVISED ANNUAL REPORT TEMPLATE

The purpose of this revised Annual Report template is to address the need expressed by a number of municipalities for assistance in the preparation and development of improved content and quality of Municipal Annual Reports. It replaces a template dating back to August 2003.

This template gives effect to the legal framework requirement, concepts and principals espoused in the White Paper on Local Government and Improving Government Performance.  It reflects the ethos of public accountability.  The content gives effect to information required for better monitoring and evaluation of government programmes in support of policy decision making. The template provides an improved overview of municipal affairs by combining the performance report data required under Municipal Systems Act Section 46 with annual report data referred to in that Act and in the MFMA.

The revised template makes its contribution by forging linkages with the Integrated Development Plan, Service Delivery and Budget Implementation Plan, Budget Reforms, In-year Reports, Annual Financial Statements and Performance Management information in municipalities.  This coverage and coherence is achieved by the use of interlocking processes and formats.

The revised template relates to the Medium Term Strategic Framework particularly through the IDP strategic objectives; cross cutting nature of services offered by different spheres of government, municipal service outcome indicators; and the contextual material as set out in Chapters 3, 4 & 5.  It also provides information on good management practice in Chapter 4; risk management in Chapter 2; and Supply Chain Management in Chapter 5; and addresses the Auditor-General’s Report, dealing with Financial and Performance Management arrangements in Chapter 6.  This opens up greater possibilities for financial and nonfinancial comparisons between municipalities and improved value for money.

The revised template provides information on probity, including: anti-corruption strategies; disclosure of financial interests by officials and councillors; disclosure of grants by external parties, disclosure of loans and grants by municipalities.  The appendices talk to greater detail including disaggregated information on municipal wards, among others.

Notes are included throughout the format to assist the compiler to understand the various information requirements. Once the draft has been finalised, training will be provided to facilitate the implementation of this initiative, and separate additional guidance may be issued if necessary.

We wish to express our gratitude to the members of the Annual Report Reference Group, consisting of national, provincial and municipal officials for their inputs and support throughout the development of this document.

MFMA Implementation Unit, National Treasury                                                                                           October 2009

# CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY

## COMPONENT A: MAYOR’S FOREWORD

MAYOR’S FOREWORD Presenting yet another annual report of Xhariep District Municipality is indeed a great privilege and honour. This annual report presents the contents of a collaborative effort between Councillors, municipal officials, communities and all our key stakeholders. It presents all of our efforts and tireless work in creating, sustaining and scaling change in the lives of the ordinary citizens of our municipality. At the beginning of the reporting year we made it our endeavour to stick to the electorate mandate and the priorities of our communities as contained in our institution’s Integrated Development Plan while building on the successes of the preceding financial years. Sticking to the electorate mandate and priorities of our community required of us to adhere to the People’s first approach, which ensures that the focus of service delivery remains our communities. Local government and communities face major challenges, which are reducing unemployment, more access to better quality basic services, overcoming the legacy of apartheid spatial development, strengthening community participation, and building effective, accountable and clean local government. The past financial year has been an eventful year with much activity from all the roleplayers in Xhariep Municipality to ensure we meet the goals that we have set for ourselves in our political programme. In realising our mission of continuously improving and developing living conditions of our communities through provision of basic services, our IDP has been and will continue to be the guiding tool. It contains the priorities such as infrastructure development, development of the local economy, job creation, social development, sports, arts and culture, community services, good governance and community participation as well as financial viability. We have also endeavoured to align our budgets with our priorities, and ensured that we are much prudent with spending of the very limited financial resources at our disposal. In ensuring that our municipality has adequate capacity to deliver to its optimal level, our staff also received necessary training in their own respective fields. We will further continue ensuring that all the staff, inclusive of the lower levels, also receive training relevant to their posts and support in doing their work. The year under review was however not without its own challenges and pitfalls, but from all those we were able to learn better lessons and picked ourselves up to ensure that our municipality rose up to those demands and steers its ship forward. Let me express the words of gratitude to the speaker, chief whip, all Councillors, Members of Mayoral Committee, Senior Management, Middle Management and the staff of Xhariep District Municipality as well as the whole community of Xhariep. Yours in service delivery ……………………………………. Cllr MJ Sehanka Executive Mayor T 1.0.1

## COMPONENT B: EXECUTIVE SUMMARY

### MUNICIPAL MANAGER’S OVERVIEW

MUNICIPAL MANAGER’S OVERVIEW In many respects 2016/17 was an eventful financial year for the municipality. Whereas the municipality faced a considerable number of obstacles and challenges, in the same token, recognizable milestones have been achieved and significant strides have been taken in addressing some of the perennial challenges that still beset the municipality. At the beginning of this financial year, there was recognition that whereas we have already laid down a solid foundation for effective operational systems over the past two years, it is important to consolidate our successes and achievements more from an explicit strategic approach. The municipality took note of the fact that legislation gives effect to local government systems that place greater service delivery responsibilities on managers and make them more accountable for performance, and in response to these, we had to gear all our administrative departments and units towards gradual improvement to ensure better performance at all levels. The operating strategies and programmes as set out in the Integrated Development Plan, the Budget and the Budget Implementation Plan (SDBIP), which constitutes the basis for performance and reporting, were formulated and developed from a forward looking perspective, aimed at not only consolidating on our previous achievements, but also taking into account critical challenges that we still have to overcome. Xhariep District Municipality believes that this approach did not only bring about the desired performance results in this financial year, but has also strengthened our ability to exercise proper accountability to council, stakeholders and communities. Confidently, Xhariep District Municipality is a completely different organization today compared to the same period last year and any other year before. There is a vast scale of improvements in different key performance areas. The municipality will therefore strive to do even better with the limited resources at our disposal. Thank you ………………………………. LY Moletsane Municipal Manager T1.1.1

### MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW

INTRODUCTION TO BACKGROUND DATA

Out of 16 district functions, Xhariep district municipality is performing 3(18.75%) of these functions. Xhariep District is the smallest compared to the others within Free State Province with about 5.2% share of the total provincial population. The population of the District stands at 146, 259 with a negative growth rate of 1.07. Sixty (60%) of the population is in the working age cohort of 15-64 years.

T 1.2.1

Population by Age Distribution

| DC16: Xhariep (YEARS) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Letsemeng | Kopanong | Mohokare | Total |
| 0-14 | 9955 | 13007 | 10393 | 33355 |
| 15-34 | 15794 | 18802 | 13613 | 48209 |
| 35-64 | 10656 | 13227 | 8245 | 32128 |
| 65+ | 3639 | 4964 | 3589 | 12192 |
| Grand Total | 40044 | 50000 | 35840 | 125884 |

Data Source: Statssa community survey 2016 T1.2.2

SOCIO ECONOMIC STATUS: Economically Active Population per local municipality

| Local Municipality | Number | Percentage (%) |
| --- | --- | --- |
| Kopanong | 19472 | 29.54 |
| Letsemeng | 16639 | 30.53 |
| Mohokare | 12110 | 32.63 |

Data Source: STATSSA (Census 2011 Survey)

OVERVIEW OF NEIGHBOURHOODS WITHIN (NAME OF MUNICIPALITY

| Type of dwellings | FS161: Letsemeng | FS162: Kopanong | FS163: Mohokare |
| --- | --- | --- | --- |
| House or brick/concrete block structure on a separate stand or yard or on a farm | 9016 | 13904 | 9027 |
| Traditional dwelling/hut/structure made of traditional materials | 17 | 57 | 74 |
| Flat or apartment in a block of flats | 63 | 80 | 62 |
| Cluster house in complex | 12 | 11 | 5 |
| Townhouse (semi-detached house in a complex) | 36 | 31 | 1 |
| Semi-detached house | 76 | 20 | 97 |
| House/flat/room in backyard | 133 | 197 | 103 |
| Informal dwelling (shack; in backyard) | 634 | 475 | 838 |
| Informal dwelling (shack; not in backyard; e.g. in an informal/squatter settlement or on a farm) | 1179 | 739 | 483 |
| Room/flat let on a property or larger dwelling/servants quarters/granny flat | 22 | 51 | 55 |
| Caravan/tent | 5 | 6 | 9 |

T 1.2.6

| Natural Resources |  |
| --- | --- |
| Major Natural Resource | Relevance to Community |
| Water (Gariep Dam) | Supply of water to households and generation of electricity. |
| Diamonds (Jaggersfontein and Koffiefontein) | Job creation, Revenue enhancement, Economic development, human settlement. |
| Uranium (Edenburg) | Job creation, Revenue enhance, Economic development, human settlement |
| Land | Job creation through farming and settlement of communities |
| Sun (Radiation energy) | Job creation through erection of solar hubs |
|  | T1.2.7 |

COMMENT ON BACKGROUND DATA:

Xhariep District forms the southern part of the Free State Province and is one of four district municipalities in the Free State. The municipality measures 34289 km sq. It is bordered by Tokologo Municipality in Lejweleputswa District to the north, Mangaung Metro and Mantsopa Municipality in Thabo Mofutsanyana District to the north-east. Other borders are with the Kingdom of Lesotho to the east, Ukhahlamba Municipality in Eastern Cape Province to the south, Pixley ka Seme Municipality in Northern Cape Province to the west and Frances Baard Municipality in Northern Cape Province to the north-west. Topographically the district is bordered for most of its eastern border by the Maluti and Drakensberg mountains. Hydrological the district is located between the Vaal River to the north, and Orange River to the south, with rivers within the district draining towards these rivers. Xhariep consists of three local municipal areas, with Letsemeng forming the north western section, Kopanong the middle section, Mohokare the south eastern section of the district

T1.2.8

### SERVICE DELIVERY OVERVIEW

SERVICE DELIVERY INTRODUCTION

The district municipality started to perform the functions of Environmental Health and Disaster Management with effect from December 2009. Critically, the Municipal Structures Amendment Act (Act 33 of 2000) provides for an extensive annual review of the division of powers and functions between Category B and Category C to ensure effective implementation of these assigned powers following an advice provided by the Municipal Demarcation Boarding emanating from the Boards’ annual capacity assessment report.

T 1.3.1

### FINANCIAL HEALTH OVERVIEW

FINANCIAL OVERVIEW

The municipality at large does not have a revenue base as it solely depends on grants from other spheres of government and that is putting a strain on the finances of the municipality as only a few projects can be carried out in a financial year

T1.4.1

| Financial Overview - 2016/2017 |  |  |  |
| --- | --- | --- | --- |
|  |  |  | R' 000 |
| Details | Original budget | Adjustment Budget | Actual |
| Income |  |  |  |
| Grants | 52 044 | 52 044 | 52 209 |
| Taxes, Levies and tariffs | 0 | 0 | 0 |
| Other | 574 | 574 | 1 101 |
| Sub Total | 52 618 | 52 618 | 53 310 |
| Less Expenditure | 52 618 | 52 618 | 58 413 |
| Net Total* | 0 | 0 | 5 103 |
| * Note: surplus/(defecit)_Deficit due to depreciation. |  |  | T1.4.2 |

| Operating Ratios |  |
| --- | --- |
| Detail | % |
| Employee Cost | 70% |
| Repairs & Maintenance | 0.19% |
| Finance Charges & Impairment | 2.7% |
|  | T 1.4.3 |

COMMENT ON OPERATING RATIOS

Employee cost is excessively above the expected norm of 30%, repairs and maintenance significantly lower than the 20% norm and finance charges considerably lower than the 10% benchmark

T1.4.3

### ORGANISATIONAL DEVELOPMENT OVERVIEW

ORGANISATIONAL DEVELOPMENT PERFORMANCE

Organization Development (OD) is about improving performance at the individual, group, and Municipal organizational levels. It is about improving the organization's ability to effectively respond to changes in its external environment, and it’s about increasing internal capabilities by ensuring the Xhariep District Municipal structures, human resources systems, job designs, communication systems, and leadership/managerial processes fully harness human motivation and help people function to their full potential.

Done well, such improvement can be transformational—producing fundamental changes in the way individuals, groups, and organizations functions.

T1.5.1

### AUDITOR GENERAL REPORT

AUDITOR GENERAL REPORT 2015/2016

Unqualified opinion

The financial statements submitted for auditing were not prepared in all material respects in accordance with the requirements of section 122 of the MFMA. Material misstatements of non-current assets, liabilities, expenditures and disclosure items identified by the auditors in the submitted financial statement were subsequently corrected and the supporting records were provided subsequently, resulting in the financial statements receiving an unqualified audit opinion.

T 1.6.1

### STATUTORY ANNUAL REPORT PROCESS

| No. | Activity | Timeframe |
| --- | --- | --- |
| 1 | Consideration of next financial year’s Budget and IDP process plan. Except for the legislative content, the process plan should confirm in-year reporting formats to ensure that reporting and monitoring feeds seamlessly into the Annual Report process at the end of the Budget/IDP implementation period | July |
| 2 | Implementation and monitoring of approved Budget and IDP commences (In-year financial reporting). |  |
| 3 | Finalise the 4th quarter Report for previous financial year |  |
| 4 | Submit draft 2015/2016 Annual Report to Internal Audit and Auditor-General |  |
| 5 | Municipal entities submit draft annual reports to MM |  |
| 6 | Audit/Performance committee considers draft Annual Report of municipality and entities (where relevant) | August |
| 8 | Mayor tables the unaudited Annual Report |  |
| 9 | Municipality submits draft Annual Report including consolidated annual financial statements and performance report to Auditor General |  |
| 10 | Annual Performance Report as submitted to Auditor General to be provided as input to the IDP Analysis Phase |  |
| 11 | Auditor General audits Annual Report including consolidated Annual Financial Statements and Performance data | September – October |
| 12 | Municipalities receive and start to address the Auditor General’s comments | November |
| 13 | Mayor tables Annual Report and audited Financial Statements to Council complete with the Auditor- General’s Report |  |
| 14 | Audited Annual Report is made public and representation is invited |  |
| 15 | Oversight Committee assesses Annual Report |  |
| 16 | Council adopts Oversight report | December |
| 17 | Oversight report is made public |  |
| 18 | Oversight report is submitted to relevant provincial councils |  |
| 19 | Commencement of draft Budget/ IDP finalisation for next financial year. Annual Report and Oversight Reports to be used as input | January |
| T1.7.1 |  |  |

# CHAPTER 2 – GOVERNANCE

INTRODUCTION TO GOVERNANCE

The Municipal Council uses a governance system that applies executive mayoral system. It is consisted of fourteen (14) Councillors with an Executive Mayor, Speaker and three (3) Mayoral Committee members are full time.

The Speaker presides over Ordinary and Special Council meetings and is also designated as a full time Councillor. The administration dispatch notices and agendas to Councillors forty eight (48) hours before the commencement of the council meeting as determined in the Standard Rule and Orders.

The Executive Mayor has executive powers and attends to day to day duties of the Municipal Council; and the three Mayoral Committee Members assist him in executing some of his responsibilities. One of the responsibilities of the Executive Mayor is to present the Mayoral Committee reports before Council.

The Municipality has appointed the Municipal Manager who is the head of the administration. He is responsible for day to day operations of the organization and accounts to the Executive Mayor. . Other managers who have been appointed in terms of section 56 of the Municipal Systems Act, 2000 reports directly to the Municipal Manager. It is important to highlight that the Municipality is composed of three departments, excluding the office of the Municipal Manager i.e. Corporate Services, Budget and Treasury Office and Planning and Social Development. These departments are headed by the section 56 Managers.

T2.0.1

## COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE

INTRODUCTION TO POLITICAL AND ADMINISTRATIVE GOVERNANCE

The Municipal Council is an executive mayoral system that was proclaimed in the Free State Provincial Gazette by the Minister of Cooperative Governance and Human Settlement. It consists of Sixteen (16) Councillors with an Executive Mayor, Speaker and three (3) Mayoral Committee members as full time Councillors

The Municipal Manager and managers directly accountable to the municipal manager organize administration in a manner that enables the Municipality to be responsive to the needs of the community within its jurisdiction. The Municipal Manager is the accounting officer who accounts to the political head, Executive Mayor as well as Council.  He further provides guidance and advice to the political structures and manages the administration of the institution

T2.1.0

### POLITICAL GOVERNANCE

INTRODUCTION TO POLITICAL GOVERNANCE

The Council has established the following Committees in terms of the Municipal Structures Act and the Municipal Finance Management Act:

Three Section 80 Committees that process items before they could be forwarded to the Mayoral Committee and eventually to Council i.e. Corporate Services Committee, Planning and Development Committee and Budget and Treasury Committee. Three Section 80 Committees that process items before they could be forwarded to the Mayoral Committee and eventually to Council i.e. Corporate Services Committee, Planning and Development Committee and Budget and Treasury Committee.

The different Departments of the Municipality prepare reports that are then submitted to the Section 80 Committees for deliberation. After the aforementioned Committees have processed the reports presented before them, they are forwarded to the Mayoral Committee for further processing. Thereafter these reports are taken to Council for consideration and adoption. Important to note is that the Section 80 Committees, Mayoral Committee and Council sit as per schedule of Council meetings that was adopted by the Council.

The Municipal Council has an Oversight Committee, which is composed of three members, one non-executive Councillor, one community member and one member of the Internal Audit Committee; and the Council by playing an Oversight role in the activities that are performed by the Municipality.

The Annual Report is prepared by the Performance Management Unit in collaboration with other departments. When the management is satisfied with this report it is then submitted to the Council for noting before the 31st of January of each year. Subsequent to this process it is forwarded to the Oversight Committee before the 31st March of each year for assessment and thereafter it is presented before the Council with the Committee comments and recommendations. The Annual Report and the Oversight Committee report are submitted to Departments of Treasury and Cooperative Governance and Traditional Affairs for comments. Furthermore, these reports are separately   published to the community for comments.

The Internal Audit Unit conducts audit throughout the year in terms of their audit plan and prepares Audit packs/reports that are then submitted to the Internal Audit Committee. After consideration of these reports the Audit Committee forwards its recommendations to Council for considerations. Council then resolves on the findings of the Shared Audit and Performance Committee with the intention to order the administration to remedy the findings revealed by the aforesaid Committee.

Note: MFMA S52 (a): The Mayor must provide general political guidance over the fiscal and financial affairs of the municipality

T2.1.1

|  | POLITICAL STRUCTURE MAYOR Cllr M.J Sehanka Exercises powers delegated to the Mayor by Council or the Executive Committee |  |  |
| --- | --- | --- | --- |
|  | SPEAKER Cllr NS Mnqunguthu Presides at Council meetings and exercises powers delegated to the Speaker in terms of section 59 of the Local Government: Municipal Systems Act, Act 32 of 2000. |  |  |
|  | CHIEF WHIP N/A To ensure political mandates are executed |  |  |
|  | MAYORAL COMMITTEE/ EXECUTIVE COMMITTEE Cllr KJ Sebeco: Chairperson of the Budget and Treasury Committee Cllr MG Ntwanambi:Chairperson of the Corporate Services Committee Cllr TD Mochechepa: Chairperson of Planning &Social Development Committee |  |  |

COUNCILLORS

The Municipal Council of Xhariep District Municipality is consisted of fifteen (15) Councilors. Seven of the fifteen Councilors are directly elected and eight (8) are seconded from the three local municipalities. Five Councilors are full time i.e the Executive Mayor, Speaker and three (3) Mayoral Committee members. Three members of the Mayoral Committee are designated as Chairpersons of Section 80 Committees. Both Budget and Treasury Committee, Planning and Social Development  and Corporate Services Committee are composed of four (4) members which includes the Chairperson of the Committee. And Corporate Services Committee is composed of four (4) members. Furthermore, it has established an oversight committee which is composed of five members, i.e. three Council members, one Community member and the Chairperson of the Shared and Performance Audit Committee.

T2.1.2

POLITICAL DECISION-TAKING

The Section 80 Committees sit as per schedule of Council meeting to process the items placed before them and make recommendations to the Mayoral Committee. These items are further processed by the Mayoral Committee and forwarded to the full sitting of Council with recommendations. Then the Council pronounces itself on the issues presented before it. The decisions are taken by majority of members present at the meeting. Where members share a different view on an item under consideration, they vote on the matter, either by show of hands or through a secret ballot as stipulated in the Standing Rules and Orders of Council. All the Resolutions passed by the Council are implemented by the administration.

T2.1.3

### 2.2	ADMINISTRATIVE GOVERNANCE

INTRODUCTION TO ADMINISTRATIVE GOVERNANCE

The Municipal Manager and managers directly accountable to the municipal manager organize administration in a manner that enables the Municipality to be responsive to the needs of the community within its jurisdiction. The Municipal Manager is the accounting officer who accounts to the political head, Executive Mayor as well as Council.  He further provides guidance and advice to the political structures; also manage the administration of the institution.

The Director: Corporate Services administer the Department of Corporate Services and advice the Municipal Manager with issues relating to administration, human resources and information technology. The Chief Financial Officer administers Budget and treasury Office and advice the Municipal Manager on matters that relate to the finances of the Municipality. The Director: Planning and Social Development is responsible for the affairs of the Department of Planning and Social Development, advices and assists the Municipal Manager on all matters that relates to this department, i.e. planning, local economic development and municipal health services.

T2.2.1

|  | TOP ADMINISTRATIVE STRUCTURE TIER 1 MUNICIPAL MANAGER Mr Mazondi Martiens Kubeka |  |
| --- | --- | --- |
| Directors | DIRECTOR: Corporate Services Vacant Chief Financial Officer(Acting) Montjane Clive Mogoale Director: Planning & Social Development Mr Mopedi Sam Mohale |  |
|  |  | T2.2.2 |

## COMPONENT B: INTERGOVERNMENTAL RELATIONS

INTRODUCTION TO CO-OPERATIVE GOVERNANCE AND INTERGOVERNMENTAL RELATIONS

Intergovernmental relations are mainly informal, making the system flexible to respond to changing circumstances. The approach of the Act is therefore that it does not seek to govern intergovernmental relations in its totality but provides only the broad framework in terms of which spheres of government interact with one another.

T 2.3.0

### 2.3	INTERGOVERNMENTAL RELATIONS

PROVINCIAL INTERGOVERNMENTAL STRUCTURE

The District is part of the Premiers’ Coordinating Forum which is used to facilitate intergovernmental relations between the province and local government in the province. The District also participates in Provincial Forums which include Provincial IDP Forum, Provincial Energy Forum, Provincial AIDS Forum as well as South African Local Government Association (SALGA).

T2.3.2

DISTRICT INTERGOVERNMENTAL STRUCTURES

Meetings are been held once in a quarter, whereby the District Municipality is responsible for ensuring the co-ordination of intergovernmental relations within the district municipality with local municipalities in the district. District Coordinating Forum: Forum consists of the Executive Mayor and 3 primary members of which is the Local Mayors.

Technical Support Committee

Forum consists of the District Municipal Manager and 3 primary members (Local Municipal Manager). The forum must meet at least once per year with service providers and other role players concerned with the development in the district to co-ordinate effective provision of services and planning in the district.

T2.3.4

## COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION

OVERVIEW OF PUBLIC ACCOUNTABILITY AND PARTICIPATION

The municipality has developed a comprehensive public participation strategy which is integrated in the development of the IDP and the Budget, the Municipal website if often used to publicise all the developments in the municipality including calls for public participation and comments on the IDP and Budget. After the adoption of the annual report the municipality also avail this document for public scrutiny as recommended by the MSA act 32 of 2000.

T 2.4.0

### 2.4	PUBLIC MEETINGS

COMMUNICATION, PARTICIPATION AND FORUMS In consideration with the mechanisms of effective public participation, the following processes and aspects were taken in consideration and were implemented as required. CONTEXT OF PUBLIC PARTICIPATION AS IMPLEMENTED Four major functions can be aligned with the public participation process namely: - Needs identification; - Identification of appropriateness of proposed solutions; - Community ownership and buy-in; and - Empowerment. MECHANISMS FOR PARTICIPATION The following mechanisms for participation were utilized: - IDP Representative Forum (IDP RF) This forum will represent all stakeholders and will be as inclusive as possible. Efforts will be made to bring additional organizations into the IDP RF and ensure their continued participation throughout the process. - Media Local newspapers were used to inform the community of the progress of the IDP and the Community consultation dates. - Information sheets These were prepared in English and be distributed to communities prier the start of all the meetings The DM’s Website The DM’s website was also utilized to communicate and inform the community. Copies of the IDP and Budget were placed on the website for people to download T2.4.1

| Public Meetings |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Nature and purpose of meeting | Date of events | Number of Participating Municipal Councillors | Number of Participating Municipal Administrators | Number of Community members attending | Manner of feedback given to community |
| IDP and Budget Public Participation | 13-04-2016 | 1 | 9 | 185 | IDP and Budget presentations |
| IDP and Budget Public Participation | 14-04-2016 | 0 | 10 | 30 | IDP and Budget presentations |
| IDP and Budget Public Participation | 15-04-2016 | 2 | 8 | 13 | IDP and Budget presentations |
| IDP and Budget Public Participation | 20-04-2016 | 1 | 7 | 84 | IDP and Budget presentations |
| T2.4.3 |  |  |  |  |  |

COMMENT ON THE EFFECTIVENESS OF THE PUBLIC MEETINGS HELD:

As per the requirements of the Municipal Systems act and the Municipal Finance Management Act the municipality has a series of outreach consultations including the IDP and Budget consultative sessions with the communities of the Xhariep District. The Municipal council has also adopted public participation strategy

The Local Government Municipal Management Act (MFMA, Act 56 of 2003) puts at the Centre of this process the voice of the people. The MFMA calls for active participation and input from the public in the budgeting process as well as the alignment of the budget to the IDP

In order to ensure public participation in local governance, government has over time put in place various pieces of legislation and policies. The following are some of the legislative and policy provisions aimed at fostering public participation at local government level:

The Constitution – 1996

Municipal Structures Act &White Paper on Local Government – 1998

Municipal Systems Act-2000

Municipal Finance Management Act-2003

Municipal Property Rates Act-2004

Municipal Finance Management Act-2003

Guidelines for Operation of Ward Committees-2005

T2.4.3.1

### 2.5	IDP PARTICIPATION AND ALIGNMENT

| IDP Participation and Alignment Criteria* | Yes/No |
| --- | --- |
| Does the municipality have impact, outcome, input, output indicators? | Yes |
| Does the IDP have priorities, objectives, KPIs, development strategies? | Yes |
| Does the IDP have multi-year targets? | Yes |
| Are the above aligned and can they calculate into a score? | Yes |
| Does the budget align directly to the KPIs in the strategic plan? | Yes |
| Do the IDP KPIs align to the Section 57 Managers | Yes |
| Do the IDP KPIs lead to functional area KPIs as per the SDBIP? | Yes |
| Do the IDP KPIs align with the provincial KPIs on the 12 Outcomes | Yes |
| Were the indicators communicated to the public? | Yes |
| Were the four quarter aligned reports submitted within stipulated time frames? | Yes |
| * Section 26 Municipal Systems Act 2000 | T2.5.1 |

## COMPONENT D: CORPORATE GOVERNANCE

OVERVIEW OF CORPORATE GOVERNANCE

As the Head of Administration the Municipal Manager is responsible for the following tasks:

-The formation and development of an economical, effective, efficient and accountable administration.

- The management of the municipality’s administration in accordance with legislation applicable to the municipality.

-The implementation of the municipality’s integrated development plan.

-The management and provision of services to the local communities in a sustainable and equitable manner.      -The appointment of staff subject to the Employment Equity Act, 1998.

-The management and effective utilisation and training of staff.

-The maintenance of discipline of staff.

-The promotion of sound labour relations and compliance with labour legislation.

- Advising the political structures and political office bearers of the municipality.

-Managing communications between the municipality’s administration and its political structures and political office bearers.

-Carrying out the decisions of the political structures and political office bearers of the municipality.

-The administration and implementation of the municipality’s by-laws and other legislation.

-The exercise of any powers and the performance of any duties delegated by the municipal council.

-Facilitating participation by the local community in the affairs of the municipality.

-The implementation of national and provincial legislation.

T2.6.0

### 2.6	RISK MANAGEMENT

RISK MANAGEMENT

The Xhariep District Municipality is committed to the effective risk management and treatment of risk in order to achieve its objectives. Management of risk is the responsibility of all Executive, Senior Management and employees and Section 62 (1) (c) (i) of the MFMA requires that:

“The municipality has and maintains: Effective, efficient and transparent systems of financial and risk management and internal control.”

Treasury Regulations S3.2.1 further prescribes that the Accounting Officer must ensure that a risk assessment is conducted regularly to identify emerging risks of the institution. A risk management strategy, which must include a fraud prevention plan, must be used to direct internal audit effort and priority, and to determine the skills required of managers and staff to improve controls and to manage these risks. The strategy must be clearly communicated to all officials to ensure that the risk management strategy is incorporated into the language and culture of the institution and thus creating an environment of working together in a consistent and integrated manner, with the overall objective of reducing risk, as far as reasonably practicable.

The embedding of risk management within the municipality is a proactive approach in mitigation of events that will have a negative impact in the achievement of municipal goals and objectives; risk management thus assists Xhariep District Municipality in:

1. Supporting the efficient use of resources (Risk Based decision making)

2. Promoting continuous improvement

3. Minimizing surprises,

4. Reassuring stakeholders,

5. Rationalization of capital and financial issues,

6. Helps internal audit to comply with Internal Audit Framework and IIA Standards

7. Continuity of service delivery

The Accounting Officer commits the Xhariep District Municipality to a process of risk management that is aligned to the principles of good corporate governance, as supported by:

Municipal Finance Management Act (MFMA), Act 56 of 2003;

Municipal Systems Act (MSA) Act 32 of 2000);

Municipal Structures Act (MSA) Act 117 of 1998); and

Treasury Regulations 3.2.1                                                                                                                                             T2.6.1

### 2.7	ANTI-CORRUPTION AND FRAUD

FRAUD AND ANTI-CORRUPTION STRATEGY

Fraud is defined as the intentional, false representation or concealment of a material fact for the purpose of inducing another to act upon it to his or her injury.

Xhariep District Municipality has a ZERO TOLERANCE to Fraud and Corruption and thus has the intent to promote consistent organizational behavior by providing guidelines and assigning responsibilities for the development of controls and conduction of investigations relating to fraud and corruption.

The fraud prevention strategy and policy are such documents designed to align Xhariep District Municipality with Municipal Finance Management Act which states that each municipality must develop an effective, efficient and transparent system of financial, risk management and internal control. Fighting against corruption is a national priority and Xhariep District Municipality positions itself to combat the scourge of fraud and corruption.

The fraud and corruption strategy demonstrates the stance of the municipality in preventing and detecting fraudulent and corrupt activities as well as corrective action when fraud has been committed

T2.7.1

### 2.8	SUPPLY CHAIN MANAGEMENT

OVERVIEW SUPPLY CHAIN MANAGEMENT

As far as the processes are concerned, a MEMO for DEMAND and ACQUISITION has been developed by the municipality to manage, control and monitor procurement of goods and services. The MEMO is signed by the responsible manager to confirm the need of the service or product, the manager for Budget and Reporting Unit confirms the budget availability, relevant HOD recommends as well as the CFO and the Accounting Officer/Municipal Manager or a Senior Manager designated to act in the capacity of the Municipal Manager, finally approves the MEMO for DEMAND and ACQUISITION. During 2016/2017 financial year, Supply Chain Management Policy of the Municipality was adopted by council on the 7th of July 2017 for implementation in the 2017/2018 financial year. The municipality also uses the Procurement Procedure Manual to help it in achieving its policy the 2017/2018 financial year. The municipality also uses the Procurement Procedure Manual to help it in achieving its policy the 2017/2018 financial year. The municipality also uses the Procurement Procedure Manual to help it in achieving its policy objectives

T2.8.1

### 2.10	WEBSITES

| Municipal Website : Content and Currency of Material |  |  |
| --- | --- | --- |
| Documents published on the Municipality's / Entity's Website | Yes / No | Publishing Date |
| Current annual and adjustments budgets and all budget-related documents | Yes |  |
| All current budget-related policies | Yes |  |
| The previous annual report (2015/2016) | Yes |  |
| The annual report (2016/2017) published/to be published | Document too big to be uploaded on the municipal website |  |
| All current performance agreements required in terms of section 57(1)(b) of the Municipal Systems Act (2016/2017) and resulting scorecards | Yes |  |
| All service delivery agreements (2016/2017) | No (documents were not submitted to IT for upload on the municipal website) |  |
| All long-term borrowing contracts (2016/2017) | No (documents were not submitted to IT for upload on the municipal website) |  |
| All supply chain management contracts above a prescribed value (give value) for 2016/2017 | Yes (contract register) |  |
| An information statement containing a list of assets over a prescribed value that have been disposed of in terms of section 14 (2) or (4) during 2016/2017 | No (documents were not submitted to IT for upload on the municipal website) |  |
| Contracts agreed in 2016/2017 to which subsection (1) of section 33 apply, subject to subsection (3) of that section | No (documents were not submitted to IT for upload on the municipal website) |  |
| Public-private partnership agreements referred to in section 120 made in 2016/2017 | No (documents were not submitted to IT for upload on the municipal website) |  |
| All quarterly reports tabled in the council in terms of section 52 (d) during 2016/2017 | No (documents were not submitted to IT for upload on the municipal website) |  |
| *The municipal website does not show the dates of uploading of the documents. |  | T2.10.1 |

COMMENT MUNICIPAL WEBSITE CONTENT AND ACCESS

The website of the Municipality is fully functional, all the documents that were submitted by user departments to be uploaded on the municipal website were uploaded in the 2016/17 financial year.

T2.10.1.1

# CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)

INTRODUCTION

The district municipality is performing the functions of Municipal Health Services and Disaster Management with effect from December 2009. Critically, the Municipal Structures Amendment Act (Act 33 of 2000) provides for an extensive annual review of the division of powers and functions between Category B and Category C to ensure effective implementation of these assigned powers following an advice provided by the Municipal Demarcation Board emanating from the Boards’ annual capacity assessment report.

T3.0.1

## COMPONENT A: BASIC SERVICES

| Financial Performance 2016/2017: Planning Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2015/2016 | 2016/2017 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 11 549 | 12 378 | 12 378 | 14 608 | (2 230) |
| Expenditure: |  |  |  |  |  |
| Employees | 7 195 | 8 016 | 8 016 | 9 132 | (1 116) |
| Repairs and Maintenance |  |  |  |  |  |
| Other | 4 869 | 4 362 | 4 362 | 3 955 | 407 |
| Total Operational Expenditure | 12 064 | 12 378 | 12 378 | 13 087 | (709) |
| Net Operational Expenditure | (515) | 0 | 0 | 1 521 | (1521) |
|  |  |  |  |  | T3.10.5 |

### 3.11	LOCAL ECONOMIC DEVELOPMENT (INCLUDING TOURISM AND MARKET PLACES)

INTRODUCTION OF ECONOMIC DEVELOPMENT

Local economic development offers local government, the private sector, not-for-profit sectors and local communities the opportunity to improve the economy. It focuses on enhancing competitiveness, increasing sustainable growth and ensuring that growth is inclusive.

The White Paper on Local Government (1998) and the South African National Framework on LED (2006) clearly states that Local government is not responsible for creation of jobs, rather it is responsible for taking active steps to ensure that the overall economic and social conditions of locality are conducive to the creation of employment opportunities, provision of infrastructure and quality services.

The role of the District for economic growth is to coordinate, facilitate and to support the initiatives brought to its attention. The sectors that are the main drivers of the district economy are outlined in the LED Strategy to provide guideline on the effective implementation of LED within our area of jurisdiction.

Tourism has the potential to boost the economic growth of the area. The District by supporting tourism activities is fulfilling its obligation of developing tourism in the area, as tourism has the potential to generate growth and development because it brings financial resources into an area (either as capital investment or as the spending power of tourists).

Agriculture is the largest contributor to the district economy accounting for the highest GDP contributor and the main source of income and employment for the largest population of the District. The agricultural sector in Xhariep District has experience high growth in production (GDP) approximately 12.2% per annum.

Manufacturing The manufacturing sector in the Xhariep District Municipality is relatively small with a limited variety of manufacturing activities and establishment of manufacturing firms within Xhariep can boost economic growth and curb unemployment rate.

Mining activities are concentrated mainly in the Jagersfontein and Koffiefontein areas and are mainly limited to diamond mining and some other associated precious and semi-precious minerals.

Tourism in Xhariep is currently limited to a small number of domestic visitors from other parts of the country. The tourism location quotient (1.1) indicates that more tourism activities are evident in Xhariep compared to the rest of the Free State. Awareness campaigns are conducted annually with the aim to inform residence about tourism opportunities that can be explored and events coordinated by private sector are supported.

T3.11.1

| Jobs Created during 2015/2016 by LED Initiatives (Excluding EPWP projects) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Total Jobs created / Top 3 initiatives | Jobs created | Jobs lost/displaced by other initiatives | Net total jobs created in year | Method of validating jobs created/lost |
|  | No. | No. | No. |  |
| Total (all initiatives) | - | - | - | - |
|  | - | - | - | - |
| 2015/2016 | - | - | - | - |
| 2016/2017 | - | - | - | - |
| Initiative A (2016/2017) | 5 | 2 | 5 | Identify beneficiaries, reporting, monitoring and implementing |
| Initiative B (2016/2017) | 13 | - | 13 | Identify beneficiaries, reporting, monitoring and implementing |
| Initiative C (2016/2017) | - | - | - | - |
|  |  |  |  | T3.11.5 |

| Job creation through EPWP* projects |  |  |
| --- | --- | --- |
| Details | EPWP Projects | Jobs created through EPWP projects |
|  | No. | No. |
| 2014/2015 | 1 | 123 |
| 2015/2016 | 4 | 189 |
| 2016/2017 | 3 | 185 |
| * - Extended Public Works Programme |  | T3.11.6 |

| Employees: Local Economic Development Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2015/2016 | 2016/2017 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 0 | 0% |
| 4 – 6 | 2 | 2 | 2 | 0 | 0% |
| 7 – 9 | 0 | 0 | 0 | 0 | 0% |
| 10 – 12 | 0 | 0 | 0 | 0 | 0% |
| 13 – 15 | 0 | 0 | 0 | 0 | 0% |
| 16 – 18 | 0 | 0 | 0 | 0 | 0% |
| 19 – 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 3 | 3 | 3 | 0 | 0% |
| T3.11.8 |  |  |  |  |  |

### 3.64	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC

INTRODUCTION TO HEALTH INSPECTIONS; FOOD AND ABATTOIR LICENCING AND INSPECTIONS, ETC

A key role responsibility in rendering an effective Municipal Health Services is the monitoring of  food and government premises in order to ensure compliance with R926, Foodstuffs, Cosmetics and Disinfectants act 1972 (Act no. 54 of 1972) and the National health act, 2003 (Act no 63 of 2003).

District Environmental Health Practitioners conduct health inspections of premises and issue out compliance notices to food premises which are found to be non-compliant with the set legislation. A certificate of acceptability (COA) is issued in accordance with the legislation to compliant premises.  Certificate of health are issued to compliant ECD’s and old age homes. Operational licences are the competency of the local municipality and other stakeholders.

Surveillance of premises is also conducted to insure vector control and to monitor health and hygiene standards of premises.

The following activities are measured:  These ensure that there is constant monitoring of compliance.

No. of COA’s issued

No. of non-compliance notices issued

No. of health inspections conducted.

Bimonthly raids are conducted with the assistance of SAPS to curb non -compliance by shop owners and seize expired foods. Monthly monitoring of all premises is conducted by the Environmental Health Practitioners.

T3.64.1

### 3.67	OTHER (DISASTER MANAGEMENT)

INTRODUCTION TO DISASTER MANAGEMENT

Disaster Management is a continuous and integrated multi-sectoral and multi-disciplinary process of planning and implementation of measures aimed at disaster prevention, -mitigation, -preparedness, -response, -recovery and –rehabilitation

Top Four Service Delivery Priorities:

1. Community Safety

2. Preparedness

3. Recovery and Rehabilitation

4. Educational Program

The DM Unit main role is to ensure a safe and unwavering environment to the Xhariep district community. Through proper planning the Unit will be able to build resilient communities through the Disaster Management Activities within the district Municipality. A budget for the review of the DM Plan, DM training and DM relief was approved to enhance the previous achievements and to implement the plan for mitigation through education, awareness and training. The DM Unit played a vital role to assist disaster stricken victims throughout the district in rebuilding of houses and rehabilitation.                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                    T3.67.1

| Employees: Disaster Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2015/2016 | 2016/2017 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 0 | 0% |
| 4 – 6 | 2 | 2 | 2 | 0 | 0% |
| 7 – 9 | 1 | 0 | 0 | 0 | 0% |
| 10 – 12 | 0 | 0 | 0 | 0 | 0% |
| 13 – 15 | 0 | 0 | 0 | 0 | 0% |
| 16 – 18 | 0 | 0 | 0 | 0 | 0% |
| 19 – 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 4 | 3 | 3 | 0 | 0% |
| T3.67.4 |  |  |  |  |  |

COMMENT ON THE PERFORMANCE OF DISASTER MANAGEMENT

The Disaster Management Plan and Disaster Management Framework were reviewed as compelled by the Disaster Management Act (57/2002). Regular Disaster Management Advisory Forum meetings are held. Assistance with Disaster Management in general is given to all Local Municipalities in the District. The Municipality is trying to educate the communities through awareness campaigns and with Disaster Management Programs at the primary schools. This, in a way will help us to prepare for and minimizes the impact of disastrous incidents in the area. Training and workshop for Councillors, Ward Committees, Disaster Management Forums and Volunteer Groups are planned to enhance our Disaster Management educational program.

The Disaster Management Unit attends to most of the incidents within the District to record the incident and report to the authorities and the respective relevant parties. Due to financial constraints, the Unit cannot support all the victims financially.

T3.67.7

## COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES

This component includes: corporate policy offices, financial services, human resource services, ICT services

INTRODUCTION TO CORPORATE POLICY OFFICES

The Municipality has developed required policies as per directive of legislations that govern the local sphere of government for all aspects of the Municipality, i.e. financial services, Human Resources, performance management, risk management, disaster management, Local Economic Development strategy, Expanded Public Works Programme Policy and Internal audit Charter.

T3.69.0

### 3.69	EXECUTIVE AND COUNCIL

This component includes: Executive office (mayor; councilors; and municipal manager).

INTRODUCTION TO EXECUTIVE AND COUNCIL

Municipality is currently executing three service delivery related matters, i.e. local economic development,   Disaster Management and Municipal Health Services. The Local Economic Development Division that is located within the Department of Planning and Social Development has made strides in providing financial assistance and providing training to Small Micro and Medium Enterprises. The Municipality has assisted interested individuals or group of people to establish their own businesses, in particular cooperatives.

The Environmental Health Services Division that is also located within the Department of Planning and Social Development is monitoring the quality of drinking water and final waste water effluent from different local municipalities that fall within its jurisdiction on frequent intervals as required by applicable legislations and policies. Furthermore this division insures compliance of food premises and local municipalities’ landfill sites.

The Disaster Management Division is located in the Office of the Municipal Manager. The division is responsible to ensure a safe and unwavering environment to the Xhariep district community.                                                                                                                                                                                           T3.69.1

| Financial Performance 2016/2017: The Executive and Council |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2015/2016 | 2016/2017 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 8 216 | 11 949 | 11 949 | 11 672 | 277 |
| Expenditure: |  |  |  |  |  |
| Employees | 9 679 | 9 278 | 9 278 | 9 076 | 202 |
| Repairs and Maintenance |  |  |  |  |  |
| Other | 11 693 | 4 470 | 4 470 | 8 101 | (3631) |
| Total Operational Expenditure | 21 372 | 13 748 | 13 748 | 17 177 | (3429) |
| Net Operational Expenditure | (13 156) | (1 799) | (1 799) | (5 505) | 3706 |
| *Deficit is materially due to depreciation (non-cash item). **The Executive and Council includes General Council and Municipal Manager |  |  |  |  | T3.69.5 |

### 3.70	FINANCIAL SERVICES

INTRODUCTION FINANCIAL SERVICES

The Budget and Treasury Office is responsible for the financial administration and management of the municipality.

T3.70.1

| Employees: Financial Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2015/2016 | 2016/2017 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 4 | 4 | 4 | 0 | 0% |
| 4 - 6 | 6 | 6 | 6 | 0 | 0% |
| 7 - 9 | 6 | 6 | 6 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 16 | 16 | 16 | 0 | 0% |
| . T3.70.4 |  |  |  |  |  |

| Financial Performance 2016/2017: Financial Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2015/2016 | 2016/2017 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 14 280 | 12 093 | 12 093 | 11 340 | 609 |
| Expenditure: |  |  |  |  |  |
| Employees | 8 023 | 9 657 | 9 657 | 7 812 | 1 466 |
| Repairs and Maintenance |  |  |  |  |  |
| Other | 3 127 | 2 436 | 2 436 | 4 925 | (455) |
| Total Operational Expenditure | 11 150 | 12 093 | 12 093 | 12 737 | 1 011 |
| Net Operational Expenditure | 3 130 | 0 | 0 | (1 397) | (402) |
|  |  |  |  |  | T3.70.5 |

### 3.71	HUMAN RESOURCE SERVICES

INTRODUCTION TO HUMAN RESOURCE SERVICES

The purpose of Human Resources Services at the institution is cater for human resource development needs of the employees, remuneration and benefits of employees, labour relations and human resources information that relates to leave management and employee personal information.

The management set itself priorities to overhaul the services the institution provides to its internal clients, the key three amongst them were;

Purify leave management

Provide accurate inputs- information to payroll

Recruit people with required competencies

So far this division has made major strides in insuring that leave of employees is managed in accordance with Municipal Human Resources Policy Manual. Every week there is reconciliation of attendance registers, VIP register with completed leave forms; and follow-ups on employees who did not sign registers or completed leave forms. The principle of no work no pay is applied on employees who are found not to have followed proper procedure in absenting themselves from work.

The official providing information to employees in payroll on remuneration and benefits of employees work s closely with the payroll division in order to ensure that accurate information is forwarded to division before processing the salaries of councillors and employees. The inputs are compiled, checked, approved by different individuals in order to ensure that correct information is provided to payroll. Such information is forwarded to payroll on or before the 15th of each month in order to give officials in payroll an ample time to process the remuneration and benefits of both councillors and officials

The Human Resources Division advertises all vacant positions as required by the Human Resources Policy Manual and set competencies that are needed from the interested individuals. It is important to highlight that the Municipality appoints only incumbents who meets minimum competency requirements as placed on the advertisement.

T3.71.1

| Employees: Human Resource Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2015/2016 | 2016/2017 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 1 | 1 | 1 | 0 | 0% |
| 4 - 6 | 3 | 5 | 5 | 0 | 0% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 5 | 7 | 7 | 0 | 0% |
| T3.71.4 |  |  |  |  |  |

| Financial Performance 2016/2017: Corporate service |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2015/2016 | 2016/2017 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 19 401 | 16 198 | 16 198 | 15 914 | 284 |
| Expenditure: |  |  |  |  |  |
| Employees | 13 684 | 14 952 | 14 922 | 13 922 | 1 030 |
| Repairs and Maintenance | 298 | 110 | 254 | 90 | 146 |
| Other | 1 829 | 1 135 | 991 | 1 577 | (586) |
| Total Operational Expenditure | 15 797 | 16 198 | 16 198 | 15 589 | 608 |
| Net Operational Expenditure | 3 604 | 0 | 0 | 325 | (324) |
|  |  |  |  |  | T3.71.5 |

### 3.72	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

This component includes: Information and Communication Technology (ICT) services.

INTRODUCTION TO INFORMATION TECHNOLOGY (IT) SERVICES

The IT Unit is an integral part of Xhariep District Municipality and plays a vital role as an enabler of the institution. Our main aim as a unit is to ensure that the business needs of the municipality in relaion to IT are prioritised and that the IT Strategy is aligned to those needs.

The IT division wants to ensure that the municipality implements IT solutions that will help with the smooth operation of the municipality, by identifying gabs in the systems, processes, IT Infrastructure etc. to ensure proper solutions are implemented in response to the identified gaps.

The Municipality also want to ensure that the institution gets value for money for its investment in the IT

As the IT unit, the focus in the 2016/2017 financial year was to further improve on the IT Infrastructure to accommodate the implimemntation of the mSCOA project.

T3.72.1

| Employees: ICT Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2015/2016 | 2016/2017 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 1 | 1 | 1 | 0 | 0% |
| 4 - 6 | 1 | 1 | 1 | 0 | 0% |
| 7 - 9 | 0 | 0 | 0 | 0 | 0% |
| 10 - 12 | 0 | 0 | 0 | 0 | 0% |
| 13 - 15 | 0 | 0 | 0 | 0 | 0% |
| 16 - 18 | 0 | 0 | 0 | 0 | 0% |
| 19 - 20 | 0 | 0 | 0 | 0 | 0% |
| Total | 2 | 2 | 2 | 0 | 0% |
| T3.72.4 |  |  |  |  |  |

PERFORMANCE OF ICT SERVICES OVERALL

The IT Unit has achieved so many successes in the 2016/2017 Financial Year to bring the IT environment to a stable position. The IT Unit together with other Units successfully implemented the mSCOA project, with the Financial Informations Systems mostly changed to be compliant with the Treasury requirements. Documents are uploaded regularly and within acceptable time on the municipal Website. The environment is pretty much stable. The challenges where experienced with the Licenses that could not be purchased as budget was shifted to other projects and budget that was insufficient

T3.72.5

## COMPONENT K: ORGANISATIONAL PERFORMANCE SCORECARD

This component includes:  Annual Performance Scorecard Report for the current year.

TOP LAYER PERFORMANCE INFORMATION

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE | REAON FOR DEVIATION |  | CORRECTIVE MEASURE |  | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MUNICIPAL MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL 1 | To review and implement municipal employment Equity Plan by 30 June 2017 | MT&ID | Ensure the annual review and enforcement of the Employment Equity Plan | Reviewed Employment Equity Plan tabled before Local Labour Forum | 30-06-17 | o | (1) | The Employment Euity Plan was reviewed but could not be tabled before the LLf due to the non functionality of the LLF |  |  | Appointment of a new LLF Committee in the 2017/2018 finnacial year | 30-09-15 | 0 |  | (1) |
| TL 2 | To implement effective performance management system by 30 June 2017 | MT&ID | Cascading Individual performance management to lower level employees | Entering into performance agreements with the employer on or before 30 June 2017 | 30-06-17 | 0 | (1) | EPAS could not be cascaded down to lower level employees due to the vacancy of Senior Management |  |  | The municipality to appoint Senior Management in the 2017/2018 financial year to can implement the Employee Performance Appraissal System(EPAS) | 30-09-15 | 0 |  | (1) |
| TL3 | To create an efficient, effective and accountable administration | GGPP | Convene a Councillor and Senior Management strategic planning session for the IDP Review and budget process on or before 30 June 2017 | Strategic planning sessions held on or before 30 June 2017 | 1 | 0 | (1) | Strategic planning session could not be held due to budget constraints |  |  | The municipality to budget for the strategic planning session for the 2017/2018 financial year | 1 | 0 |  | (1) |
| TL4 | To improve financial viability of the municipality | GGPP | Engage stakeholders to fund the municipal budget before the end of the financial year 2016/17 | Progress report on stakeholders meetings to Management and Council | 1 | 0 | (1) | The municipality did engage with some stakeholders on the sourcing of funds to fund the budget of the municipality but with no success |  |  | The KPI to be reviewed in the 2017/2018 financial year | 2 | 0 |  | (2) |
| TL5 | To promote cultural and socio economic development of our community | GGPP | Providing support to Local Municipalities through Technical IGR engagements | No. of Technical IGR meetings held | 4 | 1 | (3) | IGR meetings could not sit as scheduled due to election campaigns in the 2016/2017 financial year |  |  | Development of IGR schedule for 2017/2018 and sit as planned | 4 | 4 |  | 0 |
| TL6 | To create an efficient, effective and accountable administration | GGPP | Compliance with all the processes, procedures, controls, policies and legislation | Unqualified Audit Opinion | 31- 12-16 | 1 | 0 | - |  |  | - | 31-12-15 | 1 |  | 0 |
| TL7 | To budget strategically, grow and diversify our revenue and ensure value for money services | MFV&M | Ensure compliance with Section 32 of the MFMA | Months without irregular, unauthorised, fruitless and wasteful expenditure | 12 | 0 | (12) | This is due to non adherence to policies and legislation and long overdue invoices due to budget constarints |  |  | Compliance with legislation regulating irregular, unauthorised, fruitless and wasteful expenditure | New KPI | - |  | - |
| TL8 | To provide open transparent corruption free governance | GGPP | Enhance the effectiveness of the Risk Management Committee | Implementation of the Risk Management Committee resolutions | 4 | 0 | (4) | This is due to the non functionality of the Risk Management Committee in the year under review |  |  | The municipality to appoint the Chief Risk Officer in the 2017/2018 financial year | 4 | 0 |  | (4) |
| TL9 | To provide open transparent corruption free governance | GGPP | Fraud and corruption awareness throughout the institution | No of awareness campaigns conducted | 1 | 0 | (1) | This is due to the vacancy of the Chief Risk Officer |  |  | The municipality to appoint the Chief Risk Officer in the 2017/2018 financial year | 1 | 0 |  | (1) |
| TL10 | To create an efficient, effective and accountable administration | GGPP | Overseeing the implementation of Council Resolutions on a quarterly basis | No of Quarterly Reports submitted to Council | 4 | 2 | (2) | The resolution register was only presented twice to Council |  |  | The resolution register will be presented quarterly to Council in the new financial year | 4 | 4 |  | 0 |
| TL11 | To create an efficient, effective and accountable administration | GGPP | Enhance the effectiveness of the Shared Audit and Performance Committee | Implementation of the Shared Audit and Performance Committee resolutions | 4 | 4 | 0 | - |  |  | - | 4 | 4 |  | 0 |
| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE | REAON FOR DEVIATION |  | CORRECTIVE MEASURE |  | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
|  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL12 | To improve financial viability of the municipality | MFV&M | Prepare and adopt a sustainable budget (with capital expenditure allocation) and financial plan as part of IDP to implement in 2017/18 financial year | Budget approved on or before 30 June 2017 | 30-06-17 | 1 | 0 | - | - |  |  | 31-06-16 | 1 |  | 0 |
| TL13 | To improve financial viability of the municipality | MFV&M | Prepare GRAP compliant AFS | AFS completed on or before 31 Aug 2016 | 31-08-16 | 1 | 0 | - | - |  |  | 31-08-15 | 1 |  | 0 |
| TL14 | To improve financial viability of the municipality | MFV&M | Oversee the review and implementation of internal financial management policies and credit control strategies: | Budget related policies reviewed and adopted by Council on or before 30 June 2017 | 30-06-17 | 1 | 0 | - | - |  |  | 30-06-16 | 1 |  | 0 |
| TL15 | To improve financial viability of the municipality | MFV&M | Review of journals prior capturing on the financial system( pastel) | Monthly review of journal entries | 12 | 12 | 0 | - | - |  |  | 12 | 12 |  | 0 |
| TL16 | To improve financial viability of the municipality | MFV&M | Ensure that the MSIG conditional operational grant (Finance allocation) is fully utilised by 30 June 2017 | % of MSIG conditional operational grant spent on a quarterly basis | 99% | 0 | (99%) | COGTA did not transfer the MSIG grant to the municipality in the year under review due to the fact that transfers of funds are no longer made directly to municipalities. | COGTA to communicate such information earlier to municipalities or before the adoption of municipal budgtes |  |  | 99% | 100% |  | 1% |
| TL17 | To improve financial viability of the municipality | MFV&M | Ensure that the FMG conditional operational grant is fully utilised | % of FMG conditional operational grant spent on a quarterly basis | 99% | 100% | 1% | - | - |  |  | 99% | 94% |  | (5%) |
| TL18 | To improve financial viability of the municipality | MFV&M | Ensure that capital expenditure (Finance) is in line with budget and timeframes (SA29) | % Capital budget spent quarterly | 95% | 0% | (95%) | The initial budgeted amount was moved to the office of the Municipal Manager for the purchasing of security equipment during the adjustment budget | KPI to be reviewed in 2017/2018 financial year |  |  | 95% | 0 |  | (95%) |
| TL19 | To improve financial viability of the municipality | GGPP | Engage stakeholders to fund the municipal budget | Progress reports on stakeholders meetings to Management and Council | 1 | 0 | (1) | The municipality did engage with some stakeholders on the sourcing of funds to fund the budget of the municipality but with no success | The KPI to be reviewed in the 2017/2018 financial year |  |  | 2 | 0 |  | (2) |
| TL20 | To create an efficient, effective and accountable administration | GGPP | Compliance with all the processes, procedures, controls, policies and legislation | Unqualified Audit Opinion | 31- 12- 16 | 1 | 0 | - | - |  |  | 31-12-15 | 1 |  | 0 |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE | REAON FOR DEVIATION |  | CORRECTIVE MEASURE | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | DIRECTOR: CORPORATE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL21 | To create an efficient, effective and accountable administration | MT&ID | Overseeing and enforcing the compliance of the HR policies | Implementation Plan of the HR Policies by 31 March 2017 | 31-03-17 | 0 | (1) | There was no proper oversight role played by the HOD in terms of the monitoring of the implementation of the HR Policies due to the vacancy of the Director: Corporate Services since 2015. | Filling of the vacancy of the Director: Corporate Services in the 2017/2018 financial year |  | 31-12-15 | 0 |  | (1) |
| TL22 | To prepare and implement municipal work place skills plan annually | MT&ID | Ensure timeous submission of the WSP to LGSETA | Submission of the WSP on or before 30 April 2017 to LGSETA | 30- 04- 17 | 1 | 0 | - | - |  | 30-04-16 | 1 |  | 0 |
| TL23 | To review and implement municipal employment equity plan annually | MT&ID | Ensure timeous submission of the EE Report by 01 October 2015 (Manually) or 30 January 2016(electronically) to Department of Labour | Submission of the EE Report on or before by 01 October 2016 (Manually) or 30 January 2017(electronically)to Department of Labour | 1 | 1 | 0 | - | - |  | 2 | 0 |  | (2) |
| TL24 | To create an efficient, effective and accountable administration | GGPP | Populate organogram and prioritise the filling of vacant critical top management layer positions | No of critical top management vacant positions filled by 30 June 2017 | 30-06-17 | 0 | (1) | Interviews are scheduled for July 2017 | Senior Management will resume duties in August 2017. |  | 30-09-15 | 0 |  | (1) |
| TL25 | To create an efficient, effective and accountable administration | GGPP | Ensure the review and implementation of the ICT Policies and Strategies | Implementation Plan of the ICT Policies and Strategies by 30 September 2016 | 30-09-16 | 0 | (1) | Not all municipal policies were workshoped to municipal employees | All ICT policies will be workshoped to all municipal employees and in the 2017/2018 financial year and an implementation plan will therefore be developed |  | 30-09-15 | 0 |  | (1) |
| TL26 | To improve financial viability of the municipality | GGPP | Engage stakeholders to fund the municipal budget | Progress reports on stakeholders meetings to Management and Council | 1 | 0 | (1) | The municipality did engage with some stakeholders on the sourcing of funds to fund the budget of the municipality but with no success | The KPI to be reviewed in the 2017/2018 financial year |  | 2 | 0 |  | (2) |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE | REAON FOR DEVIATION |  | CORRECTIVE MEASURE | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | DIRECTOR: PLANNING AND SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL27 | To coordinate and support provision of safe and proper burial spaces by our local municipalities | BSD | Ensure compliance of funeral parlours in accordance with regulations relating to funeral undertakers premises ( Gov No.237 of Feb 1985 | Progress reports regarding implementation of the regulation( Gov No.237 of Feb 1985) | 4 | 1 | (3) | Council prioritized compliance matters over any other reports hence the number of reports on regulations relating to funeral undertakers premises | Council to adhere to approved schedule of Council in order to consider all reports prepared for tabling in Council |  | 4 | 0 |  | (4) |
| TL28 | Facilitate provision of sufficient bulk water supply to all municipalities | BSD | Maintain existing and improve Blue drop standards | No of water networks for which blue drop awards are achieved (95%) | 95% | 0 | (95%) | Department of Water Affairs did not issue out reports of blue drop compliance for the year under review and the pervious year | KPI to be reviewed |  | 95% | 0 |  | (95%) |
| TL29 | Implement RRAMS and monitor use of labour intensive methods to create jobs | BSD | Fully utilise RAMMS conditional grant according to expenditure cash flow prediction by 30 June 2017 | % of RAMMS conditional capital grants spent | 95% | 70.8% | (24.2%) | This is due to late additional allocation of funds from National Treasury | - |  | 95% | 100% |  | 5% |
| TL30 | Implement EPWP and monitor use of labour intensive methods to create jobs | LED | Fully utilise EPWP conditional grant according to expenditure cash flow prediction by 30 June 2017 | % of EPWP conditional capital grants spent | 95% | 100% | 5% | - | - |  | 95% | 97.96% |  | 2.96% |
| TL31 | Facilitate provision of sufficient bulk water supply to all municipalities | BSD | Ensure compliance of both waste and drinking water quality in accordance with SANS 241 | Reports submitted to Council on both waste and drinking water quality in accordance with SANS 241 | 4 | 7 | 3 | - | - |  | 4 | Water 4 Waste 4 |  | Water 0 Waste 0 |
| TL32 | Facilitate provision of sustainable basic sanitation all households in the district | BSD | Oversee the implementation of the integrated waste management plan objectives | Development of the integrated waste management Implementation Plan | 2 | 0 | (2) | The integrated waste management plan could not be implemented in the year under review due to the unsatisfactory work done by the service provider in compilation of this document. | The integrated waste management plan to be reviewed for implementation in the 2017/2018 financial year |  | 4 | 0 |  | (4) |
| TL33 | Manage and prevent harm of the environment and ensure its sustainability | BSD | Oversee the review of the Integrated Environmental Management Plan | Approved Integrated Environmental Management Plan on or before 30 September 2016 | 30-09-16 | 0 | (1) | The municipality wrote a letter to DBSA requesting assistance in conducting an environmental assessment in order to develop an Integrated Environmental Management Plan due to lack of internal capacity and funds.To date the municipality has not yet received a response on the matter. | The HOD to make a follow up with DBSA regarding the request made in terms of the assistance in conducting an environmental assessment |  | 30-09-15 | 0 |  | (1) |
| TL34 | Create an environment for economic growth and job creation | LED | Stakeholder engagements to source funding for projects | Quarterly progress reports on stakeholders meetings to Management/ Council | 4 | 0 | (4) | The municipality did engage with some stakeholders on the sourcing of funds to fund the budget of the municipality but with no success | The KPI to be reviewed in the 2017/2018 financial year |  | 2 | 0 |  | (2) |
| TL35 | To promote cultural and socio economic development of our community | BSD | Ensure the land reform committee is established | Appointment of the land reform committee members on or before 30 June 2017 | 30-06-17 | 1 | 0 | - | - |  | 30-09-15 | 0 |  | (1) |
| TL36 | To contribute to the reduction of levels of poverty in the district | BSD | Oversee the development of food security programmes in the district | Quarterly reports submitted to Council on the implementation of the food security programme | 4 | 1 | (3) | Council prioritized compliance matters over any other reports hence the number of reports on the food security programme | Council to adhere to approved schedule of Council in order to consider all reports prepared for tabling in Council |  | 4 | 1 |  | (3) |
| TL37 | Create an environment for economic growth and job creation | LED | Ensure job creation through the municipality’s EPWP | Number of temporary jobs created (EPWP) | 190 | 156 | (34) | This is due to resignations and terminationsof EPWP Labourers during the financial year 2016/2017 | - |  | 174 | 189 |  | 15 |
| TL38 | To continuously prepare, adopt, effectively implement and annually review IDP | GGPP | Oversee the compilation of the Xhariep SDF | SDF developed and approved by Council on or before 30 September 2016 | 30-09-16 | 0 | (1) | The SDF could not be reviewed due to lack of internal capacity and a budget | The department of Rural development made a commitment to make a provision in their budget to assist the municipality in the review of the SDF in 2017/2018 financial year |  | 30-09-15 |  |  |  |

DEPARTMENTAL PERFORMANCE

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE | REAON FOR DEVIATION |  | CORRECTIVE MEASURE | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Municipal Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D1 | To provide open transparent corruption free governance | MT&ID | Implementation anti-fraud, anti-corruption and risk prevention initiatives on or before 30 June 2017 | No of initiatives implemented to create awareness amongst Councillors and Staff | 1 | 0 | (1) | This is due to the vacancy of the Chief Risk Officer | The Municipality to fill the vacancy of the Chief Risk Officer in the 2017/2018 financial year |  | 1 | 0 |  | (1) |
| D2 | To provide open transparent corruption free governance | MT&ID | Advise Management and report to Risk Management Committee and SAPC on Risk Management processes by 30 June 2017 | Quarterly reports submitted to Risk Management Committee and SAPC on Risk Management processes | 4 | 0 | (4) | This is due to the vacancy of the Chief Risk Officer | The Municipality to fill the vacancy of the Chief Risk Officer in the 2017/2018 financial year |  | 4 | 0 |  | (4) |
| D3 | To create an efficient, effective and accountable administration | MT&ID | Annual Risk assessment and Fraud Risk assessment conducted on 31 July 2016 | Final Risk assessment report and Risk register | 1 | 0 | (1) | This is due to the vacancy of the Chief Risk Officer | The Municipality to fill the vacancy of the Chief Risk Officer in the 2017/2018 financial year |  | 1 | 0 |  | (1) |
| D4 | To create an efficient, effective and accountable administration | MT&ID | Quarterly progress reports on Risk Implementation Plan | No of progress reports to Management | 4 | 0 | (4) | This is due to the vacancy of the Chief Risk Officer | The Municipality to fill the vacancy of the Chief Risk Officer in the 2017/2018 financial year |  | 4 | 0 |  | (4) |
| D5 | To create an efficient, effective and accountable administration | MT&ID | Review the antifraud and corruption policy by 30 June 2017 | Approved antifraud and corruption policy | 1 | 0 | (1) | This is due to the vacancy of the Chief Risk Officer | The Municipality to fill the vacancy of the Chief Risk Officer in the 2017/2018 financial year |  | 1 | 0 |  | (1) |
| D6 | To create an efficient, effective and accountable administration | MT&ID | Advise the accounting officer and report to the audit committee on the implementation of the internal audit plan and related matters (MFMA, Act 56 of 2003, Section 165(2)(b). | No of quarterly reports prepared for Audit Committee | 4 | 3 | (1) | The IA Plan was only approved on the second quarter hence the late implementation of the plan | The Audit Committee to approve the IA Plan at the beginning of each financial year |  | 4 | 4 |  | 0 |
| D7 | To create an efficient, effective and accountable administration | MT&ID | Functional Internal Audit Unit (MFMA 62(1)) | Risk based audit plan approved by Audit Committee by 31 August 2016 | 1 | 1 | 0 | - | - |  | 1 | 1 |  | 0 |
| D8 | To implement effective performance management system by 30 June 2017 | MT&ID | Compile draft Annual Report for submission to Council by 31 January 2017 | Draft Annual Report approved by Council | 1 | 1 | 0 | - | - |  | 1 | 1 |  | 0 |
| D9 | To implement effective performance management system by 30 June 2017 | MT&ID | Compile Oversight Report on Annual Report and submit to Council by 31 March 2017 (MFMA 129(1) and MSA 46(2) | Oversight Report adopted by Council | 1 | 1 | 0 | - | - |  | 1 | 1 |  | 0 |
| D10 | To implement effective performance management system by 30 June 2017 | MT&ID | Compile the Mid- Year budget and Performance Report by 25 January 2017 (MFMA S72) | Mid-year report submissions (Mayor, Provincial and National Treasury) by 25 January 2017 | 1 | 1 | 0 | - | - |  | 1 | 1 |  | 0 |
| D11 | To implement effective performance management system by 30 June 2017 | GGPP | Implement Council Resolutions within prescribed timeframe stipulated on system | % resolutions implemented within timeframe | 95% | 75.65% | (19.35%) | This is due to resolutions that are still in progress | Make a followup on all oustanding resolutions and report progress thereof |  | 95% | 63% |  | (32%) |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT |  | ANNUAL TARGET | ACTUAL | VARIANCE |  | REASON FOR DEVIATION | CORRECTIVE MEASURE |  | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Financial Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D12 | To improve financial viability of the municipality | MFV&M | Production of annual Audit file by mid August | No of Audit files produced | 1 |  | 1 |  | 0 | - |  | - | 1 | 1 | 0 |
| D13 | To improve financial viability of the municipality | MFV&M | Closing of all municipal financial accounts at the end of each month i.t.o sec 65 of the MFMA | No of monthly reports | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D14 | To improve financial viability of the municipality | MFV&M | No of creditors reconciliations done monthly (30 days) | No of creditors reconciliation reports submitted | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D15 | To improve financial viability of the municipality | MFV&M | Financial Viability: Cost coverage (Reg 796) | Cost coverage ((Available cash+ investments)/ Monthly fixed operating expenditure (SA8) | >1 |  | 0.0033 |  | (0.9967) | Available cash and investement is less than the monthly operating expenditure due to R14.2 million cut from financial assistance |  | Improve on the cash management of the municipality | >1 | 0.17 | (0.83) |
| D16 | To improve financial viability of the municipality | MFV&M | Financial Viability: Debt coverage (Reg 796) | Debt coverage (Total operating revenue-operating grants received)/debt service payments due within the year) (SA8) | >1 |  | 0.2802 |  | (0.7198) | Total operating revenue excluding grants contributes only to less than 5% of the revenue total |  | Municipality to engage COGTA and Treasury in finding other sources of funding | >1 | (46.55) | (45.55) |
| D17 | To improve financial viability of the municipality | MFV&M | Monthly notification of awards over R 100 000 | List of awards | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D18 | To improve financial viability of the municipality | MFV&M | Effective management of payroll by providing the section 66 payroll report on a monthly basis | Monthly reports to management i.t.o sec 66 of the MFMA | 12 |  | 12 |  | 0 | - |  | - | 12 | 1`2 | 0 |
| D19 | To improve financial viability of the municipality | MFV&M | Ensure the submission of IRP5's | IRP5's submitted not later than 30 May 2017 to SARS | 1 |  | 1 |  | 0 | - |  | - | 1 | 1 | 0 |
| D20 | To improve financial viability of the municipality | MFV&M | Monthly salary reconciliations | No of reconciliations done | 12 |  | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D21 | To improve financial viability of the municipality | GGPP | Implement Council Resolutions within prescribed timeframe stipulated on system | % resolutions implemented within timeframe | 95% |  | 80.75% |  | (14.25%) | This is due to resolutions that are still in progress |  | Make a followup on all oustanding resolutions and report progress thereof | 95% | 77% | (18%) |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT | ANNUAL TARGET | ACTUAL | VARIANCE |  | REASON FOR DEVIATION | CORRECTIVE MEASURE | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Directorate: Corporate Services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D22 | To implement effective performance management system by June 2017 | MT&ID | Draw quarterly resolution execution report for all directorates | No. of reports | 4 | 7 |  | 3 | - | - | 4 | 4 |  | 0 |
| D23 | To create an efficient, effective and accountable administration | MT&ID | Implement Council resolutions within required timeframe | % of Council resolutions implementation within required timeframe | 95% | 81.43% |  | (13.57%) | This is due to resolutions that are still in progress | Make a followup on all oustanding resolutions and report progress thereof | 95% | 71.25% |  | (23.75%) |
| D24 | To create an efficient, effective and accountable administration | MT&ID | Monitoring Council resolutions to ensure implementation | Resolution register submitted to Council on a quarterly basis | 4 | 2 |  | (2) | The resolution register was only presented twice to Council | The resolution register will be presented quarterly to Council in the new financial year | New KPI | - |  | - |
| D25 | To create an efficient, effective and accountable administration | MT&ID | Ensure a sound system of records Management on a monthly basis | Inspection of registry unit to ensure all records are kept in a safe custody and sound records management practices are followed | 12 | 12 |  | 0 | - | - | New KPI | - |  | - |
| D26 | To build capacity of the organisation to effectively deliver on its Powers and Functions assignments | MT&ID | Training and development of personnel | Total number of training courses attended by 31 December 2016 | 1( MFMP) | 1( MFMP) |  | 0 | - | - | 1( MFMP) | 1( MFMP) |  | 0 |
| D27 | To build capacity of the organisation to effectively deliver on its Powers and Functions assignments | MT&ID | Training and development of personnel | % of courses resulting in competency certificates by 30 June 2017. | 95% | 95% |  | 0 | - | - | 95% | 95% |  | 0 |
| D28 | To build capacity of the organisation to effectively deliver on its Powers and Functions assignments | MT&ID | Training and development of personnel | Total number of employees attending training courses by 30 June 2017 | 10 | 11 |  | 1 | - | - | 11 | 11 |  | 0 |
| D29 | To build capacity of the organisation to effectively deliver on its Powers and Functions assignments | MT&ID | Training and development of personnel | Total number of skills development forum meetings held by 30 June 2017 | 2 | 2 |  | 0 | - | - | 2 | 2 |  | 0 |
| D30 | To prepare and implement municipal work place skills plan by June 2017 | MT&ID | Develop the WSP and implement in line with legislation and monitor outcomes then report to national as part of PMS | WSP approved by the LLF and submitted to LGSETA on or before 30 April 2017 | 1 | 1 |  | 0 | - | - | 1 | 1 |  | 0 |
| D31 | To review and implement municipal employment equity plan by June 2017 | MT&ID | Develop the EEP and implement in line with legislation and monitor outcomes then report to national as part of PMS | % of employees from the designated groups | 95% | 94.5% |  | (0,5%) | This is due to resignations | The municipality to fill those vacant positions | 95% | 98% |  | 3% |
| D32 | To create an efficient, effective and accountable administration | MT&ID | Improve labour relations | No of LLF meetings held as planned by 30 June 2017 | 8 | 1 |  | (7) | The LLF was not functional in the financial year under review | Management to see to it that the LLF sits as planned in the 2017/2018 financial year | 12 | 2 |  | (10) |
| D33 | To create an efficient, effective and accountable administration | GGPP | Public Participation Plan in place | Review of the Public Participation Plan/Strategy on or before 30 June 2017 | 1 | 0 |  | (1) | The Public Participation strategy could not be reviewed in the 2016/2017 financial year due to the vacancy of the Public Participation Officer | The strategy will be reviewed in the 2017/2018 financial year as soon as the Municipality fuills the vacancy of the Public Participation Officer | 1 | 1 |  | 0 |

| REF | IDP OBJECTIVE | KPA | KPI | UNIT OF MEASUREMENT |  | ANNUAL TARGET |  | ACTUAL VARIANCE |  | REASON FOR DEVIATION | CORRECTIVE MEASURE |  | PRIOR TARGET | PRIOR ACTUAL | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Planning and Social Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D34 | Implement EPWP and monitor use of labour intensive methods to create jobs | LED | To report on the EPWP progress, grant, staff and wages paid |  | No of monthly reports submitted to the MM/ Council | 12 | 12 |  | 0 | - |  | - | 12 | 12 | 0 |
| D35 | Implement EPWP and monitor use of labour intensive methods to create jobs | LED | To Review the District EPWP Policy by 30/06/2017 |  | District EPWP Policy reviewed and approved by Council on or before 30 June 2017 | 1 | 0 |  | (1) | The EPWP Policy is reviewed only if it necessary in a five year period. It could not be reviewed in the year under review as it was not necessary to do so. |  | KPI to be reviewed | 1 | 1 | 0 |
| D36 | Implement EPWP and monitor use of labour intensive methods to create jobs | LED | To report on the EPWP progress |  | No. of EPWP steering committee meetings held quarterly | 4 | 4 |  | 0 | - |  | - | 4 | 4 | 0 |
| D37 | Implement EPWP and monitor use of labour intensive methods to create jobs | LED | 100 % expenditure on the EPWP Grant |  | 100% Expenditure by end of June 2017 | 100% | 100% |  | 0 | - |  | - | 100% | 97.96% | (2.04%) |
| D38 | To create an efficient, effective and accountable administration | GGPP | Compile IDP / Budget (Time schedule of key deadlines (Process Plan) by 30 August 2016 (MSA 28 / MFMA 21) |  | Approved IDP Framework and Process Plan on or before 31 Aug 2016 | 1 | 1 |  | 0 | - |  | - | 1 | 1 | 0 |
| D39 | To continuously prepare, adopt, effectively implement and annually review IDP | GGPP | Compile Draft IDP, Review and submit to Council by 31 March 2017 (MSA 34) |  | Draft IDP approved on or before 31 March 2017 | 1 | 1 |  | 0 | - |  | - | 1 | 1 | 0 |
| D40 | To continuously prepare, adopt, effectively implement and annually review IDP | GGPP | Compile final IDP and submit to Council 31 May 2017 (MSA 34) |  | Final IDP approved on or before 31 May 2017 | 1 | 1 |  | - | - |  | - | 1 | 1 | 0 |
| D41 | To improve economic growth of the District | LED | Submit Quarterly reports on the implementation of LED |  | Quarterly reports on the implemntation of LED submitted to Management/Council | 4 | 4 |  | 0 | - |  | - | New KPI | - | - |
| D42 | To contribute to Tourism Development and Marketing | LED | Tourism development |  | No. of tourism awareness campaigns conducted | 2 | 2 |  | 0 | - |  | - | 2 | 2 | 0 |
| D43 | To improve economic growth of the District | LED | Quarterly District LED Forums |  | No. of Quarterly District LED Forums held | 4 | 2 |  | (2) | All district Forums were put on hold by the Office of the Mayor |  | Forums will sit as planned in the 2017/2018 financial year | 4 | 4 | 0 |
| D44 | To contribute to the reduction of levels of poverty in the district | LED | LED Projects |  | No. of LED projects supported | 2 | 2 |  | 0 | - |  | - | 2 | 2 | 0 |
| D45 | To manage and prevent harm of the environment and ensure its sustainability | BSD | Improve service delivery to communities |  | No. of person attending Health Education programmes/projects | 1200 | 1731 |  | 531 | - |  | - | 1000 | 2214 | 1214 |
| D46 | Facilitate provision of sufficient bulk water supply to all municipalities | BSD | Improve service delivery to communities |  | No of quarterly water quality reports submitted to Council | 4 | 5 |  | 1 | - |  | - | 4 | 4 | 0 |
| D47 | Facilitate provision of sufficient bulk water supply to all municipalities | BSD | Improve service delivery to communities |  | No of water quality samples collected per local municipality | Mohokare 72 | 81 |  | 9 | - |  | - | 72 | 87 | 15 |
|  |  |  |  |  |  | Letsemeng 108 | 108 |  | 0 | - |  | - | 108 | 116 | 8 |
|  |  |  |  |  |  | Kopanong 216 | 243 |  | 27 | - |  | - | 218 | 295 | 77 |
| D48 | Facilitate provision of sustainable basic sanitation all households in the district | BSD | Improve service delivery to communities |  | No of quarterly sanitation quality reports submitted to Management/ Council | 4 | 4 |  | 0 | - |  | - | 4 | 4 | 1 |
| D49 | Facilitate provision of sustainable basic sanitation all households in the district | BSD | Improve service delivery to communities |  | No of quarterly waste water samples taken per local municipality | Mohokare 12 | 10 |  | 2 | - |  | - | 12 | 10 | (2) |
|  |  |  |  |  |  | Kopanong 16 | 11 |  | (5) | Waste Water treatment Plant in Kopanong(Gariepdam) is non operational) |  | Waste water samples will be taken again when the treatment plant is functional | 8 | 6 | (2) |
|  |  |  |  |  |  | Letsemeng 8 | 8 |  | 0 | - |  | - | 16 | 7 | (9) |
| D50 | Facilitate provision of quality milk supply to all municipalitIies | BSD | Improve service delivery to communities |  | No of milk samples collected | 8 | 10 |  | 2 | - |  | - | New KPI | - | - |
| D51 | To manage and prevent harm of the environment and ensure its sustainability | BSD | Improve service delivery to communities |  | No of Environmental Health awareness | 15 | 22 |  | 7 | - |  | - | 15 | 18 | 3 |
| D52 | To implement effective performance management system by June 2017 | GGPP | Implement Council Resolutions within prescribed timeframe stipulated on system |  | % resolutions implemented within timeframe | 95% | 62.16% |  | (32.84%) | This is due to resolutions that are still in progress |  | Make a followup on all oustanding resolutions and report progress thereof | 95% | 77 | (18) |
| D53 | To manage and prevent occurrence loss of lives due to disasters | BSD | To ensure access to services delivery across the Municipal area in order to improve the livelihood of communities |  | No of municipal disaster management advisory forum meetings held (section 51 of the Disaster Management Act 2002) | 4 | 1 |  | (3) | All district Forums were put on hold by the Office of the Mayor |  | Forums will sit as planned in the 2017/2018 financial year | 4 | 4 | 0 |
| D54 | To manage and prevent occurrence loss of lives due to disasters | BSD | To ensure access to services delivery across the Municipal area in order to improve the livelihood of communities |  | No of disaster management progress reports submitted to Council | 4 | 2 |  | (2) | Disaster Management reports could not be tabled as planed due to Council prioritizing as to which reports needs to be presented to Coucil |  | Reports will be compiled and presented to Council as planned in the new financial year | 4 | 3 | (1) |
| D55 | To manage and prevent occurrence loss of lives due to disasters | BSD | To ensure access to services delivery across the Municipal area in order to improve the livelihood of communities |  | No of Disaster Management awareness sessions held in the District | 2 | 2 |  | 0 | - |  | - | 2 | 1 | (1) |

The following abbreviations are used in the service delivery targets and performance indicators:

KPA 	-	Key Performance Area

KPI	-	Key Performance Indicator

GGPP	-	Good Governance and Public Participation

MFVM	-	Municipal Financial Viability and Management

MTID	-	Municipal Transformation and Institutional Development

LED	-	Local Economic Development

BSD	-	Basic Service Delivery

MFMA	-	Municipal Finance Management Act 56 of 2003

MSA	-	Municipal Systems Act 32 of 2000

EEA	-	Employment Equity Act 55 of 1998

SDA	-	Skills Development Act 97 of 1998

MPPR	-	Local Government: Municipal Planning and Performance Management Regulations, 2001

MPR	-	Local Government: Municipal Performance Regulations for Municipal Managers and Managers Directly Accountable To

Municipal Managers, 2006

# CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE

# (PERFORMANCE REPORT PART II)

INTRODUCTION

The Municipality is constituted of four departments, namely: the Office of the Municipal Manager, Corporate Services, Planning and Social Development and Budget and Treasury. The Office of the Municipal Manager comprises of four divisions i.e. Internal Audit, Risk Management, Performance Management and Disaster Management. The Department of Corporate Services consists of four divisions, i.e. Administration, Human Resources, Information Technology and Labour Relations. The Department of Planning and Social Development is composed of four divisions, namely Local Economic Development, Integrated Development Planning, Municipal Health Services and Expanded Public Works Programme. The Budget and Treasury Office comprises of four divisions namely: Expenditure and Payroll, Supply Chain Management, Budget and Assets and Reporting and Compliance.

T4.0.1

## COMPONENT A: INTRODUCTION TO THE MUNICIPAL PERSONNEL

### 4.1	EMPLOYEE TOTALS, TURNOVER AND VACANCIES

| Vacancy Rate: 2016/2017 |  |  |  |
| --- | --- | --- | --- |
| Designations | *Total Approved Posts | *Vacancies (Total time that vacancies exist using fulltime equivalents) | *Vacancies (as a proportion of total posts in each category) |
|  | No. | No. | % |
| Municipal Manager | 1 | 0 | 0% |
| CFO | 1 | 1 | 100% |
| Other S57 Managers (excluding Finance Posts) | 2 | 1 | 50% |
| Other S57 Managers (Finance posts) | 0 | 0 | 0% |
| Police officers | - | - | 0% |
| Fire fighters | - | - | 0% |
| Senior management: Levels 13-15 (excluding Finance Posts) | - | - | 0% |
| Senior management: Levels 13-15 (Finance posts) | - | - | 0% |
| Highly skilled supervision: levels 9-12 (excluding Finance posts) | - | - | 0% |
| Highly skilled supervision: levels 9-12 (Finance posts) | - | - | 0% |
| Total | 4 | 2 | 50% |
|  |  |  | T 4.1.2 |

| Turn-over Rate |  |  |  |
| --- | --- | --- | --- |
| Details | Total Appointments as of beginning of Financial Year | Terminations during the Financial Year | Turn-over Rate* |
|  | No. | No. |  |
| 2014/2015 | 22 | 19 | 1.1% |
| 2015/2016 | 7 | 6 | 1.04% |
| 2016/2017 | 11 | 9 | 1.22% |
|  |  |  | T 4.1.3 |

COMMENT ON VACANCIES AND TURNOVER

The low turnover is an indicatation of Xhariep District Municipality`s employees who have a positive working relationship with their direct supervisors and co-workers hence they are likely to stay at their jobs. Another cause of low turnover is having room for for advancement so employees feel like they can move up in their careers if they stay at the municipality. Poor economic conditions can also contribute to low turnover because employees fear not being able to find other work.

T4.1.4

## COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE

INTRODUCTION TO MUNICIPAL WORKFORCE MANAGEMENT

The Municipality has put proper municipal workforce management systems and procedures in place in order to entrench transparent personnel administration. A Human Resources Policy is in place. Furthermore, the Municipality has an Employment Equity Plan which is used to guide the Municipality on how to implement its recruitment strategy. An Employment Equity Report which shows whether the municipality has recruited employees in accordance with its Employment Equity Plan is then compiled and submitted to the Department of Labour on annual basis.

Every year before the end of June, the Municipality conducts skill audit for each employee with the intention to identify skill gaps in the institution. The Skills Report is then submitted to the Local Government Sector Education and Training Authority together with the Works Place Skills Plan (WSP). The Officials are then sent to trainings based on the WSP.

The Municipality has other numerous policies that governs the activities that are taking place within the institution, namely, Records Management Policy, Fraud and Corruption Prevention Policy, Risk Management Policy, Delegation System Policy, Disaster Management Policy, Audit Charter, Performance Management Framework, Integrated Development Framework and budget related policies etc. These policies and procedures are meant to regulate the activities undertaken by the employees of the Municipality.

T4.2.0

### 4.2	POLICIES

| HR Policies and Plans |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Name of Policy | Completed | Reviewed | Date adopted by council or comment on failure to adopt |
|  |  | % | % |  |
| 1 | Affirmative Action | 100% | 100% | 28 August 2015 |
| 2 | Attraction and Retention | 100% | 100% | 28 August 2015 |
| 3 | Code of Conduct for employees |  |  | 28 August 2015 |
| 4 | Delegations, Authorisation & Responsibility | 100% | 100% | 28 August 2015 |
| 5 | Disciplinary Code and Procedures |  |  | 28 August 2015 |
| 6 | Essential Services | 100% | 100% | 28 August 2015 |
| 7 | Employee Assistance / Wellness |  |  | 28 August 2015 |
| 8 | Employment Equity | 100% | 100% | 28 August 2015 |
| 9 | Exit Management |  |  | 28 August 2015 |
| 10 | Grievance Procedures | 100% | 100% | 28 August 2015 |
| 11 | HIV/Aids |  |  | 28 August 2015 |
| 12 | Human Resource and Development | 100% | 100% | 28 August 2015 |
| 13 | Information Technology |  |  | 28 August 2015 |
| 14 | Job Evaluation | 100% | 100% | 28 August 2015 |
| 15 | Leave |  |  | 28 August 2015 |
| 16 | Occupational Health and Safety | 100% | 100% | 28 August 2015 |
| 17 | Official Housing |  |  | 28 August 2015 |
| 18 | Official Journeys | 100% | 100% | 28 August 2015 |
| 19 | Official transport to attend Funerals | 100% | 100% | 28 August 2015 |
| 20 | Official Working Hours and Overtime |  |  | 28 August 2015 |
| 21 | Organisational Rights | 100% | 100% | 28 August 2015 |
| 22 | Payroll Deductions |  |  | 28 August 2015 |
| 23 | Performance Management and Development | 100% | 100% | 28 August 2015 |
| 24 | Recruitment, Selection and Appointments |  |  | 28 August 2015 |
| 25 | Remuneration Scales and Allowances | 100% | 100% | 28 August 2015 |
| 26 | Resettlement |  |  | 28 August 2015 |
| 27 | Sexual Harassment | 100% | 100% | 28 August 2015 |
| 28 | Skills Development |  |  | 28 August 2015 |
| 29 | Smoking |  |  | 28 August 2015 |
| 30 | Special Skills | 100% | 100% | 28 August 2015 |
| 31 | Work Organisation |  |  | 28 August 2015 |
| 32 | Uniforms and Protective Clothing | 100% | 100% | 28 August 2015 |
| 33 | Other: |  |  |  |
| Use name of local policies if different from above and at any other HR policies not listed. |  |  |  | T 4.2.1 |

COMMENT ON WORKFORCE POLICY DEVELOPMENT:

All necessary policies that enable the Municipality to conduct its business in a fair and transparent manner has been developed and submitted before Council for adoption.

T4.2.1.1

### 4.3	INJURIES, SICKNESS AND SUSPENSIONS

| Number and Cost of Injuries on Duty |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Type of injury | Injury Leave Taken | Employees using injury leave | Proportion employees using sick leave | Average Injury Leave per employee | Total Estimated Cost |
|  | Days | No. | % | Days | R'000 |
| Required basic medical attention only | 0 | 0 | 0 | 0 | 0 |
| Temporary total disablement | 0 | 0 | 0 | 0 | 0 |
| Permanent disablement | 0 | 0 | 0 | 0 | 0 |
| Fatal | 0 | 0 | 0 | 0 | 0 |
| Total |  |  |  |  |  |
|  |  |  |  |  | T 4.3.1 |

| Number of days and Cost of Sick Leave (excluding injuries on duty) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Salary band | Total sick leave | Proportion of sick leave without medical certification | Employees using sick leave | Total employees in post* | *Average sick leave per Employees | Estimated cost |
|  | Days | % | No. | No. | Days | R' 000 |
| Lower skilled (Levels 1-2) | 43 | 0 | 5 | 5 | 8.6 | 18786 |
| Skilled (Levels 3-5) | 126 | 0 | 7 | 7 | 18 | 63758 |
| Highly skilled production (levels 6-8) | 199 | 0 | 16 | 16 | 12.4 | 148932 |
| Highly skilled supervision (levels 9-12) | 375 | 0 | 26 | 26 | 14.4 | 444149 |
| Senior management (Levels 13-15) | 158 | 0 | 18 | 18 | 9.2 | 271216 |
| MM and S57 | 0 | 0 | 3 | 3 | 0 | 0 |
| Total | 901 | 0 | 75 | 75 | 62.6 | 946841 |
|  |  |  |  |  |  | T4.3.2 |

| Number and Period of Suspensions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Position | Nature of Alleged Misconduct | Date of Suspension | Details of Disciplinary Action taken or Status of Case and Reasons why not Finalised | Date Finalised |
| Manager: Communication | Insolence and Intimidation | 03 November 2016 | Disciplinary Case was withdrawn because of procedural matters | 28 July 2017 |
|  |  |  |  | T4.3.5 |

## COMPONENT C: CAPACITATING THE MUNICIPAL WORKFORCE

INTRODUCTION TO WORKFORCE CAPACITY DEVELOPMENT

Every year before the end of June, the Municipality conduct skill audit for employees with the intention to identify skills gaps in the institution. The Skills Report is then submitted to the Local Government Sector Education and Training Authority together with the Works Place Skills Plan (WSP). The Officials are then sent to trainings based on the WSP.

T4.5.0

### 4.5	SKILLS DEVELOPMENT AND TRAINING

| Skills Matrix |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Management level | Gender | Employees in post as at 30 June 2016/2017 | Number of skilled employees required and actual as at 30 June 2016/2017 |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Learnerships |  |  | Skills programmes & other short courses |  |  | Other forms of training |  |  | Total |  |  |
|  |  | No. | Actual: End of 2015/2016 | Actual: End of 2016/2017 | Target | Actual: End of 2015/2016 | Actual: End of 2016/2017 | Target | Actual: End of 2015/2016 | Actual: End of 2016/2017 | Target | Actual: End of 2015/2016 | Actual: End of 2016/2017 | Target |
| MM and s57 | Female | 0 | 0 |  | - |  | - | - | - | - | - | - | - | - |
|  | Male | 2 | 2 | 2 | - | - | - | - | - | - | - | - | - | - |
| Councillors, senior officials and managers | Female | 15 | 4 | 4 | - | - | - | - | - | - | - | - | - | - |
|  | Male | 16 | 6 | 6 | - | - | - | - | - | - | - | - | - | - |
| Technicians and associate professionals* | Female | - | - | - | - | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - | - | - | - | - |
| Professionals | Female | 20 | 7 | 7 | - | 4 | - | - | - | - | - | - | - | - |
|  | Male | 7 | 3 |  | - | 1 | - | - | - | - | - | - | - | - |
| Sub total | Female | 35 | 11 | 11 | - |  | - | - | - | - | - | - | - | - |
|  | Male | 24 | 11 | 11 | - |  | - | - | - | - | - | - | - | - |
| Total |  | 119 | 44 | 41 |  | 5 |  |  |  |  |  |  |  |  |
| *Registered with professional Associate Body e.g CA (SA) |  |  |  |  |  |  |  |  |  |  |  |  |  | T4.5.1 |

| Financial Competency Development: Progress Report* |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | A. Total number of officials employed by municipality (Regulation 14(4)(a) and (c)) | B. Total number of officials employed by municipal entities (Regulation 14(4)(a) and (c) | Consolidated: Total of A and B | Consolidated: Competency assessments completed for A and B (Regulation 14(4)(b) and (d)) | Consolidated: Total number of officials whose performance agreements comply with Regulation 16 (Regulation 14(4)(f)) | Consolidated: Total number of officials that meet prescribed competency levels (Regulation 14(4)(e)) |
| Financial Officials |  |  |  |  |  |  |
| Accounting officer | 1 | 0 | 1 | 0 | 1 | 0 |
| Chief financial officer | 0 | 0 | 0 | 0 | 0 | 0 |
| Senior managers | 1 | 0 | 1 | 0 | 1 | 0 |
| Any other financial officials | 20 | 0 | 20 | 0 | 0 | 0 |
| Supply Chain Management Officials | 2 | 0 | 2 | 0 | 0 | 0 |
| Heads of supply chain management units | 1 | 0 | 1 | 0 | 0 | 0 |
| Supply chain management senior managers | 0 | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 25 | 0 | 0 | 0 | 0 | 0 |
| * This is a statutory report under the National Treasury: Local Government: MFMA Competency Regulations (June 2007) |  |  |  |  |  | T4.5.2 |

| Skills Development Expenditure |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |  |  |  |  |  |
| Management level | Gender | Employees as at the beginning of the financial year | Original Budget and Actual Expenditure on skills development 2016/2017 |  |  |  |  |  |  |  |
|  |  |  | Learnerships |  | Skills programmes & other short courses |  | Other forms of training |  | Total |  |
|  |  | No. | Original Budget | Actual | Original Budget | Actual | Original Budget | Actual | Original Budget | Actual |
| MM and S57 | Female |  |  |  |  |  |  |  |  |  |
|  | Male | 2 | LGSETA |  | - | - | - | - | - | - |
| Legislators, senior officials and managers | Female | 4 | LGSETA |  | - | - | - | - | - | - |
|  | Male | 6 | LGSETA |  | - | - | - | - | - | - |
| Professionals | Female | 7 | 0 | 0 | - | - | - | - | - | - |
|  | Male | 3 | 0 | 0 | - | - | - | - | - | - |
| Technicians and associate professionals | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Clerks | Female | 11 | 0 | 0 | - | - | - | - | - | - |
|  | Male | 11 | 0 | 0 | - | - | - | - | - | - |
| Service and sales workers | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Plant and machine operators and assemblers | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Elementary occupations | Female | - | - | - | - | - | - | - | - | - |
|  | Male | - | - | - | - | - | - | - | - | - |
| Sub total | Female | 16 | 0 | 0 | - | - | - | - | - | - |
|  | Male | 15 | 0 | 0 | - | - | - | - | - | - |
| Total |  | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| *% and *R value of municipal salaries (original budget) allocated for workplace skills plan. |  |  |  |  |  |  |  |  | %* | *R |
|  |  |  |  |  |  |  |  |  |  | T4.5.3 |

## COMPONENT D: MANAGING THE WORKFORCE EXPENDITURE

INTRODUCTION TO WORKFORCE EXPENDITURE

Before the beginning of the next financial year the Municipality makes necessary estimates for the workforce expenditure. The Municipality then filled only vacant positions that are budgeted for. The Municipality strives all times to appoint only suitably qualified employees for the vacant posts.

T4.6.0

# CHAPTER 5 – FINANCIAL PERFORMANCE

### 5.3	ASSET MANAGEMENT

INTRODUCTION TO ASSET MANAGEMENT

The asset management policy was drafted within the prescripts of the applicable legislations. Asset verifications are done quarterly to ensure that assets are safeguarded properly. Stock counts are performed monthly by the asset management officials and at year-end. In terms of key delegations, the Accounting Officer is the principal custodian who should ensure that the said policy is scrupulously applied and adhered to. The Chief Financial Officer is the assets registrar. The key elements of the asset management policy are classification, recognition, identification, write-off, depreciation, capitalization criteria, amendment of useful lives, and maintenance of assets.

T5.3.1

| Repairs and Maintenance Expenditure: 2016/2017 |  |  |  |  |
| --- | --- | --- | --- | --- |
| R' 000 |  |  |  |  |
|  | Original Budget | Adjustment Budget | Actual | Budget variance |
| Repairs and Maintenance Expenditure | 110 | 120 | 112 | 8 |
|  |  |  |  | T 5.3.4 |

## COMPONENT D: OTHER FINANCIAL MATTERS

### 5.12	SUPPLY CHAIN MANAGEMENT

SUPPLY CHAIN MANAGEMENT

As far as the processes are concerned, a MEMO for DEMAND and ACQUISITION has been developed by the municipality to manage, control and monitor procurement of goods and services. The MEMO is signed by the responsible manager to confirm the need of the service or product, the manager for Budget and Reporting Unit confirms the budget availability, relevant HOD recommends as well as the CFO and the Accounting Officer/Municipal Manager or a Senior Manager designated to act in the capacity of the Municipal Manager, finally approves the MEMO for DEMAND and ACQUISITION. During 2016/2017 financial year, Supply Chain Management Policy of the Municipality  was adopted by council on the 7th of July 2017 for implementation in the 2017/2018 financial year. The municipality also uses the Procurement Procedure Manual to help it in achieving its policy objectives.

T5.12.1

### 5.13	GRAP COMPLIANCE

GRAP COMPLIANCE

GRAP is the acronym for Generally Recognized Accounting Practice and it provides the rules by which municipalities are required to maintain their financial accounts. Successful GRAP compliance will ensure that municipal accounts are comparable and more informative for the municipality. It will also ensure that the municipality is more accountable to its citizens and other stakeholders. Information on GRAP compliance is needed to enable National Treasury to assess the pace of progress and consider the implications.

T5.13.1

# CHAPTER 6 – AUDITOR GENERAL AUDIT FIND

## COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS 2015/2016

### 6.1 AUDITOR GENERAL REPORT 2015/2016(Previous year)

| Auditor-General Report on Financial Performance: 2015/2016 |  |
| --- | --- |
| Audit Report Status*: Qualified |  |
| Non-Compliance Issues | Remedial Action Taken |
| Unspent conditional grant - Liability not cash backed | - The Municipality should source funds from sector departments to ensure that all grants are fully cash backed and spent. - Management should review and monitor compliance with applicable legislation and ensure unspent grants are backed by available cash resources. |
| Employee costs: Acting allowance - overpayment to senior managers. | Section 32 committee of MFMA should investigate the irregular expenditure. Management should ensure compliance with applicable laws and regulations. |
| Irregular expenditure – Incorrect write-off | Management should ensure that information relating to financial transactions entered by municipality is kept and records should be made available when requested. |
| Commitments - Commitments disclosed not accurate | Management should review the schedules and AFS to ensure that they are accurate and free from misstatements. |
| Non – Compliance - Unauthorized, Irregular and Fruitless and Wasteful expenditure incurred in the current year | The municipality should implement proper internal controls to prevent unauthorized, irregular expenditure and fruitless and wasteful expenditure. |
| Employee Cost (Compliance) - No performance Assessment for employees | Management should implement controls and policies to ensure that performance evaluations are performed on all employees. |
| Employee Cost - Severance Package paid not separately disclosed. | Management should record arbitration costs with the correct classification and proper disclosure should be made in the financial statements. |
| Employee cost: Employee did not sign the employment contracts. | Management should disclose irregular expenditure in the financial statement. An investigation will have to be carried out to determine whether the non-compliance above represents financial misconduct. |
| Naledi project: Sewer distribution to be transferred to Naledi local municipality | We recommend that management should transfer the completed site of the project to Naledi local municipality to be capitalised as it is already in use. Management should indicate their intention of completing the remaining part of the project. |
| Procurement - 3 quotations not received and no deviations letter attached. | Management should ensure that 3 quotations are obtained for purchases. Management should attempt to obtain and document verbal quotations where written quotations could not be obtained. |
| Procurement – Two quotations with similar information. | - The SCM manager should ensure that three different quotations are sourced from three different suppliers. - The accounting officer should investigate these quotations to determine if fair and equitable processes were followed. |
| Expenditure – Payments to suppliers not made within 30 days. | Management should manage their cash flow and budgets to ensure that payments are made within 30 days of receipt of invoice. |
| Fruitless and Wasteful Expenditure - Incorrect disclosure of fruitless and wasteful expenditure. | Management should reconcile the disclosure notes against fruitless and wasteful expense register to ensure that accurate and complete information is reported in the annual financial statements. |
| Leases - Finance lease incorrectly recorded as operating lease. | Management should ensure that the lease contracts are accounted as per required accounting standard of GRAP. |
| Expenditure – Incorrect classification of travel and entertainment costs. | Management should regularly monitor the implement the controls over the daily recording of transactions in the general ledger to ensure that it is done correctly. |
| Trade Payables – Balance per creditor’s listing does not agree to the financial statements. | Management should review the creditors listing and reconcile it to the amount recorded on the financial statements. Any differences should be investigated and appropriate correcting measures implemented. |
| Creditors – Unrecorded liabilities. | Management should ensure that expenses are accounted for as per required accounting standard of GRAP. Management should perform reconciliations between the creditor’s ledger and the supplier’s statements, and investigate and correct all reconciling items identified timeously. |
| Creditors – Payments not being done within 30 days | Management should manage their cash flow and budgets to ensure that payments are made within 30 days of receipt of invoice. |
| Payables: COIDA Invoice not accounted in the books of municipality. | Management should ensure that expenses are accounted for as per required accounting standard of GRAP. Management should perform reconciliations between the creditor’s ledger and the supplier’s statements, and investigate and correct all reconciling items identified timeously. |
| Payables – Difference identified on the salary control account. | Management should keep proper and complete records. All differences identified in control account reconciliations should be investigated and cleared. |
| Procurement – Overpayment of creditors | Management should ensure that payments are done for valid invoices and an official must certify that the service was rendered. Management should recover the amount from the supplier |
| Irregular expenditure – Non-compliance with sec 112(j) of MFMA | Management should adhere to rules and regulations of SCM and report in the register for irregular expenditure. |
| ISA: Security policy not approved | IT Management should fast track the process of approving the IT security policy. Furthermore measures should be put in place to ensure the implementation of the designed controls is continuously monitored on a regular basis. |
| ISA: Patch management policy and procedures not established | IT management should design adequate patch management procedures which include the following; definition of patch information sources, prioritisation, testing procedures, change management, installation and deployment and monitoring of updates to ensure consistency and continuous compliance. Furthermore the responsibility for the patch management process should be delegated to a specific individual to ensure that the organisation’s network and systems are protected by the required patches/updates. |
| ISA: User access procedures not approved | Management should fast track the approval of the user access management policy/procedures. Furthermore the user access management policy should be formally communicated to all users to ensure consistency in the implementation of user access management activities within the municipality. Management should put measures in place to constantly monitor the implementation of the policy. |
| ISA: Usernames not assigned to specific users | Management should fast track the approval of the user access management policy/procedures. Furthermore the user access management policy should be formally communicated to all users to ensure consistency in the implementation of user access management activities within the municipality. All user IDs on the systems and applications should be linked to specific persons to ensure accountability. |
| Unspent conditional grants - Quarterly reports not submitted within 30days | We recommend that all quarterly reports are submitted to CoGTA/Treasury within the specified time period stated in Section 12(2)( c) |
| Procurement - Non-Compliance with MFMA Circular 81 | Management must ensure that MFMA Circular 81 requirements are adhered to. |
| Procurement- No evidence that the bid results were published on the website of the municipality | Management should investigate the reasons why the non-compliance with SCM policy was not adhered to. Management should ensure that bid entries in the register and the bid results are published on the website as required by paragraph 22 (1) (a) of the Municipal Supply Chain Management Policy. |
| Procurement – Recommended bidder was not selected as the preferred bidder | Management should ensure that the lowest bidder who meets all requirements of the bidding process should be recommended as the preferred bidder. |
| Budget: Budgeted expenditure exceeds the Budgeted Revenue | Management should ensure that the budgeted revenue of the Municipality exceeds the budgeted operating expenditure. |
| Employee cost - Third Party Payments | Management should ensure that payments to third parties, on behalf of employees, are paid over to the relevant party on or before the 7th of the each subsequent month. |
| Employee cost – Acting period exceeding 3 months | Management should comply with legislation regarding the maximum period for acting positions. If the period will exceed 3 months (for a maximum of another 3 months) prior authorization should be obtained from the MEC. |
| Non-compliance : Audit committee | Management should ensure that the audit committee performs all functions as required by section 166(2) (a) and (b) of the MFMA. |
| Limitation of scope on the investigation report on prior year audit communication no.45. | Management should ensure that the reports are submitted to the auditors and that proper and accurate records are kept. |
| ISA: Vendors with unlimited access to systems | The activities of the vendor on the production environment should be limited and monitored on a regular basis. The reviews should include reviews of activities and specific areas modified within the system. |
| ISA - Backups and retention strategy not implemented | Management should develop and implement a backup and retention strategy in line with contractual, legal/regulatory and business requirements. |
| Procurement- Bid adjudication committee not constituted in accordance with the municipality's SCM policy. | The accounting officer should align the municipality's SCM policy in a way that will be suitable for the municipality's requirements. |
| Unspent Conditional Grant - No Roll-Over Applications. | Management should comply with the requirements of DORA. For any conditional grants rollover, proper procedures as per DORA should be followed and authorization obtained before the funds are used for other purposes. |
|  | T 6.1.1 |

## COMPONENT B: AUDITOR-GENERAL OPINION 2016/2017 (CURRENT YEAR)

### 6.2 AUDITOR GENERAL REPORT 2016/2017

AUDITOR GENERAL REPORT ON THE FINANCIAL STATEMENTS: 2016/2017

# Report of the auditor-general to the Free State Legislature and the council on the Xhariep District Municipality

## Report on the audit of the financial statements

### Opinion

- I have audited the financial statements of the Xhariep District Municipality set out on pages 126 to 189, which comprise the statement of financial position as at 30 June 2017, the statement of financial performance, statement of changes in net assets, cash flow statement and statement of comparison of budget and actual amounts for the year then ended, as well as the notes to the financial statements, including a summary of significant accounting policies.

- In my opinion, the financial statements present fairly, in all material respects, the financial position of the Xhariep District Municipality as at 30 June 2017, and its financial performance and cash flows for the year then ended in accordance with the South African Standards of Generally Recognised Accounting Practice (SA Standards of GRAP) and the requirements of the Municipal Finance Management Act of South Africa, 2003 (Act No. 56 of 2003) (MFMA) and the Division of Revenue Act of South Africa, 2016 (Act No. 3 of 2016) (DoRA).

### Basis for opinion

- I conducted my audit in accordance with the International Standards on Auditing (ISAs). My responsibilities under those standards are further described in the auditor-general’s responsibilities for the audit of the financial statements section of my report.

- I am independent of the municipality in accordance with the International Ethics Standards Board for Accountants’ Code of ethics for professional accountants (IESBA code) and the ethical requirements that are relevant to my audit in South Africa. I have fulfilled my other ethical responsibilities in accordance with these requirements and the IESBA code.

- I believe that the audit evidence I have obtained is sufficient and appropriate to provide a basis for my opinion.

### Material uncertainty related to going concern

- I draw attention to the matter below. My opinion is not modified in respect of this matter.

- Note 36 in the financial statements, indicates that the municipality incurred a net loss of R5 102 624 during the year ended 30 June 2017 and, as of that date, the municipality’s current liabilities exceeded its current assets by R14 441 675. The municipality has been deducting pay as you earn from employee’s salaries, but has been unable to pay over R4 518 685 (2016: R585 765) of these amounts deducted to the relevant third parties as disclosed in note 46. These conditions, along with other matters as set forth in note 36, indicate the existence of a material uncertainty that may cast significant doubt on the municipality’s ability to operate as a going concern and to meet its service delivery objectives.

### Emphasis of matters

- I draw attention to the matters below. My opinion is not modified in respect of these matters.

#### Material impairments

- As disclosed in note 7 to the financial statements, a provision for the impairment of debtors of R3 543 530 (2016: R2 103 576) has been made with regard to irrecoverable trade debtors.

#### Unauthorised expenditure

- As disclosed in note 38 to the financial statements, the municipality incurred unauthorised expenditure of R5 237 820 (2016: R2 797 621) during 2016-17 due to expenditure that exceeded the budgeted amounts for impairment of assets and audit fees.

#### Irregular expenditure

- As disclosed in note 40 to the financial statements, the municipality incurred irregular expenditure of R1 509 550 (2016: R4 181 999) in 2016-17 due to non-compliance with Supply Chain Management (SCM) Regulations.

#### Fruitless and wasteful expenditure

- As disclosed in note 39 to the financial statements, fruitless and wasteful expenditure of R870 415 (2016: R440 631) was incurred due to penalties and interest charged on accounts not being paid timely.

### Restatement of corresponding figures

- As disclosed in note 34 to the financial statements, the corresponding figures for 
30 June 2016 have been restated as a result of errors in the financial statements of the municipality at, and for the year ended, 30 June 2017.

### Other matter

- I draw attention to the matter below. My opinion is not modified in respect of this matter.

#### Unaudited disclosure notes

- In terms of section 125(2)(e) of the MFMA, the municipality is required to disclose particulars of non-compliance with the MFMA. This disclosure requirement, as contained in note 48 to the financial statements, did not form part of the audit of the financial statements and, accordingly, I do not express an opinion on it.

### Responsibilities of the accounting officer for the financial statements

- The accounting officer is responsible for the preparation and fair presentation of the financial statements in accordance with the SA Standards of GRAP and the requirements of the MFMA and DoRA and for such internal control as the accounting officer determines is necessary to enable the preparation of financial statements that are free from material misstatement, whether due to fraud or error.

- In preparing the financial statements, the accounting officer is responsible for assessing the Xhariep District Municipality’s ability to continue as a going concern, disclosing, as applicable, matters relating to going concern and using the going concern basis of accounting unless the intention is to liquidate the municipality or cease operations, or there is no realistic alternative but to do so.

### Auditor-general’s responsibilities for the audit of the financial statements

- My objectives are to obtain reasonable assurance about whether the financial statements as a whole are free from material misstatement, whether due to fraud or error, and to issue an auditor’s report that includes my opinion. Reasonable assurance is a high level of assurance, but is not a guarantee that an audit conducted in accordance with the ISAs will always detect a material misstatement when it exists. Misstatements can arise from fraud or error and are considered material if, individually or in aggregate, they could reasonably be expected to influence the economic decisions of users taken on the basis of these financial statements.

- A further description of my responsibilities for the audit of the financial statements is included in the annexure to the auditor’s report.

## Report on the audit of the annual performance report

### Introduction and scope

- In accordance with the Public Audit Act of South Africa, 2004 (Act No. 25 of 2004) (PAA) and the general notice issued in terms thereof I have a responsibility to report material findings on the reported performance information against predetermined objectives for selected key performance areas (KPAs) presented in the annual performance report. I performed procedures to identify findings but not to gather evidence to express assurance.

- My procedures address the reported performance information, which must be based on the approved performance planning documents of the municipality. I have not evaluated the completeness and appropriateness of the performance indicators included in the planning documents. My procedures also did not extend to any disclosures or assertions relating to planned performance strategies and information in respect of future periods that may be included as part of the reported performance information. Accordingly, my findings do not extend to these matters.

- I evaluated the usefulness and reliability of the reported performance information in accordance with the criteria developed from the performance management and reporting framework, as defined in the general notice, for the following selected KPAs presented in the annual performance report of the municipality for the year ended 30 June 2017:

| KPAs | Pages in the annual performance report |
| --- | --- |
| Basic service delivery (BSD) | 48 – 85 |
| Local economic development (LED) | 48 – 85 |

- I performed procedures to determine whether the reported performance information was properly presented and whether performance was consistent with the approved performance planning documents. I performed further procedures to determine whether the indicators and related targets were measurable and relevant, and assessed the reliability of the reported performance information to determine whether it was valid, accurate and complete.

- I did not raise any material findings on the usefulness and reliability of the reported performance information for the following KPAs:

- Basic service delivery (BSD)

- Local economic development (LED)

### Other matters

- I draw attention to the matters below:

- Achievement of planned targets

- Refer to the annual performance report on pages 48 to 85 for information on the achievement of planned targets for the year and explanations provided for the under and overachievement of a number of targets.

- Adjustment of material misstatements

- I identified material misstatements in the annual performance report submitted for auditing. These material misstatements were on the reported performance information of basic service delivery and local economic development. As management subsequently corrected the misstatements, I did not raise any material findings on the usefulness and reliability of the reported performance information.

## Report on audit of compliance with legislation

### Introduction and scope

- In accordance with the PAA and the general notice issued in terms thereof I have a responsibility to report material findings on the compliance of the municipality with specific matters in key legislation. I performed procedures to identify findings but not to gather evidence to express assurance.

- The material findings on compliance with specific matters in key legislations are as follows:

#### Annual financial statements

- The financial statements submitted for auditing were not prepared, in all material respects, in accordance with the requirements of section 122 of the MFMA. Material misstatements of non-current assets, liabilities, expenditure and disclosure items identified by the auditors in the submitted financial statement were subsequently corrected, resulting in the financial statements receiving an unqualified audit opinion.

#### Budget

- Reasonable steps were not taken to prevent unauthorised expenditure of R5 237 820, as disclosed in note 38 to the annual financial statements, in contravention of section 62(1)(d) of the MFMA. The majority of the unauthorised expenditure was caused by expenditure that exceeded the budgeted amounts for impairment of assets and audit fees.

#### Consequence management

- Unauthorised, irregular, fruitless and wasteful expenditure, incurred by the municipality was not investigated to determine if any person was liable for the expenditure, as required by section 32(2)(a)(b) of the MFMA.

#### Expenditure management

- Money owed by the municipality was not always paid within 30 days, as required by section 65(2)(e) of the MFMA.

- Effective steps were not taken to prevent irregular expenditure of R1 509 550 as disclosed in note 40 to the annual financial statements, as required by section 62(1)(d) of the MFMA. The majority of the irregular expenditure was caused by not obtaining quotations or following a bidding process.

- Effective steps were not taken to prevent fruitless and wasteful expenditure of R870 415, as disclosed in note 39 to the annual financial statements, in contravention of section 62(1)(d) of the MFMA. The majority of the disclosed fruitless and wasteful expenditure was caused by interest and penalties being charged due to late payments.

#### Human resource management

- Appropriate systems and procedures to monitor, measure and evaluate performance of staff were not developed and adopted, as required by section 67(1)(d) of the Municipal Systems Act, 2000 (Act No. 32 of 2000).

#### Liability management

- An effective system of internal control for liabilities was not in place, as required by section 63(2)(c) of the MFMA.

#### Procurement and contract management

- Some of the goods and services with a transaction value of below R200 000 were procured without obtaining the required price quotations, in contravention of SCM regulation 17(a) and (c). Similar non-compliance was also reported in the previous year.

- Some of the goods and services of a transaction value above R200 000 were procured without inviting competitive bids, as required by SCM regulation 19(a).

- The preference point system was not applied for some of the procurement of goods and services above R30 000, as required by section 2(a) of the Preferential Procurement Policy Framework Act, 2000 (Act No. 5 of 2000) (PPPFA).

## Other information

- The Xhariep District Municipality’s accounting officer is responsible for the other information. The other information comprises the information included in the annual report. The other information does not include the financial statements, the auditor’s report and those selected KPAs presented in the annual performance report that have been specifically reported in the auditor’s report.

- My opinion on the financial statements and findings on the reported performance information and compliance with legislation do not cover the other information and I do not express an audit opinion or any form of assurance conclusion thereon.

- In connection with my audit, my responsibility is to read the other information and, in doing so, consider whether the other information is materially inconsistent with the financial statements and the KPAs presented in the annual performance report, or my knowledge obtained in the audit, or otherwise appears to be materially misstated. If, based on the work I have performed on the other information obtained prior to the date of this auditor’s report, I conclude that there is a material misstatement of this other information, I am required to report that fact.

- I did not receive the other information prior to the date of this auditor’s report. When I do receive and read this information, if I conclude that there is a material misstatement therein, I am required to communicate the matter to those charged with governance and request that the other information be corrected. If the other information is not corrected, I may have to retract this auditor’s report and re-issue an amended report as appropriate, however, if it is corrected this will not be necessary.

## Internal control deficiencies

- I considered internal control relevant to my audit of the financial statements, reported performance information and compliance with applicable legislation; however, my objective was not to express any form of assurance thereon. The matters reported below are limited to the significant internal control deficiencies that resulted in the findings on compliance with legislation included in this report.

- Various material adjustments were made to the financial statements. This was mainly due to vacancies in key positions which were not filled to facilitate sound financial management, as the position of chief financial officer remained vacant during the financial year under review. There has been a slow response in implementing and monitoring the audit action plan to address internal control deficiencies identified during the previous audits and as a result it was again a last-minute effort to avoid audit report matters.

- The significant unauthorised, irregular and fruitless and wasteful expenditure incurred was due to lack of consequence management within the municipality. Effective steps were not taken to ensure that there were consequences for poor performance and transgressions, as none of the unauthorised, irregular and fruitless and wasteful expenditure was investigated during the financial year.

- The municipality did not always comply with applicable legislation. No formal processes were in place to monitor compliance with legislation, which resulted in the number of reported non-compliance issues. Consequences for poor performance and non-compliance with legislation were lacking.

- The audit committee and internal audit unit provided limited assurance over financial and performance reporting as well as compliance with legislation, as the audit committee was not functional for the entire financial year and as a result the internal audit unit was not fully effective.

Bloemfontein

30 November 2017

# Annexure – auditor-general’s responsibility for the audit

- As part of an audit in accordance with the ISAs, I exercise professional judgement and maintain professional scepticism throughout my audit of the financial statements, and the procedures performed on reported performance information for selected key performance areas and on the municipality’s compliance with respect to the selected subject matters.

### Financial statements

- In addition to my responsibility for the audit of the financial statements as described in the auditor’s report, I also:

- identify and assess the risks of material misstatement of the financial statements whether due to fraud or error, design and perform audit procedures responsive to those risks, and obtain audit evidence that is sufficient and appropriate to provide a basis for my opinion. The risk of not detecting a material misstatement resulting from fraud is higher than for one resulting from error, as fraud may involve collusion, forgery, intentional omissions, misrepresentations, or the override of internal control

- obtain an understanding of internal control relevant to the audit in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the municipality’s internal control

- evaluate the appropriateness of accounting policies used and the reasonableness of accounting estimates and related disclosures made by the accounting officer

- conclude on the appropriateness of the accounting officer’s use of the going concern basis of accounting in the preparation of the financial statements. I also conclude, based on the audit evidence obtained, whether a material uncertainty exists related to events or conditions that may cast significant doubt on the Xhariep District Municipality’s ability to continue as a going concern. If I conclude that a material uncertainty exists, I am required to draw attention in my auditor’s report to the related disclosures in the financial statements about the material uncertainty or, if such disclosures are inadequate, to modify the opinion on the financial statements. My conclusions are based on the information available to me at the date of the auditor’s report. However, future events or conditions may cause a municipality to cease continuing as a going concern

- evaluate the overall presentation, structure and content of the financial statements, including the disclosures, and whether the financial statements represent the underlying transactions and events in a manner that achieves fair presentation.

### Communication with those charged with governance

- I communicate with the accounting officer regarding, among other matters, the planned scope and timing of the audit and significant audit findings, including any significant deficiencies in internal control that I identify during my audit.

- I also confirm to the accounting officer that I have complied with relevant ethical requirements regarding independence, and communicate all relationships and other matters that may reasonably be thought to have a bearing on my independence and, where applicable, related safeguards.

GLOSSARY

GLOSSARY

| Accessibility indicators | Explore whether the intended beneficiaries are able to access services or outputs. |
| --- | --- |
| Accountability documents | Documents used by executive authorities to give “full and regular” reports on the matters under their control to Parliament and provincial legislatures as prescribed by the Constitution. This includes plans, budgets, in-year and Annual Reports. |
| Activities | The processes or actions that use a range of inputs to produce the desired outputs and ultimately outcomes. In essence, activities describe "what we do". |
| Adequacy indicators | The quantity of input or output relative to the need or demand. |
| Annual Report | A report to be prepared and submitted annually based on the regulations set out in Section 121 of the Municipal Finance Management Act. Such a report must include annual financial statements as submitted to and approved by the Auditor-General. |
| Approved Budget | The annual financial statements of a municipality as audited by the Auditor General and approved by council or a provincial or national executive. |
| Baseline | Current level of performance that a municipality aims to improve when setting performance targets. The baseline relates to the level of performance recorded in a year prior to the planning period. |
| Basic municipal service | A municipal service that is necessary to ensure an acceptable and reasonable quality of life to citizens within that particular area. If not provided it may endanger the public health and safety or the environment. |
| Budget year | The financial year for which an annual budget is to be approved – means a year ending on 30 June. |
| Cost indicators | The overall cost or expenditure of producing a specified quantity of outputs. |
| Distribution indicators GLOSSARY | The distribution of capacity to deliver services. |
| Financial Statements | Includes at least a statement of financial position, statement of financial performance, cash-flow statement, notes to these statements and any other statements that may be prescribed. |
| General Key performance indicators | After consultation with MECs for local government, the Minister may prescribe general key performance indicators that are appropriate and applicable to local government generally. |
| Impact | The results of achieving specific outcomes, such as reducing poverty and creating jobs. |
| Inputs | All the resources that contribute to the production and delivery of outputs. Inputs are "what we use to do the work". They include finances, personnel, equipment and buildings. |
| Integrated Development Plan (IDP) | Set out municipal goals and development plans. |
| National Key performance areas | - Service delivery & infrastructure - Economic development - Municipal transformation and institutional development - Financial viability and management - Good governance and community participation |
| Outcomes | The medium-term results for specific beneficiaries that are the consequence of achieving specific outputs. Outcomes should relate clearly to an institution's strategic goals and objectives set out in its plans. Outcomes are "what we wish to achieve". |
| Outputs | The final products, or goods and services produced for delivery. Outputs may be defined as "what we produce or deliver". An output is a concrete achievement (i.e. a product such as a passport, an action such as a presentation or immunization, or a service such as processing an application) that contributes to the achievement of a Key Result Area. |
| Performance Indicator | Indicators should be specified to measure performance in relation to input, activities, outputs, outcomes and impacts. An indicator is a type of information used to gauge the extent to which an output has been achieved (policy developed, presentation delivered, service rendered) GLOSSARY |
| Performance Information | Generic term for non-financial information about municipal services and activities. Can also be used interchangeably with performance measure. |
| Performance Standards: | The minimum acceptable level of performance or the level of performance that is generally accepted. Standards are informed by legislative requirements and service-level agreements. Performance standards are mutually agreed criteria to describe how well work must be done in terms of quantity and/or quality and timeliness, to clarify the outputs and related activities of a job by describing what the required result should be. In this EPMDS performance standards are divided into indicators and the time factor. |
| Performance Targets: | The level of performance that municipalities and its employees strive to achieve. Performance Targets relate to current baselines and express a specific level of performance that a municipality aims to achieve within a given time period. |
| Service Delivery Budget Implementation Plan | Detailed plan approved by the mayor for implementing the municipality’s delivery of services; including projections of the revenue collected and operational and capital expenditure by vote for each month. Service delivery targets and performance indicators must also be included. |
| Vote: | One of the main segments into which a budget of a municipality is divided for appropriation of money for the different departments or functional areas of the municipality. The Vote specifies the total amount that is appropriated for the purpose of a specific department or functional area. Section 1 of the MFMA defines a “vote” as: a) one of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned |

APPENDICES

# APPENDICES

## APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE

| Council Members | Full Time / Part Time | Committees Allocated | *Ward and/ or Party Represented | Percentage Council Meetings Attendance |
| --- | --- | --- | --- | --- |
|  | FT/PT |  |  | % |
| CLLR MJ SEHANKA | FT | Mayoral Committee | - | 100 |
|  |  | Council | ANC | 87 |
| CLLR MG NTWANAMBI | FT | Corporate Services |  | 100 |
|  |  | Mayoral Committee |  | 50 |
|  |  | Council | ANC | 60 |
| CLLR AN NOVEMBER | PT | Planning & Social Development |  | 83 |
|  |  | Council | ANC | 73 |
| CLLR MJ MOITSE | PT | Corporate Services |  | 100 |
|  |  | Council | ANC | 56 |
| CLLR C BURGER | PT | Budget and Treasury |  | 78 |
|  |  | Council | DA | 73 |
| CLLR B SMITH | PT | Corporate Services |  | 60 |
|  |  | Council | DA | 73 |
| CLLR AJJ VAN RENSBURG | PT | Planning & Social Development | DA | 67 |
| APPENDICES |  | Council | DA | 60 |
| CLLR MJ PHALISO | PT | Budget &Treasury |  | 56 |
|  |  | Council | ANC | 80 |
| CLLR IS RIDDLE | PT | Corporate Services | DA | 80 |
|  |  | Council |  | 67 |
| CLLR MJ MOEKETSI | PT | Budget &Treasury |  | 56 |
|  |  | Council | ANC | 87 |
| CLLR JK SEBECO | FT | Budget &Treasury | ANC | 100 |
|  |  | Mayoral Committee |  | 100 |
|  |  | Council |  | 80 |
| CLLR MS MOGAPI | PT | Planning & Social Development |  | 50 |
|  |  | Council | ANC | 60 |
| CLLR TD MOCHECHEPA | FT | Planning & Social Development |  | 100 |
|  |  | Mayoral Committee |  | 100 |
|  |  | Council | ANC | 67 |
| CLLR NS MQUNGQUTHU | FT | Speaker – Council | ANC | 89 |
| CLLR TS TSEUOA | PT | Budget &Treasury | ANC | 100 |
|  |  | Council | ANC | 100 |

APPENDICES

## APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES

| Committees (other than Mayoral / Executive Committee) and Purposes of Committees |  |
| --- | --- |
| Municipal Committees | Purpose of Committee |
| Oversight Committee | Playing an oversight Role over the finances and the administration of the Municipality |
| Audit Committee | Performing duties as stipulated in Section 166 of the MFMA |
| MPAC | Playing an oversight Role over the finances and the administration of the Municipality |

APPENDICES

## APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY

| Municipal / Entity Functions |  |  |
| --- | --- | --- |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No)* | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 4, Part B functions: |  |  |
| Air pollution | Yes |  |
| Building regulations | No |  |
| Child care facilities | Yes |  |
| Electricity and gas reticulation | No |  |
| Firefighting services | No |  |
| Local tourism | Yes |  |
| Municipal airports | No |  |
| Municipal planning | Yes |  |
| Municipal health services | Yes |  |
| Municipal public transport | No |  |
| Municipal public works only in respect of the needs of municipalities in the discharge of their responsibilities to administer functions specifically assigned to them under this Constitution or any other law | No |  |
| Pontoons, ferries, jetties, piers and harbours, excluding the regulation of international and national shipping and matters related thereto | No |  |
| Stormwater management systems in built-up areas | No |  |
| Trading regulations | No |  |
| Water and sanitation services limited to potable water supply systems and domestic waste-water and sewage disposal systems | No |  |
| Continued next page |  |  |
| Continued from previous page |  |  |
| Municipal / Entity Functions |  |  |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No)* | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 5, Part B functions: |  |  |
| Beaches and amusement facilities APPENDICES | No |  |
| Billboards and the display of advertisements in public places | No |  |
| Cemeteries, funeral parlours and crematoria | Yes |  |
| Cleansing | No |  |
| Control of public nuisances | No |  |
| Control of undertakings that sell liquor to the public | No |  |
| Facilities for the accommodation, care and burial of animals | No |  |
| Fencing and fences | No |  |
| Licensing of dogs | No |  |
| Licensing and control of undertakings that sell food to the public | No |  |
| Local amenities | No |  |
| Local sport facilities | No |  |
| Markets | No |  |
| Municipal abattoirs | No |  |
| Municipal parks and recreation | No |  |
| Municipal roads | No |  |
| Noise pollution | Yes |  |
| Pounds | No |  |
| Public places | No |  |
| Refuse removal, refuse dumps and solid waste disposal | No |  |
| Street trading | No |  |
| Street lighting | No |  |
| Traffic and parking | No |  |
| * If municipality: indicate (yes or No); * If entity: Provide name of entity |  | T D |

APPENDICES

## APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE 2016/2017

| Municipal Audit Committee Recommendations |  |  |
| --- | --- | --- |
| Date of Committee | Committee recommendations during 2014/2015 | Recommendations adopted (enter Yes) If not adopted (provide explanation) |
| Procurement- Bid adjudication committee not constituted in accordance with the municipality's SCM policy. | The accounting officer should align the municipality's SCM policy in a way that will be suitable for the municipality's requirements. | Yes |
| Unspent Conditional Grant - No Roll-Over Applications. | Management should comply with the requirements of DORA. For any conditional grants rollover, proper procedures as per DORA should be followed and authorization obtained before the funds are used for other purposes. | Yes |
| Procurement- Bid adjudication committee not constituted in accordance with the municipality's SCM policy. | The accounting officer should align the municipality's SCM policy in a way that will be suitable for the municipality's requirements. | Yes |
| Unspent Conditional Grant - No Roll-Over Applications. | Management should comply with the requirements of DORA. For any conditional grants rollover, proper procedures as per DORA should be followed and authorization obtained before the funds are used for other purposes. | Yes |
|  |  | T G |

APPENDICES

## APPENDIX H(i) – Long Term Contracts (20 Largest Contracts Entered into during 2016/2017

| Long Term Contracts (20 Largest Contracts Entered into during 2016/2017) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R' 000 |  |  |  |  |  |
| Name of Service Provider (Entity or Municipal Department) | Description of Services Rendered by the Service Provider | Start Date of Contract | Expiry date of Contract | Project manager | Contract Value |
| Thepa Trading | Printers | 1 June 2015 | 31 May 2018 | Mr Andile Tyhokolo | R 1 161 390.86 |
| Thepa Trading | Telephone Systems | 02 October 2015 | 30 September 2018 | Mr Andile Tyhokolo | R 539 779.32 |
| LQ Technologies | Internet Service Provision | 1 February 2017 | 31 January 2020 | Mr Andile Tyhokolo | R 900 000.00 |
| Lateral Unison | Short Term Insurances | 1 July 2016 | 30 June 2017 | Mr Clive Mogoale | R 210 446.00 |
| Aganang Consulting Engineers | Rural Roads Assets Management systems | 9 November 2016 | 31 October 2019 | Mr Paki Dlomo | R 6 373 000.00 |
| OS Holdings | mSCOA Project Implementation | 1 December 2016 | 30 November 2019 | Mr Sabelo Zwane | R 5 793 373.00 |
|  |  |  |  |  | T H.1 |

## APPENDIX I –SERVICE PROVIDER PERFORMANCE SCHEDULE

| Service Provider | Project Name | Contract Amount | Project Status | End User Remarks |
| --- | --- | --- | --- | --- |
| Thepa Trading | Printers | R 1 161 390.86 | Active | The service provider renders satisfactory service |
| Thepa Trading | Telephone Systems | R 539 779.32 | Active | The service provider is redering acceptable service, there is room for improvement |
| LQ Technologies | Internet Service Provision | R 900 000.00 | Active | The service provider is rendering satisfactory service |
| Lateral Unison | Short Term Insurances | R 210 446.00 | Extension | The service provider renders satisfactory service |
| Aganang Consulting Engineers | Rural Roads Assets Management systems | R 6 373 000.00 | Active |  |
| OS Holdings | mSCOA Project Implementation | R 5 793 373.00 | Active | mSCOA systems has been implemented as of July 2017 and to date the progress has been according to plan and to the satisfaction of the Municipality |

## APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS

| Disclosures of Financial Interests |  |  |
| --- | --- | --- |
| Period 1 July to 30 June of 2016/2017 (Current Year) |  |  |
| Position | Name | Description of Financial interests* (Nil / Or details) |
| (Executive) Mayor | M.J Sehanka | Nil |
| Member of MayCo / Exco |  |  |
|  | M.G Ntwanambi | Nil |
|  | JK Sebeco | Nil |
|  | TD Mochechepa | Nil |
| Councillor | N Jafta | Nil |
|  | H Shebe | Nil |
|  | T Mokhele | Nil |
|  | M.J Mohapi | Nil |
|  | M.J Mphore | Nil |
|  | NC Spochter | Nil |
|  | S. A Sola | Nil |
| Municipal Manager | MM Kubeka | Nil |
| Chief Financial Officer(Acting) | MC Mogoale | Nil |
| (Executive) Directors | MS Mohale | Nil |
| TJ |  |  |

## APPENDIX K (i): REVENUE COLLECTION PERFORMANCE BY Source

| Revenue Collection Performance by Source |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| R '000 |  |  |  |  |  |  |
| Description | 2014/2015 | 2015/2016 |  |  | 2016/17 Variance |  |
|  | Actual | Original Budget | Adjustments Budget | Actual | Original Budget | Adjustments Budget |
| Agency services |  |  |  |  |  |  |
| Transfers recognised - operational | 51 564 | 51 774 | 51 774 | 52 564 | 52 044 | 52 044 |
| Other revenue | 882 | 563 | 563 | 884 | 574 | 574 |
| Total Revenue (excluding capital transfers and contributions) |  |  |  |  |  |  |
| Variances are calculated by dividing the difference between actual and original/adjustments budget by the actual. This table is aligned to MBRR table A4. |  |  |  |  |  | T K.2 |

## APPENDIX T – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT

| National and Provincial Outcomes for Local Government |  |  |
| --- | --- | --- |
| Outcome/Output | Progress to date | Number or Percentage Achieved |
| Output: Improving access to basic services | N/A |  |
| Output: Implementation of the Community Work Programme | N/A |  |
| Output: Deepen democracy through a refined Ward Committee model | N/A |  |
| Output: Administrative and financial capability | Xhariep is doing well in terms of this output. For the past two financial years the municipality made remarkable strides in terms of improving its Audit opinion from a qualification to unqualified. Budget related policies are in place and approved by Council. Financial statements are GRAP Compliant. | 85% |
| T T |  |  |

## VOLUME II: ANNUAL FINANCIAL STATEMENTS

Volume II of the Annual Report(attached as an Annexure)