## Tender status 11-12 (hidden)
Contract Management template 2011/2012
Name of Comany | Name of Project | Bid number | VAT number | Contact person | Contact details | Advert date | Tender closing | Appointment date | Vote Number | Contract Amount | Amount paid | Outstanding balance | Stage of completion and comments | Recommendation
Synchrim Multi Travel, Mvelase Travel & tours | Request for proposals: Travel agency | XDM-TAP01/11/12 |  |  |  | 2012-02-22 | 2012-03-13 | 2012-03-26 | 4000/4011/050;100;150;200;250 | 0 | 0 | 0 | The project will be on going and suppliers will invoice the municipality on the rate that will be agreed upon between suppliers and the municipality
Builders Warehouse | Building Material for the refurbishment of Smithfield hall | BM-SFH01/11/12 |  |  |  | 2011-09-27 | 2011-10-07 |  | 4000/3215/250 | 53054.35 | 53054.35 | 0 | 95% Complete | LED unit finalising the project
Lezmin Computers | Supply of computers | XDM-SALAD02;11/12 |  |  |  | 12-09-2011 | 20-09/2011 | 2011-10-14 | 4000/4098/200;6400/4420/150 | 77016.2 | 82116.2 | -5100 | 100% completed- At the time of payment certain laptops agreed upon where no longer on the market, the municipality therefore had to get the latest versions of the requested laptops, hence there were price changes.
Phiwe Construction | Repairs to leaking roof | REPAIRS 01/11/12 |  |  |  | 2011-08-01 | 2011-08-12 | 2011-08-23 | 3370/3375/150 | 96987.78 | 96987.78 | 0 | 100% completed
LQ Technologies | Backup Sever Solution | XDM-BSS01/11/12 |  |  |  | 2012-03-23 | 2012-04-04 | 2012-04-19 | 6400/4420/150 | 97000 | 97000 | 0 | 100% complete
First Technology | Supply of stationery | XDM-STATIONERY01/11 |  |  |  | 2011-08-16 | 2011-08-24 | 2011-08-25 | 4000/4004/050;150;200;250 | 126207.48 | 126207.48 | 0 | 100% completed
Amohelang Trading | Supply of furniture | XDM-FURNITURE 02/11/12 |  |  |  | 2011-08-30 | 2011-09-08 | 2011-09-16 | 6400/4415/100;150 | 126664.75 | 126664.75 | 0 | 100% completed | It is recommended to management that the services of Amohela Trading no longer be used by the municipality and he be listed on the National Treasury list of prohibited suppliers. This is as a result of him failing to pay his suppliers(CN Business furniture)and his suppliers wanted to re-posess furniture from the municipality.
KTP Management Consultancy | Allignment of IDP and PMS | XDM-API/11/12 |  |  |  | 2012-02-27 | 2012-03-06 |  | 4000/4480/050 | 144000 | 144000 | 0 | 100% completed
ASM Consulting | needs analysis at Letsemeng Local Municipality | XDM-JOBDISC 10/11 |  |  |  | 2011-07-01 | 2012-07-12 | 2011-08-16 | 4000/4017/150 | 161228.07 | 161228.07 | 0 | 100% complete | That Mr. Wetes provide the SCM unit with a completion report
Matsapa Trading 725 | Supply of Environmental Health awareness materials for XDM | [6 empty] | 2012-06-29 |  | 161825
Sikisi Communication Strategies | Communication Strategy | COM-STR 01/11/12 |  |  |  | 2011-11-02 | 2011-11-10 | 2011-11-17 | 4000/4470/050 | 162500 | 162500 | 0 | 95% completed-workshop still to be conducted | It is recommended that management ensure that a workshop regarding the said subject is conducted to the entire staff.
Inkamva ICT | Tourism brochures,DVDs, pens, and T-shirts | XDM-TMP01/11/12 |  |  |  | 2012-03-23 | 2012-04-04 | 2012-04-17 | 4000/4039/100 | 162706.5 | 162706.5 | 0 | 100% complete
Makomota Investment Holdings PTY (ltd) | Review of policies: tarrif policy, bad debt written -off policy, tender policy, banking and investment policy,budget policy, cellphone policy,laptops policy, budget transfers and virement policy, travelling and subsistence policy, credit control and debt collection policy and fixed assets policy | XDM-ROBRP/11/12 |  |  |  | 2011-12-05 | 2011-12-13 | 2011-12-13 | 4000/4492/200 | 175104 | 175104 | 0 | 90% complete-progress report to be requested from the budget and reporting unit. | It is recommended that management ensure that a workshop regarding the said subject is conducted to the entire staff.
Ntsu Trading 673 cc | Koffiefontein Fencing | XDM-KOFF-FEN01/11/12 |  |  |  | 2011-10-12 | 2011-10-20 | 2012-01-05 | 4000/4092/100 | 178453.28 | 178453.28 | 0 | 95% complete Shortage of material | LED unit finalising the project
Bafetohile Development Institute | Training on disciplinary hearing procedures | TMDHP 11/11 |  |  |  | 2011-11-16 | 2011-11-24 | 2011-12-08 | 4000/4017/150 | 180000 | 180000 | 0 | 100% completed
Stimer Construction | Printing of XDM annual Report | [6 empty] | 2011-09-15 | 4000/4004/050 | 184588 | 184588 | 0 | 100% completed
Khethakanye Consultancy | Training on finance for non-finance managers and officials | TF-NFMO 11/11 |  |  |  | 2011-11-23 | 2011-12-01 | 2011-12-02 | 4000/4017/150 | 185548.2 | 185548.2 | 0 | 100% completed
Khethakanye Consultancy | Printing of XDM annual budget | [6 empty] | 2011-09-16 | 4000/4004/200 | 187290 | 187290 | 0 | 100% completed
KTP Management Consultancy | Municipal Strategic Planning | STR-PLAN 01/11/12 |  |  |  | 2011-10-04 | 2011-10-13 | 2011-10-14 | 4000/4087/100 | 188995.2 | 118995 | R - | 100% completed
Kissmetics General Trading | Needs analysis at Letsemeng Local Municipality |  |  |  |  | 2012-06-18 | 2012-06-26 | 2012-06-26 | 3200/3400/150 | 189560 | 189560 | 0 | 95% Complete | Report to be submited to SCM Unit
| Workshop on municipal financial oversight and the establishment of municipal public accounts committees | MFO-MPAC11/11 |  |  |  | 2011-11-16 | 2011-11-24 |  | new vote |  |  | 0 | Bid was put on hold by management,but a go-ahead has been given to continue with the bid. | Since 90 days has lapsed since the bid was advertised, it is recommended that a re-advertisement be done.
Khethakanye Consultancy | Training on Occupational Health and safety for fifty two EPWP labourers | XDM-OHS/11/12 |  |  |  | 2012-03-16 | 2012-03-26 | 2012-04-19 | 4000/4055/100 | 192198.84 | 192198.84 | 0 | 100% complete
Khethakanye Consultancy | Parafin safety awareness | XDM-PSA11/12 |  |  |  | 2011-08-30 | 2011-09-07 | 2011-09-16 | 4000/4034/100 | 194960.2 | 194960.2 | 0 | 100% completed
O2 Information Technology | Launching of satelite broadband | XDM: BRDBND-Launch 01/11/12 |  |  |  | 2011-12-02 | 2011-12-12 | 2011-12-14 | 4000/4206/150 | 195000 | 195000 | 0 | 100% completed
Amogelang Thato | Delegation of powers | XDM-DOP/11/12 |  |  |  | 2012-02-27 | 2012-03-06 | 2012-03-19 | 4000/4490/050 | 199588 | 195988 | 3600 | In progress
Moba Consultancy Services | Employee Wellness awareness and training | XDM-EW 01/11 |  |  |  | 2011-08-12 | 2011-09-01 | 2011-09-16 | 4000/4017/150 | 259165 | 259165 | 0 | 100% completed
Khethakanye Consultancy | Employee Wellness awareness and training | XDM-EW02/11/12 |  |  |  | 2012-03-16 | 2012-04-05 | 2012-04-19 | 4000/4017/150 | 287930.47 | 287930.47 | 0 | 100% Complete
Thewo Development & Consulting Engineers | Environmental Management Framework | XDM-EMF 01/11 |  |  |  | 2011-07-07 | 2012-07-27 | 2011-11-17 | 4000/4088/100 | 332310 |  | 332310 | Progress report to be continuously provided by the user department | That Ms. Tindleni provide the SCM unit with a progress report
Venture Ink Trading | Supply of office furniture | XDM-FURNITURE 10/11/12 |  |  |  | 2011-07-14 | 2011-08-03 | 2011-08-25 | 6400/4415/200;100 | 411559.25 | 411559.25 | 0 | 100% completed
Khethakanye Consultancy | Disaster Management Framework | XDM-DMP 10/11 |  |  |  | 2011-06-22 | 2011-07-12 | 2011-07-26 | 4000/4034/100 | 481471.2 | 481471.2 | 0 | 100% complete
Makomota Investment Holdings PTY (ltd) | Support on the implementation of SCM policy and procedures as well as the entire BTO, daily, monthly and annual operations and processes | SCM/MAC 01/11/12 |  |  |  | 2011-10-24 | 2011-11-11 | 2011-11-17 | 4000/4098/200 | 586530 | 392996.76 | 193533.24 | 100% complete | That the Budget and Reporting unit provide the SCM unit with a progress report
Matsapa Trading 631 | Re- advertisement: Supply and installation of aircondtioners | XDM-AIRCONS01/11/12 |  |  |  | 2012-06-01 | 2012-06-21 | 2012-06-29 | 6400/4415/150 | 691576.44 | 621150.24 | 70426.2 | In progress
OXY Trading 279 T/A MBV Construction Group | Tiling,carpets and blinds for Xhariep District Municipality | XDM-RENOV 01/11/12 |  |  |  | 2011-09-08 | 2011-09-29 | 2011-11-17 | 3370/3375/150 | 1073898.99 | 1401496.5 | -327597.51 | 100% complete | That the Corporate Department provide the SCM unit with a progress report
Stimer Construction | RE-AVDERTISEMENT: Supply of shoes, belts and purse machinery and materials | XDM;SOMAC &MAT01/11/12 |  |  |  | 2012-02-01 | 2012-02-21 | 2012-03-23 | 4000/4046/100 | 2096674.91 | 1362838.69 | 733836.22 | 100% Complete
Stimer Construction | Supply and installation of security services at XDM | [7 empty] | 4000/4900/150 | 2516689.55 |  | 2516689.55 | In progress
Stimer Construction & Projects | Provision and installation of security system at Naledi Local Municipality | XDM-LOC-CCTV/11/12 |  |  |  | 2012-03-16 | 2012-04-05 | 2012-04-19 | 3200/3200/150 | 2724944.88 |  | 2724944.88 | In progress
| IT support at naledi | XDM-NLM-ITS11/12 |  |  |  |  | 2012-05-21 |  | 3200/3400/150 |  |  |  | In progress
| Supply of business cards | XDM-BC01/11/12 |  |  |  | 2012-05-16 | 2012-05-28 | [5 empty] | In progress
| Workshop on municipal financial oversight and the establishment of municipal public accounts committees; Re-advertisement | XDM-MPAC11/12 |  |  |  | 2012-03-12 | 2012-03-20 |  | 4000/4017/150 |  |  |  | In progress
Nala Consulting | Development of Integrated Transport Plan for XDM | XDM-ITP11/12 |  |  |  | 2012-03-16 | 2012-04-05 |  | Not budgeted for |  |  |  | In progress
| Valuation and auction of municipal obsolete assets | XDM-AUC11/12 |  |  |  | 2012-06-01 | 2012-07-21 | [5 empty] | In progress
| Tourism grading workshop | [5 empty] | 2012-07-22 | [5 empty] | In progress
L2 Consulting | Microsoft volume lisencing | XDM-MVL/11/12 |  |  |  | 2012-06-01 | 2012-07-20 |  | 4000/4491/150 | 510000 | 0 | 0 | In progress
| Document Management System | XDM-DMS11/12 |  |  |  | 2012-06-01 | 2012-07-20
Makomota Investment Holdings PTY (ltd) | GRAP compliant AFS | XDM-AFS/11/12 |  |  |  | 2012-06-14 | 2012-07-03 | 2012-07-05 |  | 549423
Compiled by: |  | Reviewed by | [6 empty] | Approved by
Ms.R. Kholong |  | Mr. S.J. Matobako | [6 empty] | Mr.E.N. Mokhesuoe
Note on C7: serutla: -

## Commitments 11-12 (hidden)
COMMITMENTS
COMPANY NAME | PROJECT NAME | REFERENCE | DATE OF APPOINTMENT | CONTRACT AMOUNT | AMOUNT PAID | OUTSTANDING AMOUNT
Thewo Development & Consulting Engineers | Environmental Management Framework | XDM-EMF 01/11 | 2011-11-17 | 332310 |  | 332310
Stimer Construction | RE-AVDERTISEMENT: Supply of shoes, belts and purse machinery and materials | XDM;SOMAC &MAT01/11/12 | 2012-03-23 | 2096674.91 | 1362838.69 | 733836.22
Amogelang Thato | Delegation of powers | XDM-DOP/11/12 | 2012-03-19 | 199588 | 195988 | 3600
Stimer Construction & Projects | Provision and installation of security system at Naledi Local Municipality | XDM-LOC-CCTV/11/12 | 2012-04-19 | 2724944.88 | 1634966.67 | 1089978.21
Makomota Investment Holdings | Support on the implementation of SCM policy and procedures as well as the entire BTO, daily, monthly and annual operations and processes | SCM/MAC 01/11/12 | 2012-11-17 | 586530 | 392996.76 | 193533.24
Matsapa Trading 631 | Re- advertisement: Supply and installation of aircondtioners | XDM-AIRCONS01/11/12 | 2012-06-29 | 691576.44 | 0 | 691576.44
Stimer Construction & Projects | Provision and installation of security system at Xhariep District Municipality |  | 2011-12-01 | 2879312.85 | 2879312.85 | 0

## Contract Register
2014/2015 CONTRACT REGISTER FOR JUNE 2015
Name of Company | Name of Project | Ref No | Advert Date | Tender Closing Date | Appointment Date | Date the contract was signed | Duration of the contract | Contract Expiry date | Contract Amount | Amount paid in 2013/2014 | Amount paid in 2014/15 | Outstanding Balance | Remarks from the project steering Committee | Stage of Completion and Comments | Amendment of the contract | Penalties under the contract | Penalties paid by the municipality | Comment
Morar Incorporated | Compilation of annual financial statements | XDM-AFS 13/14 | 2014-06-13 | 2014-07-02 | 2014-07-22 | N/A | 1 Month | 2014-07-21 | 491300 |  | 491300 | 0 | N/A | complete | N/A | None | N/A | N/A
Royal Haskoning DHV | Rural roads asset management grant | XDM-RAMS 12/13 | 2013-05-06 | 2013-05-23 | 2013-07-16 |  | 24 Months | 2015-06-30 | 2427174 | 1268934.38 | 1531233.21 | 320766.79 | N/A | contract came to an end | N/A | None | N/A | contract came to an end at 30 June 2015( balance outstanding per the system)
O2 Information Technology | Website Maintanance | XDM-WEBSITE | N/A | N/A | N/A | Monthly | Monthly | Monthly | 28000 |  | 226258.06 | 0 | N/A | Complete_30/06/2015 | N/A | N/A | N/A | An amount of 56 000.00 was paid back on the 4th of July 2015 because it was reversed by the bank as the account was closed.
Roseta Trading CC | Mentorship for Shoe Production | XDM-MENTOR 13/14 | N/A | N/A | 2014-08-07 | 2014-08-07 | 3 months | 2014-10-27 | 195000 | 0 | 195000 | 0 | N/A | Complete | N/A | N/A | N/A
Roseta Trading CC | Lease of machinery for shoe production | XDM-LEASE 13/14 | 2014-02-28 | 2014-03-10 | 2014-04-15 | 2014-05-01 | 6 Months |  | 32400 |  | 32400 | 0 | N/A | Complete | N/A | None | N/A | N/A
Roseta Trading CC | Mentorship for Shoe Production | XDM-MENTOR 13/14 | 2013-08-16 | 2013-09-04 | 2013-11-29 | 2014-01-28 | 6 Months | 2014-07-30 | 390000 | 330000 | 60000 | 0 | N/A | Complete | N/A | None | N/A | N/A
Procon IT Solution | Supply of internet services | XDM-INTERNET 13/14 | 2014-01-31 | 2014-02-19 | 2014-04-15 | 2014-05-21 | 12 months | 2015-04-30 | 54000 |  | 51000 | 0 | N/A | contract came to an end | N/A | None | N/A | contract came to an end at 30 April 2015 and renewed on a month to month basis until June 2015. Pro rata payment was made during first month of appointment(There were 342 that was charged for internet recap amounting to R1710.00. This amount is amount is not included in the total amount paid)
Procon IT Solution | back up service | XDM-BACK-UP 13/14 |  |  |  |  | Monthly |  | 3450 |  | 4500 | 4500 | [5 empty] | Outstanding invoices for June
Procon IT Solution | Supply of internet services | XDM-INTERNET 13/15 | N/A | N/A | N/A | 2015-05-01 | Monthly |  | 4500 |  | 3450 | 3450 | [5 empty] | Outstanding invoices for June
Njunga Construction and Projects | Cleaning and greening of cemetries for Kopanong and Letsemeng Local Municipalities | XDM-CEMETRIES/13/14 | 2014-08-04 | 2014-08-21 | 2014-09-01 | 2014-09-01 | 2 Months | 2014-10-31 | 450000 |  | 450000 | 0 | N/A | Complete | N/A | N/A | N/A | N/A
Procon IT Solution | Web monitor, lan guard and antivirus | XDM-WEB 13/14 | 2014-05-19 | 2014-05-17 | 2014-06-18 | 2014-07-01 | 12 months | 2015-06-30 | 19402 |  | 19402 | 0 | N/A | Complete | N/A | None | N/A | N/A
Procon IT Solution | Supply of back-up services | XDM-BACK-UP 13/14 | 2014-01-31 | 2014-02-19 | 2014-04-15 | 2014-05-01 | 12 months | 2015-04-30 | 41400 |  | 41400 | 41400 | N/A | Complete | N/A | None | N/A | contract came to an end at 30 April 2015 and renewed on a month to month basis until June 2015.
Free State Travel | Travel Agency | XDM Travel 12/13 | 2013-07-26 | 2013-08-14 | 2014-02-10 | 2014-05-12 | 12 months | 2015-05-11 | 10% Commission |  | 701162 | 85543.19 | N/A | ongoing | N/A | None | N/A | contract came to an end at 30 April 2015 and renewed on a month to month basis until June 2015.
Lateral Unison | Insurance of municipal assets | [5 empty] | 12 months | 2015-06-30 |  |  | 513807.21 |  | N/A | N/A | N/A | None | N/A | the amount is the annual premium
Digicoms | Telephone systems | [5 empty] | Monthly | Monthly | charged per usage |  | 279855.92 | [6 empty] | amount paid depends on the usage
Wolters Kluwer | Supply and installation of audit software | XDM-AUDIT-SOFTWARE 13/14 | 2014-05-02 | 2014-05-13 | 2014-06-18 | N/A | 12 months | 2015-06-17 | 158773.11 |  | 147189.09 | 11584.02 | N/A | N/A | N/A | N/A | N/A | N/A
Mission Point Trading_Review of I | Review of IWMP | XDM-IWMP 13/14 | 2015-01-09 | 2015-01-28 | 2015-04-08 | 2015-01-09 | 2015-01-28 | 2015-04-08 | 290928 |  | 290928 | 0 | N/A | Complete | N/A | N/A | N/A | N/A
Multitech | Finance lease of machinery | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 77465.12(Including VAT) |  | 920156.92
Multitech | repairs and maintanance | N/A | N/A | N/A | N/A | N/A | N/A | N/A | charged per usage |  | 538268.79
Thepa Trading | Supply and maintanance of printers | XDM-PRINTERS 14/15 | 2015-03-24 | 2015-04-10 | 2015-05-11 | 2015-06-01 | 36 months | 2018-08-31 | 1161390.86 |  | 0 | 1161390.86 | N/A | N/A | N/A | N/A | N/A | 32260.86 per month
Business Connexion | Microsoft volume licensing. | XDM-MVL 14/15 | N/A | 2014-07-30 | 2014-10-24 | 2014-08-13 | annual fee |  | 263491.39 |  | 0 | 263491.39 | N/A | Complete | N/A | N/A | N/A | N/A
.36+

## For management (hidden)
Status on tenders 2011/2012
Name of Comany | Name of Project | Bid number | Advert date | Tender closing | Appointment date | Vote Number | Contract Amount | Amount paid | Outstanding balance | Stage of completion and comments | Recommendation
Moba Consultancy Services | Employee Wellness awareness and training | XDM-EW 01/11 | 2011-08-12 | 2011-09-01 | 2011-09-16 | 4000/4017/150 | 259165 | 259165 | 0 | 100% completed
Khethakanye Consultancy | Employee Wellness awareness and training | XDM-EW02/11/12 | 2012-03-16 | 2012-04-05 | 2012-04-19 | 4000/4017/150 | 287930.47 | 287930.47 | 0 | 100% Complete
Thewo Development & Consulting Engineers | Environmental Management Framework | XDM-EMF 01/11 | 2011-07-07 | 2012-07-27 | 2011-11-17 | 4000/4088/100 | 332310 |  | 332310 | Progress report to be continuously provided by the user department | That Ms. Tindleni provide the SCM unit with a progress report
Venture Ink Trading | Supply of office furniture | XDM-FURNITURE 10/11/12 | 2011-07-14 | 2011-08-03 | 2011-08-25 | 6400/4415/200;100 | 411559.25 | 411559.25 | 0 | 100% completed
Khethakanye Consultancy | Disaster Management Framework | XDM-DMP 10/11 | 2011-06-22 | 2011-07-12 | 2011-07-26 | 4000/4034/100 | 481471.2 | 481471.2 | 0 | 100% complete
Makomota Investment Holdings PTY (ltd) | Support on the implementation of SCM policy and procedures as well as the entire BTO, daily, monthly and annual operations and processes | SCM/MAC 01/11/12 | 2011-10-24 | 2011-11-11 | 2011-11-17 | 4000/4098/200 | 586530 | 586530 | 0 | 100% complete
Matsapa Trading 631 | Re- advertisement: Supply and installation of aircondtioners | XDM-AIRCONS01/11/12 | 2012-06-01 | 2012-06-21 | 2012-06-29 | 6400/4415/150 | 691576.44 | 720724.04 | -29147.6 | In progress | The negative amount of R29,147.60 represent a variation which occured during the execution of the project.
OXY Trading 279 T/A MBV Construction Group | Tiling,carpets and blinds for Xhariep District Municipality | XDM-RENOV 01/11/12 | 2011-09-08 | 2011-09-29 | 2011-11-17 | 3370/3375/150 | 1073898.99 | 1401496.5 | -327597.51 | 100% complete
Stimer Construction | RE-AVDERTISEMENT: Supply of shoes, belts and purse machinery and materials | XDM;SOMAC &MAT01/11/12 | 2012-02-01 | 2012-02-21 | 2012-03-23 | 4000/4046/100 | 2096674.91 | 1362838.69 | 733836.22 | 100% Complete
Stimer Construction | Supply and installation of security services at XDM | N/A | N/A | N/A | N/A | 4000/4900/150 | 2516689.55 | 2879312.85 | -362623.3 | In progress
Stimer Construction & Projects | Provision and installation of security system at Naledi Local Municipality | XDM-LOC-CCTV/11/12 | 2012-03-16 | 2012-04-05 | 2012-04-19 | 3200/3200/150 | 2724944.88 | 2724944.88 | 0 | complete
| Valuation and auction of municipal obsolete assets | XDM-AUC11/12 | 2012-06-01 | 2012-07-21 | [5 empty] | Evaluation still to sit
L2 Consulting | Microsoft volume lisencing | XDM-MVL/11/12 | 2012-06-01 | 2012-07-20 |  | 4000/4491/150 | 510000 | 225000 | 285000 | In progress

## Commitments 12-13 (hidden)
COMMITMENTS 2012/2013
COMPANY NAME | PROJECT NAME | DATE OF APPOINTMENT | CONTRACT AMOUNT | AMOUNT PAID | OUTSTANDING AMOUNT
LQ Technologies | Upgrading of IT system at Xhariep District Municipality | 2012-10-31 | 896952 | 0 | 896952
Njunga Construction and project | Upgrading of IT system at Letsemeng Local Municipality | 2012-10-31 | 957000 | 0 | 957000
Stimer construction and projects | Provision and installation of security system at Letsemeng Local Municipality | 2012-10-31 | 2820523.59 | 0 | 2820523.59
Lekhetho and sons | Supply of two blade servers and one sharepoint server for XDM | 2012-10-31 | 332880 | 0 | 332880
Stimer construction and projects | Installation of wireless alarm system | 2012-10-31 | 676933 | 0 | 676933
Kissmetics General Trading | Supply of protective clothing for XDM | 2012-10-31 | 80780 | 0 | 80780
5765068.59

## Sheet2 (hidden)
Project name | Contract/Projected amount | Amount paid | Oustanding amount | Decemeber | January | February | March | April | May | June | Notes
Microsoft volume lisencing | 510000 | 510000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
GRAP compliant AFS | 549423 | 391986.77 | 157436.23 | 157436.23 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Printing of annual budget | 91487.2 | 0 | 91487.2 | 91487.2 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Supply of stationery | 193800 | 193800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Printing of IDP professional IDP bookelets | 175000 | 0 | 175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Document Management System | 640000 | 640000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Supply of cleaning materials | 88507.25 | 88507.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Upgrading of electricity | 46274.74 | 0 | 46274.74 | 46274.74 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Upgrading of IT system at Xhariep District Municipality | 896952 | 538171.2 | 358780.8 | 358780.8 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Upgrading of IT system at Letsemeng Local Municipality | 957000 | 808500 | 148500 | 148500 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Provision and installation of security system at Letsemeng Local Municipality | 2820523.59 | 1376854.4 | 1443669.19 | 484223.06 | 484223.06 | 484223.06 | 0 | 0 | 0 | 0 | A1
Supply of two blade servers and one sharepoint server for XDM | 332880 | 332880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Installation of wireless alarm system | 676933 | 0 | 676933 | 676933 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Supply of protective clothing for XDM | 80780 | 80780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Servicing of old aircondtioners | 45030 | 45030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Facilitation of public participation summit | 189000 | 189000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | A1
Procurement of yellow fleet | 15000000 | 0 | 15000000 | 0 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | A3
Renovations of the office of the Excecutive Mayor | 30000 | 0 | 30000 | 0 | 15000 | 15000 | 0 | 0 | 0 | 0 | A1
Training of EPWP labourers | 200000 | 0 | 200000 | 0 | 100000 | 100000 | 0 | 0 | 0 | 0 | A2
Procument of new mayoral car | 900000 | 0 | 900000 | 0 | 900000 | 0 | 0 | 0 | 0 | 0 | A3
Sewer network | 3608171.82 | 2622846.76 | 985325.06 | 140760.72 | 140760.72 | 140760.72 | 140760.72 | 140760.72 | 140760.72 | 140760.72 | A1
Internal Streets | 3122094.88 | 2865231.24 | 256863.64 | 113000 | 23977.27 | 23977.27 | 23977.27 | 23977.27 | 23977.27 | 23977.27 | A1
Sewer outfall | 1810057.8 | 1736484.79 | 73573.01 | 73573.01 | 0 | 0 | 0 | 0 | 0 |  | A1
TOTAL |  |  |  | 2290968.76 | 4163961.05 | 3263961.05 | 2664737.99 | 2664737.99 | 2664737.99 | 2664737.99
A1- Projects that are already in progress
A2- Advertised but not yet awarded
A3- Not advertised, not budgeted for

## Sheet3 (hidden)
Sizwe Ntsaluba and Gobodo Advisory | IT Audit | XDM-IT AUDIT 12/12 | 2013-04-29 | 2013-05-16 | 2013-07-30 | 292068 | 292068 | Sizwe Ntsaluba Gobobo and Advisory must submit their projecr implementation paln
Makomota Investment Holdings PTY (ltd) | Compilation of annual financial statements | XDM-AFS 12/13 | 2013-05-06 | 2013-05-23 | 2013-07-16 | 670000 | 670000 | Makomota Investment must submit their project implementation paln
Royal Haskoning DHV | Rural roads asset management grant | XDM-RAMS 12/13 | 2013-05-06 | 2013-05-23 | 2013-07-16 | 2427174 | 2427174 | Royal Haskoning must submit their project implementation paln