2023-2024

XHARIEP DISTRICT MUNICIPAITY

(FINAL)

# CONTENTS

CONTENTS	2

PROPOSED REVISED ANNUAL REPORT TEMPLATE	5

CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY	6

COMPONENT A: MAYOR’S FOREWORD	6

COMPONENT B: EXECUTIVE SUMMARY	7

1.1.	MUNICIPAL MANAGER’S OVERVIEW	7

1.1.	MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW	8

1.2.	FINANCIAL HEALTH OVERVIEW	10

1.3.	AUDITOR GENERAL REPORT	12

1.4.	STATUTORY ANNUAL REPORT PROCESS	13

CHAPTER 2 – GOVERNANCE	14

COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE	14

2.1	POLITICAL GOVERNANCE	15

2.2	ADMINISTRATIVE GOVERNANCE	18

COMPONENT B: INTERGOVERNMENTAL RELATIONS	19

2.3	INTERGOVERNMENTAL RELATIONS	19

COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION	20

2.4	PUBLIC MEETINGS	21

2.5	IDP PARTICIPATION AND ALIGNMENT	23

COMPONENT D: CORPORATE GOVERNANCE	24

2.5	RISK MANAGEMENT	25

2.7	ANTI-CORRUPTION AND FRAUD	25

2.8	SUPPLY CHAIN MANAGEMENT	26

2.10	WEBSITES	27

CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)	28

COMPONENT A: BASIC SERVICES	28

3.11	LOCAL ECONOMIC DEVELOPMENT (INCLUDING TOURISM AND MARKET PLACES)	29

3.64	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC	32

3.67	DISASTER MANAGEMENT	34

COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES	36

3.69	EXECUTIVE AND COUNCIL	36

3.71	HUMAN RESOURCE SERVICES	40

3.72	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES	43

COMPONENT K: ORGANISATIONAL PERFORMANCE SCORECARD	45

CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE	79

(PERFORMANCE REPORT PART II)	79

COMPONENT A: INTRODUCTION TO THE MUNICIPAL PERSONNEL	80

4.1	EMPLOYEE TOTALS, TURNOVER AND VACANCIES	80

COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE	81

4.3	INJURIES, SICKNESS AND SUSPENSIONS	81

4.5	SKILLS DEVELOPMENT AND TRAININg	84

COMPONENT D: OTHER FINANCIAL MATTERS	87

5.12	SUPPLY CHAIN MANAGEMENT	87

CHAPTER 6 – AUDITOR GENERAL AUDIT FINDINGS	88

COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS 2023-2024	88

COMPONENT B: AUDITOR-GENERAL OPINION 2023-2024 (CURRENT YEAR)	89

Report of the auditor-general to the Free State Legislature and the council on the Xhariep District Municipality	89

Report on the audit of the financial statementsOpinion	89

Report of the auditor-general to the Free State Provincial Legislature and the council on the Xhariep district Municipality	89

Annexure to the auditor’s report	99

GLOSSARY	103

APPENDICES	106

APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE	106

APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES	108

APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY	109

APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE 2023-2024	111

APPENDIX H – LONG TERM CONTRACTS (tubi)	114

APPENDIX I – MUNICIPAL ENTITY/ SERVICE PROVIDER PERFORMANCE SCHEDULE	116

APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS	118

APPENDIX K (ii): REVENUE COLLECTION PERFORMANCE BY SOURCE	120

APPENDIX T – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT	121

VOLUME II: ANNUAL FINANCIAL STATEMENTS	122

AUDIT ACTION PLAN…………………………………………………………………………………………………………………………..…….191

# PROPOSED REVISED ANNUAL REPORT TEMPLATE

The purpose of this revised Annual Report template is to address the need expressed by a number of municipalities for assistance in the preparation and development of improved content and quality of Municipal Annual Reports. It replaces a template dating back to August 2003.

This template gives effect to the legal framework requirement, concepts and principals espoused in the White Paper on Local Government and Improving Government Performance.  It reflects the ethos of public accountability.  The content gives effect to information required for better monitoring and evaluation of government programmes in support of policy decision making. The template provides an improved overview of municipal affairs by combining the performance report data required under Municipal Systems Act Section 46 with annual report data referred to in that Act and in the MFMA.

The revised template makes its contribution by forging linkages with the Integrated Development Plan, Service Delivery and Budget Implementation Plan, Budget Reforms, In-year Reports, Annual Financial Statements and Performance Management information in municipalities.  This coverage and coherence is achieved by the use of interlocking processes and formats.

The revised template relates to the Medium Term Strategic Framework particularly through the IDP strategic objectives; cross cutting nature of services offered by different spheres of government, municipal service outcome indicators; and the contextual material as set out in Chapters 3, 4 & 5.  It also provides information on good management practice in Chapter 4; risk management in Chapter 2; and Supply Chain Management in Chapter 5; and addresses the Auditor-General’s Report, dealing with Financial and Performance Management arrangements in Chapter 6.  This opens up greater possibilities for financial and non-financial comparisons between municipalities and improved value for money.

The revised template provides information on probity, including: anti-corruption strategies; disclosure of financial interests by officials and councillors; disclosure of grants by external parties, disclosure of loans and grants by municipalities.  The appendices talk to greater detail including disaggregated information on municipal wards, among others.

Notes are included throughout the format to assist the compiler to understand the various information requirements. Once the draft has been finalised, training will be provided to facilitate the implementation of this initiative, and separate additional guidance may be issued if necessary.

We wish to express our gratitude to the members of the Annual Report Reference Group, consisting of national, provincial and municipal officials for their inputs and support throughout the development of this document.

MFMA Implementation Unit, National Treasury                                                                                           October 2009

# CHAPTER 1 – MAYOR’S FOREWORD AND EXECUTIVE SUMMARY

## COMPONENT A: MAYOR’S FOREWORD

Dear Esteemed Residents of Xhariep District Municipality,

It is with great pride and a profound sense of responsibility that I present to you the Annual Report for the 2023-2024 financial year. This report serves as a testament to our unwavering commitment to transparency, accountability, and the continuous improvement of service delivery within our community. As your Executive Mayor, I am acutely aware of the trust you have placed in us, and it is our duty to ensure that we honour that trust through diligent governance and effective leadership.

Our municipality, inaugurated on 26 November 2021, is a vibrant tapestry woven from the diverse voices of our residents. With a Council comprised of dedicated members from the African National Congress, the Democratic Alliance, and the Economic Freedom Fighters, we embody a spirit of collaboration and inclusivity that is essential for the progress of our district. Together, we have navigated the complexities of governance, ensuring that every decision made reflects the aspirations and needs of our constituents.

The past year has been marked by significant achievements and challenges alike. Guided by our Strategic Plan and the Integrated Development Plan (IDP), we have allocated resources to projects that enhance the quality of life for all residents. Our commitment to maintaining quality service delivery is unwavering, and I am proud to report that we have made substantial strides in addressing the needs of our community.

As we reflect on our accomplishments, we must also acknowledge the challenges that lie ahead. The road to sustainable development requires resilience, innovation, and a steadfast dedication to our shared vision. We are committed to fostering a culture of accountability and integrity, ensuring that our actions are always in the best interest of our residents.

I extend my heartfelt gratitude to the members of the Municipal Council, our dedicated municipal staff, and the citizens of Xhariep District Municipality. Your active participation and engagement are vital to our success. Together, we can build a future that leaves no one behind, as espoused by our President, Mr. Cyril Ramaphosa.

As we embrace the future, let us remain united in our efforts to create a prosperous, inclusive, and sustainable district for all. I invite you to explore this report, which not only highlights our achievements but also outlines our vision for the years to come.

Yours in local government

……………………………………………..

NI Mehlomakulu

T1.0.1

# COMPONENT B: EXECUTIVE SUMMARY

## MUNICIPAL MANAGER’S OVERVIEW

It is with considerable pride and a profound sense of duty that I submit the Annual Report for the Xhariep District Municipality for the fiscal year 2023-2024. This document captures our steadfast commitment to serving our communities, promoting sustainable development, and ensuring the utmost standards of governance and accountability.

Throughout the preceding year, we encountered numerous challenges; nevertheless, we have emerged with resilience, guided by our strategic vision and the frameworks delineated in our Integrated Development Plan (IDP). Our dedicated team has exerted considerable effort to implement pivotal projects and initiatives that correspond with our Key Performance Areas (KPAs), thereby ensuring that we not only fulfil but surpass the expectations of our residents.

The report outlines our accomplishments across various sectors, wherein we have prioritized the needs of our citizenry by actively engaging them in the decision-making processes through the IDP and Budget public participation forums. This collaborative methodology has reinforced the social contract between the municipality and its constituents, enabling us to better comprehend and respond to their aspirations.

Our financial stability remains a fundamental aspect of our operations, and we are devoted to transparent and responsible management of public resources. The Auditor-General’s Report, which is incorporated within this document, reflects our commitment to upholding elevated standards of financial integrity and performance management. We acknowledge that accountability is of utmost significance, and we are continually striving to enhance our systems and processes to ensure adherence to all legislative mandates.

As we anticipate the future, we maintain our focus on constructing a prosperous and inclusive district. Our initiatives concerning job creation, skills development, and infrastructure enhancement are meticulously designed to empower our communities and invigorate economic growth. We also pledge our commitment to promoting good governance practices, risk management, and anti-corruption strategies, as guided by principles and ethics.

I would like to reiterate my gratitude in the compilation of this report to our dedicated staff and all stakeholders for their invaluable contributions and support throughout this endeavor. Your unwavering commitment to excellence and service delivery has been instrumental in our successes.

In conclusion, as it is the norm, I invite all stakeholders to engage with this report as we continue our journey toward a vibrant and sustainable future for the Xhariep Municipality.

Together, let us collaborate as we strive to enhance the quality of life for all our residents

Yours sincerely,

………………………

LY Moletsane 									                              T1.1.1 Municipal Manager

### MUNICIPAL FUNCTIONS, POPULATION AND ENVIRONMENTAL OVERVIEW

Population Details

In 2011 the Xhariep district total population was 121 945 and in 2022 the district has increased its population size to 131 901 which amount to 8.2% and is ranked number five in the Free State Province. The female population has increased to 68 657 compared to males at 63 244. Source: Statistics SA Census Survey 2022 T1.2.2

INTRODUCTION TO BACKGROUND DATA

Out of 16 district functions, Xhariep district municipality is performing 6(37.5%) of these functions. Xhariep District is the smallest compared to the others within Free State Province with about 5.2% share of the total provincial population. With 125 884 people, the Xhariep District Municipality housed 0.2% of South Africa's total population in 2017.  Compared to Free State's average annual growth rate (0.62%), the growth rate in Xhariep's population at -0.73% was significant lower than that of the province

T 1.2.1

The Census Survey Report of 2022 is a large‐scale survey which happened in between Censuses 2011 and 2022. The main objective of the survey is to provide population and household statistics at municipal level to all stakeholders including the government and private sector to support planning and decision‐making.

It is concerning that the number of households in Xhariep District decreased by around 2 815 since 2001 and it is ranked number five (5) in the entire province. In 2022 the average household size was 3.7

| Natural Resources |  |
| --- | --- |
| Major Natural Resource | Relevance to Community |
| Water (Gariep Dam) | Supply of water to households and generation of electricity. |
| Diamonds(Jagersfontein and Koffiefontein) | Job creation, Revenue enhancement, Economic development, human settlement. |
| Uranium (Edenburg) | Job creation, Revenue enhance, Economic development, human settlement |
| Land | Job creation through farming and settlement of communities |
| Sun (Radiation energy) | Job creation through erection of solar hubs |
|  | T1.2.7 |

BACKGROUND DATA

Xhariep District forms the southern part of the Free State Province and is one of four district municipalities in the Free State. The municipality measures 34289 km sq. It is bordered by Tokologo Municipality in Lejweleputswa District to the north, Mangaung Metro and Mantsopa Municipality in Thabo Mofutsanyana District to the north-east. Other borders are with the Kingdom of Lesotho to the east, Ukhahlamba Municipality in Eastern Cape Province to the south, Pixley ka Seme Municipality in Northern Cape Province to the west and Frances Baard Municipality in Northern Cape Province to the north-west. Topographically the district is bordered for most of its eastern border by the Maluti and Drakensberg mountains. Hydrological the district is located between the Vaal River to the north, and Orange River to the south, with rivers within the district draining towards these rivers. Xhariep consists of three local municipal areas, with Letsemeng forming the north western section, Kopanong the middle section, Mohokare the south eastern section of the district

T1.2.8

### FINANCIAL HEALTH OVERVIEW

FINANCIAL OVERVIEW

The municipality is heavily dependent on grants with little revenue base, the government grants are from National and other spheres of government. This dependency puts a lot of pressure and strain on the municipality’s ability to finance both operating and capital expenditures.

The municipality’s structure does not respond to the core functions of the municipality due to cash flow challenges. Revenue strategies and performance of powers and functions of the municipality as stipulated in the municipal Structures Act will assist in the long term sustainability of the municipality.

T1.4.1

| Financial Overview - 2023/2024 |  |  |  |
| --- | --- | --- | --- |
|  |  |  | R' 000 |
| Details | Original budget | Adjustment Budget | Actual |
| Revenue |  |  |  |
| Grants | 87 712 000 | 132 414 000 | 89 691 583 |
| Rental of facilities | 167 000 | 263 000 | 695 911 |
| Interest Earned | 1 115 000 | 1 555 000 | 2 498 534 |
| Other Income | 88 000 | 88 000 | 123 918 |
| Public contributions donations and other transfers | 89 082 000 | 134 320 000 | 93 009 946 |
| Expenditure | (91 012 000) | (91 948 000) | (99 969 239) |
| Actuarial gains/losses | - | - | 148 268 |
| Surplus / Deficit | (1 930 000) | 42 372 000 | (6 811 025) |
|  |  |  | T1.4.2 |

| Operating Ratios |  |
| --- | --- |
| Detail | % |
| Employee Cost | 47% |
| Repairs & Maintenance | 1% |
| Finance Charges & Impairment | 2% |
|  | T1.4.3 |

COMMENT ON OPERATING RATIOS

Employee related costs (inclusive of councilor’s remuneration) constitutes 56% of the total expenditure and repairs and maintenance (1%) significantly lower than the 8% NT guide while finance charges and impairment are curbed lower at 3%.

T1.4.3

ORGANISATIONAL DEVELOPMENT PERFORMANCE

Organization Development (OD) is about improving performance at the individual, group, and Municipal organizational levels. It is about improving the organization's ability to effectively respond to changes in its external environment, and it’s about increasing internal capabilities by ensuring the Xhariep District Municipal structures, human resources systems, job designs, communication systems, and leadership/managerial processes fully harness human motivation and help people function to their full potential.

Done well, such improvement can be transformational—producing fundamental changes in the way individuals, groups, and organizations functions.

T1.5.1

### AUDITOR GENERAL REPORT

AUDITOR GENERAL REPORT 2022-2023 (Previous Financial Year)

The Municipality received an unqualified opinion. The following are the issues that lead to the audit outcome mentioned above:

- Material adjustments in the Annual Financial Statements;

- Material uncertainty relating to going concern;

- Irregular, Fruitless and Wasteful Expenditure;

-  Non investigation by MPAC

T 1.6.1

### STATUTORY ANNUAL REPORT PROCESS

| No. | Activity | Timeframe |
| --- | --- | --- |
| 1 | Consideration of next financial year’s Budget and IDP process plan. Except for the legislative content, the process plan should confirm in-year reporting formats to ensure that reporting and monitoring feeds seamlessly into the Annual Report process at the end of the Budget/IDP implementation period | July |
| 2 | Implementation and monitoring of approved Budget and IDP commences (In-year financial reporting). |  |
| 3 | Finalised the 4th quarter Report for previous financial year |  |
| 4 | Submit draft 2022-2023 Annual Report to Internal Audit |  |
| 5 | Audit/Performance committee considers draft Annual Report of municipality and entities (where relevant) | August |
| 6 | Mayor tables the unaudited Annual Report |  |
| 7 | Municipality submits draft Annual Report including consolidated annual financial statements and performance report to Auditor General |  |
| 8 | Annual Performance Report as submitted to Auditor General to be provided as input to the IDP Analysis Phase |  |
| 9 | Auditor General audits Annual Report including consolidated Annual Financial Statements and Performance data | September – October |
| 10 | Municipalities receive and start to address the Auditor General’s comments | January |
| 11 | Mayor tables Annual Report and audited Financial Statements to Council complete with the Auditor- General’s Report |  |
| 12 | Audited Annual Report is made public and representation is invited |  |
| 13 | Oversight Committee assesses Annual Report | February |
| 14 | Council adopts Oversight report | March |
| 15 | Oversight report is made public |  |
| 16 | Oversight report is submitted to relevant provincial councils |  |
| 17 | Commencement of draft Budget/ IDP finalisation for next financial year. Annual Report and Oversight Reports to be used as input | March |
| T1.7.1 |  |  |

# CHAPTER 2 – GOVERNANCE

INTRODUCTION TO GOVERNANCE

A municipal council is made up of the Municipal councilors who are democratically elected by registered votes within the municipal control. The Speaker is the chairperson of the Municipal Council which she presides over both Ordinary and Special Council meeting and she is also responsible for the discipline of the Municipal Councilors.

The Mayoral Committee consists of Municipal Councilors appointed by the Executive Mayor to serve in the Mayoral Committee. The number of Municipal Councilors on the Mayoral Committee is the minimum number that is needed for efficient and effective government.

The Executive Committee chaired by the Executive Mayor is responsible for the executive functions of the municipality.

T2.0.1

## COMPONENT A:  POLITICAL AND ADMINISTRATIVE GOVERNANCE

INTRODUCTION TO POLITICAL AND ADMINISTRATIVE GOVERNANCE

The current term of the Municipal Council was inaugurated on the 26 November 2021 and consists of sixteen (16) Councilors.

The Municipal Council consists of ten (10) Councilors who are representing the African National Congress, four (4) Councilors representing Democratic Alliance and two (2) Councillors representing the Economic Freedom Fighters. The Council was appointed or elected as follows: Executive Mayor (1), Speaker (1), 10 Councilors are appointed in three (3) Portfolio Committees which are headed by Members of the Mayoral Committee.

The Council has appointed 3 Councilors as MPAC Committee, The Municipal Manager as the Accounting Officer and the three Section 56 Managers were appointed by the Municipal Council of Xhariep District Municipality.

The Municipal Manager and the managers directly accountable to the Municipal Manager organize Administration in a manner that enables the Municipality to be responsive to the needs of the Community within its jurisdiction.

The Municipal Manager is accountable for the overall performance of the Municipality and she is accountable to the Executive Mayor and Council.

T2.1.0

### POLITICAL GOVERNANCE

INTRODUCTION TO POLITICAL GOVERNANCE

In line with the provisions of the Local Government: Municipal Structures Act 117 of 1998, Xhariep District Municipality has an established political component.

The main role of the political component is provided for in the Structures Act.

Section 80 of the Municipal Structures Act specifies procedures for establishing committees in Municipal council with an executive committee.

One of the functions of the portfolio committee is to process the report tabled before by the Departments before they could be forwarded to the Mayoral Committee and eventually to Council.

In terms of section 79 of the Structures Act, a Municipal Council has established Committees such, as MPAC, which is composed of three (3) Councilors necessary for the effective and efficient performance of its functions.

The Annual Report is prepared by the Performance Management Unit in collaboration with other departments after the Management has satisfied itself with the contents of the report it is then submitted to Council for noting. Subsequent to this process, the Annual report is submitted to Oversight Committee before the 31 March each year thereafter to Provincial Authorities.

The Internal Audit conducts audit throughout the year in terms of their audit plan and prepare Audit packs that are then submitted to Internal Audit Committees. After consideration of these reports the Audit Committee forwards its recommendations to Council for consideration.

T2.1.1

|  | POLITICAL STRUCTURE MAYOR Cllr NI Mehlomakulu Exercises powers delegated to the Mayor by Council or the Executive Committee |  |  |
| --- | --- | --- | --- |
|  | SPEAKER Cllr MA Shasha Presides at Council meetings and exercises powers delegated to the Speaker in terms of section 59 of the Local Government: Municipal Systems Act, Act 32 of 2000. |  |  |
|  | CHIEF WHIP N/A To ensure political mandates are executed MAYORAL COMMITTEE/ EXECUTIVE COMMITTEE Cllr AM Lebaka: Chairperson of the Budget and Treasury Committee Cllr NJ Garekoe: Chairperson of the Corporate Services Committee Cllr TD Mochechepa: Chairperson of Planning & Social Development |  |  |
|  | COMPOSITION OF COUNCIL AS AT 30 JUNE 2020 Political Party; Total; Directly elected; Seconded. African National Congress; 10; 6; 4. Democratic party; 4; 1; 3. Economic Freedom Fighters; 2; 1; 1. | T2.1.1 |

COUNCILLORS

The current Council structure consist of 16 Councillors, six (6) Councilors are directly elected and ten (10) are Seconded from the three local Municipalities which are, Kopanong, Letsemeng and Mohokare local Municipality. The six full time Councilors includes the Speaker, the Executive Mayor, the three (3) Mayoral Committee members and the Chairperson of the MPAC

Directly Elected Councilors or PR Councillor:

Cllr AM Shasha

Cllr NI Mehlomakulu

Cllr NJ Garekoe

Cllr AM Molai

Cllr AJJ Van Rensburg

Cllr TI Phatsoane

Seconded Councilors from Local Municipalities:

Kopanong Local Municipality	Letsemeng Local Municipality	      Mohokare Local Municipality

Cllr MG Mokheseng			Cllr AN November	                      Cllr TD Mochechepa

Cllr RW Van Wyk	                                                Cllr MM Potgieter		      Cllr IS Riddle

Cllr MV Malgas				Cllr AM Lebaka 			      Cllr NA Adoons

Cllr ME Lekoenea

T2.1.2

POLITICAL DECISION-TAKING

The Constitution gives both the legislative and executive powers of a Municipality to the Municipal Council. All Municipal Councilors are involved in taking decisions about how the Municipal Council is run, what services it should provide and how it should spend its money.

The Municipal Council is responsible for all the decisions of a Municipality but it may give specific functions to Committees as provided for in part 5; section 79 of the Structures Act. The Section 80 Committee sit as per schedule of Council meeting which is approved by Council to process the reports placed before them and make recommendations to the Mayoral Committee .The recommendation of the Section 80 may be changed by the Mayoral Committee or may be forwarded to the Council as they are. Then Council pronounces itself on the recommendations/ issues tabled before it. Where members share a different view on any matter under consideration, they vote on the matter, either by show of hands or through a secret ballot as stipulated in the standing rules and Orders. All decisions taken by Council are called resolutions which are implemented by the administration. In Xhariep District Municipality, these resolutions are taken to Departments through Execution list. Thereafter a Resolution register on resolutions implemented is developed to be presented in Council sitting.

T2.1.3

### ADMINISTRATIVE GOVERNANCE

INTRODUCTION TO ADMINISTRATIVE GOVERNANCE

The Municipal Manager is the accounting officer who accounts to the political head, Executive Mayor as well as Council.  He further provides guidance and advice to the political structures; also manage the administration of the institution.

The Director: Corporate Services administer the Department of Corporate Services and advice the Municipal Manager with issues relating to administration, human resources and information technology. The Chief Financial Officer administers Budget and treasury Office and advice the Municipal Manager on matters that relate to the finances of the Municipality. The Director: Planning and Social Development is responsible for the affairs of the Department of Planning and Social Development, advices and assists the Municipal Manager on all matters that relates to this department, i.e. planning, local economic development and municipal health services

T2.2.1

|  | TOP ADMINISTRATIVE STRUCTURE MUNICIPAL MANAGER Mr PV Litabe(Acting) Mrs Lebohang Yvonne Moletsane |  |
| --- | --- | --- |
|  | DIRECTOR: Corporate Services Mbulelo Aven Jafta Chief Financial Officer Mr PV Vincent Litabe Mr TS Matsiliso(Acting) Director: Planning & Social Development Mrs NY Augustus(Acting) Mr OA Kale |  |

## COMPONENT B: INTERGOVERNMENTAL RELATIONS

INTRODUCTION TO CO-OPERATIVE GOVERNANCE AND INTERGOVERNMENTAL RELATIONS

Intergovernmental relations are mainly informal, making the system flexible to respond to changing circumstances. The approach of the Act is therefore that it does not seek to govern intergovernmental relations in its totality but provides only the broad framework in terms of which spheres of government interact with one another.

T 2.3.0

### 2.3	INTERGOVERNMENTAL RELATIONS

PROVINCIAL INTERGOVERNMENTAL STRUCTURE

The District is part of the Premiers’ Coordinating Forum which is used to facilitate intergovernmental relations between the province and local government in the province. The District also participates in Provincial Forums which include Provincial IDP Forum, Provincial Energy Forum, Provincial AIDS Forum as well as South African Local Government Association (SALGA).

T2.3.2

DISTRICT INTERGOVERNMENTAL STRUCTURES

Meetings are held once in a quarter, whereby the District Municipality is responsible for ensuring the co-ordination of intergovernmental relations within the district municipality with local municipalities in the district. District Coordinating Forum: Forum consists of the Executive Mayor and 3 primary members of which is the Local Mayors.

Technical Support Committee

Forum consists of the District Municipal Manager and 3 primary members (Local Municipal Manager). The forum must meet at least once per year with service providers and other role players concerned with the development in the district to co-ordinate effective provision of services and planning in the district.

T2.3.4

## COMPONENT C: PUBLIC ACCOUNTABILITY AND PARTICIPATION

OVERVIEW OF PUBLIC ACCOUNTABILITY AND PARTICIPATION

The Municipality is committed to governing its area of its jurisdiction and its citizens in accordance with the spirit of the Constitution of the Republic of South Africa. This requires the Municipality to undertake community consultation, participation and empowerment as central features. The review of the institution’s current Integrated Development Plan included community participation through Stakeholder Engagements and public participation meetings. Through such measures, the communities are able to provide input on their priorities for the period under review. Some benefits include building and strengthening partnerships with various organisation from communities and broader civil society to establish a people’s contract in ensuring that citizen participation and representative democracy are combined to promote people-centered and people-driven development and governance.

T 2.4.0

### PUBLIC MEETINGS

COMMUNICATION, PARTICIPATION AND FORUMS The Xhariep District Municipality has a functional Communication Unit. The Communication Unit is a strategic component within the municipality that cut across all departments and units including the public. The Communication Unit also ensures that communication is well coordinated, effectively managed and responsive to the diverse information needs of the people. To fulfill this mammoth task, the communication unit has established the following mechanism, namely; - District Communicators Forum - Periodic update of the municipal website - Quarterly newsletter - Council notices The council meetings are opened to the public; this is to ensure that the public is informed and council businesses are at the public domain. T2.4.1

| Public Meetings |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Nature and purpose of meeting | Date of events | Number of Participating Municipal Councilors | Number of Participating Municipal Administrators | Number of Community members attending |  |
| IDP/Budget public participation | 18 April 2023 | 10 | 13 | 17 |  |
| IDP/Budget public participation | 19 April 2023 | 5 | 7 | 16 |  |
| IDP/Budget public participation | 26 April 2023 | 3 | 12 | 22 |  |
| T2.4.3 |  |  |  |  |  |

COMMENT ON THE EFFECTIVENESS OF THE PUBLIC MEETINGS HELD

Some of the benefits of public meetings include community being part of the decision-making process and, as result, minimizing community protests and civil unrests. The other benefit is that community will take ownership of development within their environment and have a sense of belonging.

T2.4.3.1

### 2.5	IDP PARTICIPATION AND ALIGNMENT

| IDP Participation and Alignment Criteria* | Yes/No |
| --- | --- |
| Does the municipality have impact, outcome, input, output indicators? | Yes |
| Does the IDP have priorities, objectives, KPIs, development strategies? | Yes |
| Does the IDP have multi-year targets? | Yes |
| Are the above aligned and can they calculate into a score? | Yes |
| Does the budget align directly to the KPIs in the strategic plan? | Yes |
| Do the IDP KPIs align to the Section 57 Managers | Yes |
| Do the IDP KPIs lead to functional area KPIs as per the SDBIP? | Yes |
| Do the IDP KPIs align with the provincial KPIs on the 12 Outcomes | Yes |
| Were the indicators communicated to the public? | Yes |
| Were the four quarter aligned reports submitted within stipulated time frames? | No |
| * Section 26 Municipal Systems Act 2000 | T2.5.1 |

## COMPONENT D: CORPORATE GOVERNANCE

OVERVIEW OF CORPORATE GOVERNANCE

As the Head of Administration the Municipal Manager is responsible for the following tasks:

-The formation and development of an economical, effective, efficient and accountable administration.

- The management of the municipality’s administration in accordance with legislation applicable to the municipality.

-The implementation of the municipality’s integrated development plan.

-The management and provision of services to the local communities in a sustainable and equitable manner.      -The appointment of staff subject to the Employment Equity Act, 1998.

-The management and effective utilisation and training of staff.

-The maintenance of discipline of staff.

-The promotion of sound Labour relations and compliance with Labour legislation.

- Advising the political structures and political office bearers of the municipality.

-Managing communications between the municipality’s administration and its political structures and political office bearers.

-Carrying out the decisions of the political structures and political office bearers of the municipality.

-The administration and implementation of the municipality’s by-laws and other legislation.

-The exercise of any powers and the performance of any duties delegated by the municipal council.

-Facilitating participation by the local community in the affairs of the municipality.

-The implementation of national and provincial legislation.

T2.6.0

### RISK MANAGEMENT

RISK MANAGEMENT

MFMA, section 62 (1) (c) (i) states that the Accounting Officer of a municipality is responsible for the municipality, and must for this purpose take all reasonable steps to ensure that the municipality has and maintains effective, efficient and transparent systems off financial and risk management and internal control.

Paragraph 13 of Chapter 13 of the Public Sector Risk Management Framework states that the Risk Management Committee must provide timely and useful reports to the Accounting Officer/Authority on the state of Risk Management, together with accompanying recommendations to address any deficiencies identified.

Risk Management Committee comprised of an independent The Risk Management Committee Chairperson and Directors as members appointed by the Accounting Officer.  The risk management policies were approved by council for 2023-2024 financial year. The following are the responsibilities of Risk Management:

1. Facilitating annual risk assessment within the municipality

2. Advising and guiding the municipality in terms of Institutional risk matters.

3. Developing the Risk Management Strategic documents and Implementation Plan.

4. Coordinating risk management activities.

5. Compilation of Risk Register

T2.6.1

### 2.7	ANTI-CORRUPTION AND FRAUD

FRAUD AND ANTI-CORRUPTION STRATEGY

In terms of section 3.2.1 of Treasury Regulations, the Accounting Officer must ensure that a risk assessment is conducted regularly to identify emerging risks to the institution. A Fraud and Corruption Management Strategy must be used to direct the internal audit effort and priority, and to determine the skills required of managers and staff to improve controls and to manage these risks.

During the year under review Fraud and Corruption Policy and Strategy was approved, the municipality continued to enforce strategies to combat fraud and corruption. Anti-Fraud and Corruption awareness campaign was conducted by issuing of the Fraud and Awareness Pamphlets as part of efforts to strengthen mechanisms to prevent and combat fraud and corruption.

T2.7.1

### 2.8	SUPPLY CHAIN MANAGEMENT

OVERVIEW SUPPLY CHAIN MANAGEMENT

The Supply Chain Management Policy of the municipality was reviewed to ensure that it is in line with the Municipal Supply Chain Management Regulations, other applicable legislations and guidelines of National Treasury. The reviewed SCM policy of the municipality for 2023/24 financial year was approved by the Council in June 2023. The municipality also developed the Preferential Procurement Policy in line with the new Preferential Procurement Regulation of 2022, which was also part of the policies approved by Council in June 2023.

The municipality (as far as the National Treasury SCM implementation check list is concerned, both quarterly and annually) does not have IT related projects above R10m, hence it has not yet utilized the services of SITA to procure such goods or service; and Lastly, an institutional delegation of powers has to be established in collaboration with Free State Provincial Treasury.

No Councillor is a member of any committee handling Supply Chain processes. All three (3) Officials in Supply Chain have the MFMA minimum competency requirements in 2016.

Non – compliance with Supply Chain Management Policy and other applicable legislations which resulted in irregular expenditure – As a remedial action to this problem, such expenditure to be investigated by MPAC, consequence management to be implemented and the SCM checklist to be reviewed and implemented effectively to ensure for an example, that all transactions, prior to awarding, are given to suppliers/service providers that are CSD compliant and/or comply with all the necessary bidding requirements.

T2.8.1

### 2.10	WEBSITES

| Municipal Website : Content and Currency of Material |  |  |
| --- | --- | --- |
| Documents published on the Municipality's / Entity's Website | Yes / No |  |
| Current annual and adjustments budgets and all budget-related documents | No |  |
| All current budget-related policies | No |  |
| The previous annual report (2022-2023) | Yes |  |
| The annual report (2023-2024) published/to be published | Yes |  |
| All current performance agreements required in terms of section 57(1)(b) of the Municipal Systems Act (2023-2024) and resulting scorecards | Yes |  |
| All service delivery agreements (2023-2024) | No |  |
| All long term borrowing contracts (2023-2024) | No |  |
| All supply chain management contracts above a prescribed value (give value) for 2023-2024 | No |  |
| An information statement containing a list of assets over a prescribed value that have been disposed of in terms of section 14 (2) or (4) during 2023-2024 | No |  |
| Contracts agreed in 2021-2022 to which subsection (1) of section 33 apply, subject to subsection (3) of that section | No |  |
| Public-private partnership agreements referred to in section 120 made in 2023-2024 | No |  |
| All quarterly reports tabled in the council in terms of section 52 (d) during 2023-2024 | No |  |
|  |  | T2.10.1 |

COMMENT MUNICIPAL WEBSITE CONTENT AND ACCESS

The Communications Unit is the custodian of the municipality website content. All documents and content are sent to the communications unit for verification and upload onto the municipal website.

The role of the IT Unit is to ensure that website is up and running. The municipality has a new website with domain name: www.xhariep.gov.za , some of the information is still sitting on the Provincial website that was created for all Free State Municipalities.

T2.10.1

# CHAPTER 3 – SERVICE DELIVERY PERFORMANCE (PERFORMANCE REPORT PART I)

## COMPONENT A: BASIC SERVICES

INTRODUCTION TO BASIC SERVICES

The district municipality started to perform the functions of Environmental Health with effect from December 2009. Critically, the Municipal Structures Amendment Act (Act 33 of 2000) provides for an extensive annual review of the division of powers and functions between Category B and Category C to ensure effective implementation of these assigned powers following an advice provided by the Municipal Demarcation Boarding emanating from the Boards’ annual capacity assessment report.

Basic services being offered by the District Municipality is as per Health profession Act, 1974 (Act no. 56 of 1974) Regulations defining the scope of the profession of Environmental Health: Amendment: Water and Waste Water quality, Food control, Waste management, Health Surveillance of premises, Vector control, Surveillance and prevention of communicable diseases, Environmental pollution, Disposal of the dead and noise control.

T3.1.0

| Employees: Planning Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022-2023 | 2023-2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 2 | 4 | 4 | 0 | 0 |
| 4 – 6 | 5 | 8 | 6 | 2 | 25% |
| 7 – 9 | 3 | 2 | 0 | 0 | 0 |
| 10 – 12 | 0 | 0 | 0 | 0 | 0 |
| 13 - 15 | 0 | 0 | 0 | 0 | 0 |
| 16 – 18 | 0 | 0 | 0 | 0 | 0 |
| 19 – 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 10 | 14 | 10 | 2 | 14.28% |
| T3.10.4 |  |  |  |  |  |

| Financial Performance 2023-2024: Planning Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2022-2023 | 2023-2024 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 16,233 | 14 255 | 18 214 | 14 335 | 3 879 |
| Expenditure: |  |  |  |  |  |
| Employees | 10,732 | 11 578 | 10 460 | 10 564 | (104) |
| Repairs and Maintenance | 0 | 0 | 0 | 0 | 0 |
| Other | 3,655 | 2 677 | 7 754 | 3 771 | 3 983 |
| Total Operational Expenditure | 14,387 | 14 255 | 18 214 | 14 335 | 3 879 |
| Net Operational Expenditure | 2,846 | 0 | 0 | 0 | 0 |
|  |  |  |  |  | T3.10.5 |

### 3.11	LOCAL ECONOMIC DEVELOPMENT (INCLUDING TOURISM AND MARKET PLACES)

INTRODUCTION TO ECONOMIC DEVELOPMENT

The review of the LED strategy is ongoing with the desktop work having been complete, this includes provision of current statistics that are acquired with the assistance of the DESTEA research unit and the COGTA. Free State COGTA is assisting the Xhariep District Municipality together with all its local municipalities in developing / review of the Local Economic Development Plans. A draft document for the district is in place, upon the final outstanding review processes to ensure priorities of the 7th administration of government are incorporated and proper alignment concluded together with Free State COGTA, the draft document will be tabled in council for adoption as a draft document for consultation, after the consultations, the final LED will be tabled and adopted in Council.

COGTA continues to assist local municipalities in the Free State with the development and review of LED Strategies, DESTEA continues as the lead department in economic development alignment with municipalities is yet to be realized.

T3.11.1

| Jobs Created during 2023-2024 by LED Initiatives (Excluding EPWP projects) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Total Jobs created / Top 3 initiatives | Jobs created | Jobs lost/displaced by other initiatives | Net total jobs created in year | Method of validating jobs created/lost |
|  | No. | No. | No. |  |
| 2021-2022 | 32 | 0 | 32 | Periodic maintenance of the National Route N1 section 14 between Springfontein north and Trompsburg, km 2.20 to km 18.60 |
|  | 30 | 0 | 30 | Periodic maintenance of the National Route N1 Section 13 Between Springfontein South and Springfontein North, km 41.60 to km 2.20 |
|  | 53 | 0 | 53 | Periodic maintenance of the National Route N1 section 13, from Driekuil (km 20.0) to Mount road (km 41.6) |
| 2022-2023 | 101 | 0 | 101 | National Route N1section 14 between Springfontein north and Trompsburg, KM 2.20 to 18,60 |
|  | 36 | 0 | 36 | Periodic maintenance of the National Route N1 section 13, between Springfontein South and Springfontein North Km 41.60 to Km 2.20 |
|  | 94 | 0 | 94 | Periodic maintenance of the National Route N1 section 13, from Driekuil (km 20.0) to Mount Road (Km 41.6) |
| 2023-2024 | 0 | 0 | 0 | - |
|  | 0 | 0 | 0 | - |
|  | 0 | 0 | 0 | - |
|  |  |  |  | T3.11.5 |

| Job creation through EPWP* projects |  |  |
| --- | --- | --- |
| Details | EPWP Projects | Jobs created through EPWP projects |
|  | No. | No. |
| 2021-2022 | 3 | 188 |
| 2022-2023 | 3 | 166 |
| 2023-2024 | 3 | 210 |
| * - Extended Public Works Programme |  | T3.11.6 |

| Employees: Local Economic Development Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022-2023 | 2023-2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 0 | 0 |
| 4 – 6 | 2 | 2 | 1 | 1 | 50% |
| 7 – 9 | 0 | 0 | 0 | 0 | 0 |
| 10 – 12 | 0 | 0 | 0 | 0 | 0 |
| 13 – 15 | 0 | 0 | 0 | 0 | 0 |
| 16 – 18 | 0 | 0 | 0 | 0 | 0 |
| 19 – 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 0 | 3 | 2 | 1 | 33% |
| T3.11.8 |  |  |  |  |  |

- 3.64	 HEALTH INSPECTION; FOOD AND ABBATOIR LICENSING AND INSPECTION; ETC

INTRODUCTION TO HEALTH INSPECTIONS; FOOD AND ABATTOIR LICENCING AND INSPECTIONS, ETC

A key responsibility in rendering an effective Municipal Health Services is the monitoring of  food and health surveillance of private and government premises in order to ensure compliance with R638, Foodstuffs, Cosmetics and Disinfectants act 1972 (Act no. 54 of 1972) and the National health act, 2003 (Act no 63 of 2003).

District Environmental Health Practitioners conduct health inspections of premises and issue out compliance notices to food premises which are found to be non-compliant with the set legislation. A certificate of acceptability (COA) is issued in accordance with the legislation to compliant premises.  For other premises Certificate of health is issued to compliant ECD’s and old age homes inclusive of the COA. Operational licenses are the competency of the local municipality and other stakeholders.

Surveillance of premises is also conducted to ensure vector control and to monitor health and hygiene standards of premises. Spot raids are conducted with the assistance of SAPS to curb non -compliance by shop owners and seize expired foods. Quarterly monitoring of all premises is conducted by the Environmental Health Practitioners. The compliance of food premises inspected in the district was: Quarter 1: 32, 5%, Quarter 2: 47, 5%, Quarter 3: 50% and Quarter 4: 12, 5%.

Challenges:

The lack of by-laws and law enforcement remains a challenge in ensuring compliance of all food and other premises in the district.

Health and Hygiene

Health and hygiene awareness activities were successfully carried out by the Environmental Health Practitioners in an effort to influence behavioral change on matters of health and the environment. The topics covered included food safety, hand hygiene, the national Environmental Health norms and standards for premises and communicable diseases amongst others. The key focus groups were the community members, School learners and the food handlers. The total number of people reached during the awareness campaigns conducted in the four quarters of the 2023/24 financial year were 1000.

Waste Management and Health surveillance of premises

The Environmental Health Practitioners in Xhariep District Municipality conducted landfill site audits in the second quarter of the 2023/24 financial year to determine the level of compliance. Waste Management functions of Environmental Health under the Health Professions Act, 1974 (Act no. 56 of 1974) Regulations defining the scope of profession of Environmental Health: Amendment. All landfill sites in the district were found to be non-complaint in terms of the National Environmental Management Waste Act, 59 of 2008. The current compliance rate is; Mohokare LM (0%), Kopanong LM (0%) and Letsemeng LM (0 %). This has a negative impact on both human health and the Environment.

Disposal of the dead and exhumation of human remains

Another key role is the implementation of Regulations Relating to the Management of Human Remains – Government Notice Number – R 363 of 22 May 2013. The District Environmental Health Practitioners conducted compliance inspections at funeral undertaker’s premises and issued out compliance notices to both government and private which were found to be non-compliant with legislation and where premises were compliant; a certificate of competence was issued. Monitoring was conducted in the fourth quarter of the financial year. 83% of the premises that were visited were compliant.

Water quality monitoring

The Environmental Health Practitioners monitored the quality of drinking water at the point of use on a monthly basis to ensure that community members receive water that is safe for human consumption and the water does not pose a risk on human health. The results obtained from the laboratory after analysis are communicated with the local municipalities, the Department of Health and the community where necessary. This is done to ensure that the local municipalities supply the community with treated water and complies with the standards in terms of SANS 241:2015. The total number of drinking water samples for the financial year 2023/24 was 396 excluding the re-samples.

Wastewater effluent monitoring

Wastewater samples were also collected in the financial year to monitor the quality of wastewater effluent discharged into the environment in terms of the National Water Act, 36 of 1998; the general authorization limits. The total number of samples collected was 20 and 100% of the wastewater treatment plants were found to be non-compliant; the wastewater effluent discharged into the environment is untreated and causes environmental pollution in terms of the National Environmental Management Act, 107 of 1998. The results and recommendations were shared with the affected local municipalities in the district.

T3.64.1

### 3.67	DISASTER MANAGEMENT

INTRODUCTION TO DISASTER MANAGEMENT

Disaster Management is a continuous and integrated multi-sectorial and multi-disciplinary process of planning and implementation of measures aimed at disaster prevention, -mitigation, -preparedness, -response, -recovery and –rehabilitation

Top Four Service Delivery Priorities:

1. Community Safety

2. Preparedness

3. Recovery and Rehabilitation

4. Educational Program

The DM Unit main role is to ensure a safe and unwavering environment to the Xhariep district community. Through proper planning the Unit will be able to build resilient communities through the Disaster Management Activities within the district Municipality. A budget for the Disaster Management Contribution has been set aside for affected families. The DM Unit played a vital role by conducting educational programme both at Secondary and Primary Schools in the district municipality. We are also in partnership with Working on Fire (WoF) to conduct Fire Awareness at local level with the assistance of local Councillors

T3.67.1

| Employees: Disaster Management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022/2023 | 2023/2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 – 3 | 1 | 1 | 1 | 0 | 0 |
| 4 – 6 | 1 | 2 | 1 | 1 | 50% |
| 7 – 9 | 0 | 0 | 0 | 0 | 0 |
| 10 – 12 | 0 | 0 | 0 | 0 | 0 |
| 13 – 15 | 0 | 0 | 0 | 0 | 0 |
| 16 – 18 | 0 | 0 | 0 | 0 | 0 |
| 19 – 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 2 | 3 | 2 | 1 | 33.3% |
| T3.67.4 |  |  |  |  |  |

## COMPONENT I: CORPORATE POLICY OFFICES AND OTHER SERVICES

This component includes: corporate policy offices, financial services, human resource services, ICT services.

### 3.69	EXECUTIVE AND COUNCIL

This component includes: Executive office (mayor; councilors; and municipal manager).

INTRODUCTION TO EXECUTIVE AND COUNCIL

Municipality is currently executing three service delivery related matters, i.e. local economic development,   Disaster Management and Municipal Health Services. The Local Economic Development Division that is located within the Department of Planning and Social Development has made strides in providing financial assistance and providing training to Small Micro and Medium Enterprises. The Municipality has assisted interested individuals or group of people to establish their own businesses, in particular cooperatives.

The Environmental Health Services Division that is also located within the Department of Planning and Social Development is monitoring the quality of drinking water and final waste water effluent from different local municipalities that fall within its jurisdiction on frequent intervals as required by applicable legislations and policies. Furthermore this division insures compliance of food premises and local municipalities’ landfill sites.

The Disaster Management Division is located in the Department of Planning and Social Development. The division is responsible to ensure a safe and unwavering environment to the Xhariep district community.

T3.69.1

| Employees: The Executive and Council |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022-2023 | 2023-2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 5 | 5 | 4 | 1 | 20% |
| 4 - 6 | 6 | 6 | 6 | 0 | 0 |
| 7 - 9 | 5 | 5 | 5 | 0 | 0 |
| 10 - 12 | 0 | 0 | 0 | 0 | 0 |
| 13 - 15 | 0 | 0 | 0 | 0 | 0 |
| 16 - 18 | 0 | 0 | 0 | 0 | 0 |
| 19 - 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 16 | 16 | 15 | 1 | 6.66% |
| T3.69.4 |  |  |  |  |  |

| Financial Performance 2023-2024: The Executive and Council |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2022-2023 | 2023-2024 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 15,300 | 12 187 | 13 868 | 16 751 | (2 883) |
| Expenditure: | 0 |  |  |  |  |
| Employees | 11,216 | 11 996 | 12 141 | 12 458 | (317) |
| Repairs and Maintenance | 0 | 0 | 0 | 0 | 0 |
| Other | 5,112 | 191 | 1 727 | 4 293 | (2566) |
| Total Operational Expenditure | 16,328 | 12 187 | 13 868 | 16 751 | (2 883) |
| Net Operational Expenditure | -1,028 | 0 | 0 | 0 | 0 |
| Net expenditure to be consistent with summary table T5.1.2 in Chapter 5. Variances are calculated by dividing the difference between the Actual and Original Budget by the Actual. |  |  |  |  | T3.69.5 |

| Employees: Financial Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022-2023 | 2023-2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 3 | 3 | 3 | 0 | 0 |
| 4 - 6 | 5 | 5 | 5 | 0 | 0 |
| 7 - 9 | 4 | 4 | 4 | 0 | 0 |
| 10 - 12 | 0 | 0 | 0 | 0 | 0 |
| 13 - 15 | 0 | 0 | 0 | 0 | 0 |
| 16 - 18 | 0 | 0 | 0 | 0 | 0 |
| 19 - 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 12 | 12 | 12 | 0 | 0 |
| T3.70.4 |  |  |  |  |  |

| Financial Performance 2023-2024: Financial Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2022-2023 | 2023-2024 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 14,662 | 39 820 | 79 879 | 36 478 | 43 401 |
| Expenditure: |  |  |  |  |  |
| Employees | 9,507 | 10 411 | 10 257 | 10 271 | (14) |
| Repairs and Maintenance | 0 | 0 | 0 | 0 | 0 |
| Other | 3,726 | 29 409 | 69 622 | 26 207 | 43 415 |
| Total Operational Expenditure | 13, 233 | 39 820 | 79 879 | 36 478 | 43 401 |
| Net Operational Expenditure | 1, 429 | 0 | 0 | 0 | 0 |
| Net expenditure to be consistent with summary table T5.1.2 in Chapter 5. Variances are calculated by dividing the difference between the Actual and Original Budget by the Actual. |  |  |  |  | T3.70.5 |

### 3.71	HUMAN RESOURCE SERVICES

INTRODUCTION TO HUMAN RESOURCE SERVICES

The management set itself priorities to overhaul the services the institution provides to its internal clients, the key three amongst them were;

Purify leave management

Provide accurate inputs- information to payroll

Recruit people with required competencies

So far this division has made major strides in ensuring that leave of employees is managed in accordance with Municipal Human Resources Policy Manual. Every week there is reconciliation of attendance registers, VIP register with completed leave forms; and follow-ups on employees who did not sign registers or completed leave forms. The principle of no work no pay is applied on employees who are found not to have followed proper procedure in absenting themselves from work.

The official providing information to employees in payroll on remuneration and benefits of employees work s closely with the payroll division in order to ensure that accurate information is forwarded to division before processing the salaries of councillors and employees. The inputs are compiled, checked, approved by different individuals in order to ensure that correct information is provided to payroll. Such information is forwarded to payroll on or before the 15th of each month in order to give officials in payroll an ample time to process the remuneration and benefits of both councillors and officials

The Human Resources Division advertises all vacant positions as required by the Human Resources Policy Manual and set competencies that are needed from the interested individuals. It is important to highlight that the Municipality appoints only incumbents who meets minimum competency requirements as placed on the advertisement.

T3.71.1

| Employees: Human Resource |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022-2023 | 2023-2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 1 | 1 | 1 | 0 | 0 |
| 4 - 6 | 3 | 5 | 3 | 2 | 40% |
| 7 - 9 | 1 | 1 | 1 | 0 | 0 |
| 10 - 12 | 0 | 0 | 0 | 0 | 0 |
| 13 - 15 | 0 | 0 | 0 | 0 | 0 |
| 16 - 18 | 0 | 0 | 0 | 0 | 0 |
| 19 - 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 5 | 7 | 5 | 2 | 11% |
| T3.71.4 |  |  |  |  |  |

| Financial Performance 2023-2024: Human Resource Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R'000 |  |  |  |  |  |
| Details | 2022-2023 | 2023-2024 |  |  |  |
|  | Actual | Original Budget | Adjustment Budget | Actual | Variance to Budget |
| Total Operational Revenue | 24,795 | 22 818 | 31 641 | 35 111 | (3 470) |
| Expenditure: |  |  |  |  |  |
| Employees | 19,290 | 19 356 | 18 718 | 19 691 | (973) |
| Repairs and Maintenance | 147 | 90 | 664 | 633 | 31 |
| Other | 4,866 | 3 372 | 12 259 | 14 787 | (2 528) |
| Total Operational Expenditure | 24,303 | 22 818 | 31 641 | 35 111 | (3 470) |
| Net Operational Expenditure | 492 | 0 | 0 | 0 | 0 |
| Net expenditure to be consistent with summary table T5.1.2 in Chapter 5. Variances are calculated by dividing the difference between the Actual and Original Budget by the Actual. |  |  |  |  | T3.71.5 |

### 3.72	INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

This component includes: Information and Communication Technology (ICT) services

INTRODUCTION TO INFORMATION AND COMMUNICATION TECHNOLOGY (ICT) SERVICES

The main objective of the IT Unit is to

1. Ensure connectivity at all times: This was achieved through enhancement of the bandwidth from 10mbps to 50mbps and the connectivity is much stronger.

2. Ensure stable Network infrastructure: The network is fairly stable. The project to Revamp Municipal Network Infrastructure, was halted due to litigations by the service provider, demanding payment for incomplete work

3. Ensure Servers and server room is fully functional: The servers are fully functional. The network infrastructure in a better state, but the Network Infrastructure Revamp project was halted in its final stages, fire extinguishing unit will also be replaced, the floor was listed as well in case of flooding.

4. Ensure information systems are fully operational: The municipality is housing the Financial Information System on the cloud. All Information Systems are functioning properly.

5. Ensure smooth Telecommunications: The project to install fully functional Telephone System was halted due to litigations by the service provider, demanding payment for incomplete work, as a result the telephone system is not functioning.

6. Ensure printing facility is available: The municipality has recently bought a printer for the archives office for volume printing. There are also small printers bought for various offices to address printing at a smaller scale.

7. Ensure Municipal Website is fully functional: The municipality has a new fully functional website

T3.72.1

| Employees: ICT Services |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Job Level | 2022-2023 | 2023-2024 |  |  |  |
|  | Employees | Posts | Employees | Vacancies (fulltime equivalents) | Vacancies (as a % of total posts) |
|  | No. | No. | No. | No. | % |
| 0 - 3 | 1 | 1 | 1 | 0 | 0 |
| 4 - 6 | 1 | 1 | 1 | 0 | 0 |
| 7 - 9 | 0 | 0 | 0 | 0 | 0 |
| 10 - 12 | 0 | 0 | 0 | 0 | 0 |
| 13 - 15 | 0 | 0 | 0 | 0 | 0 |
| 16 - 18 | 0 | 0 | 0 | 0 | 0 |
| 19 - 20 | 0 | 0 | 0 | 0 | 0 |
| Total | 2 | 2 | 2 | 0 | 0 |
| T3.72.4 |  |  |  |  |  |

## COMPONENT K: ORGANISATIONAL PERFORMANCE SCORECARD

This component includes:  Annual Performance Scorecard Report for the current year

TOP LAYER PERFORMANCE INFORMATION

| REF | IDP OBJECTIVE |  |  | KPA | KPI |  |  | UNIT OF MEASUREMENT |  |  |  | ANNUAL TARGET |  |  | ACTUAL |  |  | VARIANCE |  |  |  | REASON FOR DEVIATION |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  | PRIOR TARGET |  | PRIOR ACTUAL |  | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | MUNICIPAL MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL 1 | Develop and enhance human capital services to minimize service delivery |  | MT&ID |  |  | Employment contracts |  |  | Number of signed performance agreements by the MM and Sec 56 Managers |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | Filling of the vacancy of the Director: Planning & Social Development | 4 |  |  | 3 |  | (1) |
| TL2 | Develop and enhance human capital services to minimize service delivery |  | MT&ID |  |  | Performance Management |  |  | Assessment of the Performance of Senior Management on a quarterly basis |  |  |  | 2 x informal 2 x formal |  |  | 2 x informal 0 x formal |  |  | 2 x informal 0 x formal |  | The last formal review is scheduled for September 2024. |  |  | The formal review to take place as scheduled | 2 x informal 2 x formal |  |  | 2 x informal 2 x formal |  | 0 |
| TL3 | Develop and enhance human capital services to minimize service delivery |  | MT&ID |  |  | Performance Management |  |  | No. of performance analysis reports to Management on a quarterly basis |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - | 4 |  |  | 4 |  | 0 |
| TL4 | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Overseeing the functionality of Audit Committee |  |  | Quarterly Audit Committee meetings |  |  |  | 4 |  |  | 3 |  |  | (1) |  | The Internal Audit division fell behind on the third-quarter audits, which caused the committee to be unable to meet as scheduled. |  |  | The vacancy of the Internal Audit has been filled. | 4 |  |  | 2 |  | (2) |
| TL5 | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Overseeing the functionality of MPAC |  |  | Number of MPAC meetings held |  |  |  | 4 |  |  | 2 |  |  | (2) |  | There were no UIF reports referred to the MPAC for investigation in the second and forth quarter hence the negative variance |  |  | The Accounting Officer to follow up with the BTO on the submission of these reports to MPAC so that the committee sits as planned | New KPI |  |  | New KPI |  | New KPI |
| TL6 | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Ensure the sitting of management |  |  | Number of formal (minuted) meetings to which all senior managers were invited-held |  |  |  | 4 |  |  | 0 |  |  | (4) |  | Senior Management sits regularly but do not keep records or minutes of their meetings |  |  | Record keeping of Senior Management minutes as prescribed by MFMA circular 88 | New KPI |  |  | New KPI |  | New KPI |
| TL7 | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Providing support to Local Municipalities through Technical IGR engagements |  |  | No. of Technical IGR meetings held |  |  |  | 4 |  |  | 2 |  |  | (2) |  | The Technical IGR could not sit as planned in the second and fourth quarter due to provincial meetings clashing with the sitting of the Technical IGR. |  |  | The convener of the Technical IGR to communicate the schedule of the District Technical IGR with the provincial departments to avoid the clash of dates | 4 |  |  | 3 |  | (1) |
| TL8 | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Overseeing the functionality of the Risk Management Committee |  |  | No. of Risk Management reports submitted to the Risk Management Committee on a quarterly basis |  |  |  | 4 |  |  | 3 |  |  | (1) |  | The risk management report was compiled but could not be presented to the Risk Management Committee due to the committee not convening in the fourth quarter. |  |  | Risk Management report will be presented in the next sitting of the Risk Management Committee | 4 |  |  | 1 |  | (3) |
| TL9 | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Improved audit outcomes |  |  | Monitoring the implementation of AGSA audit action plan and report quarterly |  |  |  | 2 |  |  | 2 |  |  | 0 |  | - |  |  | - | 2 |  |  | 2 |  | 0 |
| TL10 | Continue with accountable and developmental orientated monetary management to sustain a sound fiduciary position |  | MFV&M |  |  | Ensure compliance with Section 32 of the MFMA |  |  | Monthly reports on irregular, unauthorized, fruitless and wasteful expenditure |  |  |  | 12 |  |  | 12 |  |  | 0 |  | - |  |  | - | 12 |  |  | 12 |  | 12 |
| TL11 | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Ensure compliance with Municipal Staff Regulations (2021) |  |  | Monitoring the implementation plan of the Municipal Staff Regulations (2021) on a quarterly basis |  |  |  | 4 |  |  | 4 |  |  | 4 |  | - |  |  | - | 4 |  |  | 4 |  | 0 |
| REF | IDP OBJECTIVE |  | KPA |  |  | KPI |  |  | UNIT OF MEASUREMENT |  |  |  | ANNUAL TARGET |  |  | ACTUAL |  |  | VARIANCE |  | REASON FOR DEVIATION |  |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  | PRIOR TARGET |  | PRIOR ACTUAL |  | PRIOR VARIANCE |
|  |  | CHIEF FINANCIAL OFFICER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL12 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Annual Financial Statements |  |  |  | Compilation AFS on or before 31 Aug 2023 and submission to AGSA |  |  |  | 1 |  |  | 1 |  |  | 0 |  | - |  |  | - |  | 1 |  | 1 |  | 0 |
| TL13 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Oversee the review and implementation of the Audit Action Plan |  |  |  | Updated Action Plan |  |  |  | 2 |  |  | 2 |  |  | 0 |  | - |  |  | - |  | 2 |  | 2 |  | 0 |
| TL14 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Ensure that the FMG conditional operational grant is fully utilized by 30 June 2024 |  |  |  | % of FMG conditional operational grant spent on a quarterly basis |  |  |  | 100% |  |  | 100% |  |  | 0 |  | - |  |  | - |  | 100% |  | 100% |  | 100% |
| TL15 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Oversee the implementation of the SCM Policy |  |  |  | Quarterly reports on the deviations of the SCM Policy |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | 4 |  | 4 |  | 0 |
| TL16 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Oversee the implementation of the SCM Policy |  |  |  | Annual Report on the deviations of the SCM Policy to Council |  |  |  | 1 |  |  | 0 |  |  | (1) |  | Annual Report on the deviations of the SCM Policy compiled but could not be tabled to Council at the end of the fourth quarter |  |  | Annual Report on the deviations of the SCM Policy will be tabled in the next sitting of Council (on or before the end of August 2024). SCM also to align its reporting with the approved SDBIP targets |  | 1 |  | 0 |  | (0) |
| TL17 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Oversee the implementation of the SCM Policy |  |  |  | B-BBEE Procurement Spend on Empowering Suppliers that are at least 30% black women owned |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | New KPI |  | New KPI |  | New KPI |
| TL18 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Oversee the implementation of the SCM Policy |  |  |  | B-BBEE Procurement Spend on Empowering Suppliers that are at least 51% black owned based |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | New KPI |  | New KPI |  | New KPI |
| TL19 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Ensure Compliance to SCM Regulations |  |  |  | Number of awards made in terms of SCM Reg 32 |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | New KPI |  | New KPI |  | New KPI |
| TL20 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Compilation of MFMA Sec 71 reports to Provincial and National Treasury |  |  |  | Monthly MFMA Sec 71 reports |  |  |  | 12 |  |  | 12 |  |  | 0 |  | - |  |  | - |  | 12 |  | 12 |  | 0 |
| TL21 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Compilation of MFMA Sec 52 (d) reports to Provincial and National Treasury |  |  |  | Quarterly Sec 52 (d) (MFMA) reports |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | 12 |  | 12 |  | 0 |
| TL22 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Compilation of SCM reports to Provincial and National Treasury |  |  |  | SCM quarterly reports |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | 4 |  | 4 |  | 0 |
| TL23 |  | To manage the finances of the municipality to ensure financial viability | MFV&M |  | Monitor the implementation of the Demand Management Plan |  |  |  | Quarterly reports on the implementation of the Demand Management Plan |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | 4 |  | 4 |  | 0 |
| TL24 |  | Sustain good corporate governance through effective and accountable clean administration | MT&ID |  | Ensure compliance with the Municipal Staff Regulations (2021) |  |  |  | Monitoring the implementation plan of the Municipal Staff Regulations (2021) of a quarterly basis |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  |  | - |  | 4 |  | 4 |  | 0 |
| TL25 |  | Sustain good corporate governance through effective and accountable clean administration | GG&PP |  | Overseeing the functionality of the Risk Management Committee |  |  |  | No. of Risk Management reports submitted to the Risk Management committee by Senior Management |  |  |  | 4 |  |  | 3 |  |  | (1) |  | The risk management report was compiled but could not be presented to the Risk Management Committee due to the committee not convening in the fourth quarter. |  |  | Risk Management report will be presented in the next sitting of the Risk Management Committee |  | 4 |  | 1 |  | (3) |
| REF |  | IDP OBJECTIVE | KPA |  | KPI |  |  |  | UNIT OF MEASUREMENT |  |  |  | ANNUAL TARGET |  |  | ACTUAL |  |  | VARIANCE |  | REASON FOR DEVIATION |  |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  | PRIOR TARGET |  | PRIOR ACTUAL |  | PRIOR VARIANCE |
|  |  | DIRECTOR: CORPORATE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL26 |  | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Oversee the compilation and the submission of the WSP |  |  | WSP approved by the LLF and submitted to LGSETA in April 2024 |  |  |  | 1 |  |  | 1 |  |  | 0 |  | - | - |  |  |  | 1 | 1 |  | 0 |
| TL27 |  | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Ensure compliance with the Municipal Staff Regulations (2021) |  |  | Review of the Employment Equity Policy/Plan on or before 30 Sep 2023 |  |  |  | 1 |  |  | 1 |  |  | 1 |  | - | - |  |  |  | 1 | 1 |  | 0 |
| TL28 |  | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Employment Equity |  |  | Monitor and report on the implementation the Employment Equity Plan |  |  |  | 1 |  |  | 1 |  |  | 0 |  | - | - |  |  |  | 1 | 1 |  | 0 |
| TL29 |  | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Work Skills Plan |  |  | Number of municipal officials completed training in the 2023-2024 financial year |  |  |  | 15 |  |  | 15 |  |  | 0 |  | - | - |  |  |  | 5 | 5 |  | 0 |
| TL30 |  | Oversee the achievement of good governance through the implementation of council resolution |  | GG&PP |  |  | Sitting of Council and Council Committees |  |  | Develop schedule for the sitting of Council and Council Committees and table before Council |  |  |  | 1 |  |  | 1 |  |  | 0 |  | - | - |  |  |  | 1 | 1 |  | 0 |
| TL31 |  | Oversee the achievement of good governance through the implementation of council resolution |  | GG&PP |  |  | Sitting of Council and Council Committees |  |  | No. of Council portfolio committee meetings held |  |  |  | 6 |  |  | 4 |  |  | (2) |  | The Council portfolio committees did not sit as per the approved SDBIP projections in the 2023-2024 financial year | Sitting of the Council portfolio committees will be aligned to the SDBIP projections |  |  |  | New KPI | New KPI |  | New KPI |
| TL32 |  | Oversee the achievement of good governance through the implementation of council resolution |  | GG&PP |  |  | Ensure that Council sits as regulated by the MSA (Act 32 of 2000) |  |  | Number of ExCo or Mayoral Executive meetings held |  |  |  | 6 |  |  | 6 |  |  | 0 |  | - | - |  |  |  | New KPI | New KPI |  | New KPI |
| TL33 |  | Oversee the achievement of good governance through the implementation of council resolution |  | GG&PP |  |  | Ensure that Council sits as regulated by the MSA (Act 32 of 2000) |  |  | No. of Council meetings(ordinary) held |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - | - |  |  |  | 4 | 6 |  | 2 |
| TL34 |  | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Stakeholder relations |  |  | No. of Political IGR meetings held |  |  |  | 4 |  |  | 0 |  |  | (4) |  | Political IGR did not sit as planned in the year under review | The Executive Mayor to resuscitate the Political IGR |  |  |  | 4 | 4 |  | 0 |
| TL35 |  | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Stakeholder relations |  |  | No. of District AIDS Council meetings held |  |  |  | 4 |  |  | 1 |  |  | (3) |  | District AIDS Council did not sit as planned in the year under review | The Executive Mayor to resuscitate the District AIDS Council |  |  |  | 4 | 3 |  | (1) |
| TL36 |  | To maintain a skilled, capable and diverse workforce in a good working environment |  | MT&ID |  |  | Ensure functionality of Local Labour Forum |  |  | No. of Local Labour Forum meetings |  |  |  | 4 |  |  | 2 |  |  | (2) |  | Local Labour Forum did not sit as planned in the year under review | The Director Corporate Services will resuscitate the LLF and ensure that it sits as planned in the new financial year |  |  |  | 4 | 4 |  | 0 |
| TL37 |  | To maintain a skilled, capable and diverse workforce in a good working environment |  | MT&ID |  |  | Performance Management System |  |  | Cascading Individual performance management to (Lower level employees before 30 June 2024 |  |  |  | 2 |  |  | 2 |  |  | 0 |  | - | - |  |  |  | New KPI | New KPI |  | New KPI |
| TL38 |  | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Ensure compliance with the Municipal Staff Regulations (2021) |  |  | Monitoring the implementation plan of the Municipal Staff Regulations (2021) on a quarterly basis |  |  |  | 4 |  |  | 4 |  |  | 0 |  | - | - |  |  |  | 4 | 4 |  | 0 |
| TL39 |  | Embed good governance through sound administrative practices and improved stakeholder relation |  | GG&PP |  |  | Overseeing the functionality of the Risk Management Committee |  |  | No. of Risk Management reports submitted to the Risk Management committee by Senior Management |  |  |  | 4 |  |  | 3 |  |  | (1) |  | The risk management report was compiled but could not be presented to the Risk Management Committee due to the committee not convening in the fourth quarter. | Risk Management report will be presented in the next sitting of the Risk Management Committee |  |  |  | 4 | 1 |  | (3) |
| TL40 |  | Oversee the achievement of good governance through the implementation of council resolution |  | GG&PP |  |  | Anti-Fraud and Corruption |  |  | Quarterly reports on disciplinary cases for misconduct relating to fraud and corruption |  |  |  | 4 |  |  | 1 |  |  | (3) |  | Only one report of the MPAC was referred to the DC board for investigation | The sitting of the MPAC as planned in the new financial year will influence the number of reports from the DC board |  |  |  | New KPI | New KPI |  | New KPI |
| REF |  | IDP OBJECTIVE |  | KPA |  |  | KPI |  |  | UNIT OF MEASUREMENT |  |  |  | ANNUAL TARGET |  |  | ACTUAL |  |  | VARIANCE |  | REASON FOR DEVIATION |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  |  | PRIOR TARGET |  | PRIOR ACTUAL | PRIOR VARIANCE |
|  |  | DIRECTOR: PLANNING AND SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TL41 |  | Provide safe and healthy environment for the community |  | BSD&ID |  |  | Maintaining and improving the standard of water quality(compliance to SANS 241) |  |  |  | Ensure that water quality tests are done on a quarterly basis |  |  | 4 |  |  | 3 |  |  | (1) |  | Water samples could not be taken as planned for the month of July 2023 due to the lapse of the contract of the Service Provider |  | Appointment of the service provider on time |  | 4 |  |  | 4 | 0 |
| TL42 |  | Provide safe and healthy environment for the community |  | BSD&ID |  |  | Maintaining and improving the standard of water quality(compliance to SANS 241) |  |  |  | Total number of water samples tested |  |  | 396 |  |  | 363 |  |  | (33) |  | Water samples could not be taken as planned for the month of July 2023 due to the lapse of the contract of the Service Provider |  | Appointment of the service provider on time |  | 396 |  |  | 396 | 396 |
| TL43 |  | Provide safe and healthy environment for the community |  | BSD&ID |  |  | Maintaining and improving the standard of water quality(compliance to SANS 241) |  |  |  | Number of water sample tests that complied with SANS 241 requirements |  |  | 396 |  |  | 306 |  |  | (57) |  | The target for water samples taken as per the approved SDBIP 2023-2024 is 396 but because of non-taking of 33 water samples in the month of July; the municipality managed only to test 363 samples. From the 363 samples taken; only 306 met the SANS 241 requirement due to some samples having E.coli and total coliforms. |  | Timeous appointment of service provider and resampling of all failed batches water samples |  | New KPI |  |  | New KPI | New KPI |
| TL44 |  | Provide safe and healthy environment for the community |  | BSD&ID |  |  | Wastewater samples compliant to water use license conditions |  |  |  | Total wastewater samples tested for all determinants over the municipal financial year |  |  | 20 |  |  | 20 |  |  | 0 |  | All the treatment plants in the 3 local municipalities were accessible in the 2023-2024 financial year hence waste water samples could be taken as planned |  | - |  | 20 |  |  | 19 | (1) |
| TL45 |  | Provide safe and healthy environment for the community |  | BSD&ID |  |  | Wastewater samples compliant to water use license conditions |  |  |  | Number of wastewater samples tested per determinant that meet compliance to specified water use license requirements |  |  | 20 |  |  | 0 |  |  | (20) |  | This is due to old waste water infrastructure that causes the treatment plants not functioning as they should therefore treatment does not take place and as a result untreated effluent is released back to the environment |  | Local municipalities to ensure the upgrading and maintenance of the waste water treatment plants to ensure compliance with the general authorization limits |  | New KPI |  |  | New KPI | New KPI |
| TL46 |  | Strategic support on the implementation of municipal programmes and projects |  | BSD&ID |  |  | Ensure that the RRAMS grant is fully utilized by 30 June 2024 |  |  |  | % of RRAMS grant spent on a quarterly basis |  |  | 100% |  |  | 100% |  |  | 0 |  | - |  | - |  | 100% |  |  | 100% | 0 |
| TL47 |  | Strategic support on the implementation of municipal programmes and projects |  | BSD&ID |  |  | Play an oversight role in terms of the implementation of the RRAMS project |  |  |  | No. of reports to Management/ Council on the implementation of the RRAMS project |  |  | 4 |  |  | 0 |  |  | (4) |  | Reports on the implementation of the RRAMS project were compiled but there is no proof that they were tabled before management or Council |  | Reporting of the RRAMS project will be as projected by the approved SDBIP in the new financial year |  | 4 |  |  | 3 | (1) |
| TL48 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED |  |  | Job Creation |  |  |  | No. of jobs opportunities created through the Expanded Public Works Programme |  |  | 160 |  |  | 210 |  |  | 50 |  | More EPWP workers were recruited due to the favorable EPWP budget |  | - |  | 237 |  |  | 166 | (71) |
| TL49 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED |  |  | Ensure participation of all local municipalities towards the implementation of LED |  |  |  | No of LED Forums |  |  | 4 |  |  | 2 |  |  | (2) |  | Two LED Forum meetings could not be confirmed |  | Proper record keeping |  | 4 |  |  | 4 | 0 |
| TL50 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED |  |  | Lobbying of external stakeholders to invest in Xhariep |  |  |  | No. of stakeholder engagement meetings |  |  | 2 |  |  | 2 |  |  | 0 |  | - |  | - |  | 2 |  |  | 2 | 0 |
| TL51 |  | Provide safe and healthy environment for the community |  | BSD&ID |  |  | Ensuring compliance of funeral undertakers premises |  |  |  | No. of reports on Funeral parlours compliance status |  |  | 1 |  |  | 1 |  |  | 0 |  | - |  | - |  | New KPI |  |  | New KPI | New KPI |
| TL52 |  | Sustain good corporate governance through effective and accountable clean administration |  | GG&PP |  |  | Overseeing the functionality of the Risk Management Committee |  |  |  | No. of Risk Management reports submitted to the Risk Management Committee by Senior Management |  |  | 4 |  |  | 3 |  |  | (1) |  | The risk management report was compiled but could not be presented to the Risk Management Committee due to the committee not convening in the fourth quarter. |  | Risk Management report will be presented in the next sitting of the Risk Management Committee |  | 4 |  |  | 1 | (3) |
| TL53 |  | Sustain good corporate governance through effective and accountable clean administration |  | MT&ID |  |  | Ensure compliance with the Municipal Staff Regulations (2021) |  |  |  | Monitoring the implementation plan of the Municipal Staff Regulations (2021) on a quarterly basis |  |  | 4 |  |  | 4 |  |  | 0 |  | - |  | - |  | 4 |  |  | 4 | 0 |

DEPARTMENTAL PERFORMANCE

| REF |  |  | IDP OBJECTIVE | KPA |  | KPI |  |  |  |  |  | UNIT OF MEASUREMENT |  |  |  |  |  | ANNUAL TARGET |  |  |  | ACTUAL |  |  |  |  |  | VARIANCE |  |  |  | REASON FOR DEVIATION |  |  |  |  |  |  |  |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  |  |  |  |  |  |  | PRIOR TARGET |  |  |  |  | PRIOR ACTUAL |  |  |  |  | PRIOR VARIANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | MUNICIPAL MANAGER |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D1 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Implementation of the Risk Management, anti-fraud and anti-corruption initiatives |  |  |  |  | No. of Risk Management, anti-fraud and anti-corruption awareness conducted |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 0 |
| D2 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Risk Management |  |  |  |  | Development of the Risk Management Register before 30-Sep- 2023 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 0 |
| D3 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Risk Management |  |  |  |  | No. of quarterly risk assessments performed for each(4) department |  |  |  |  |  |  | 4 |  |  |  | 4 |  |  |  |  |  | 0 |  |  |  |  |  | Tools of trade were bought for the CRO |  |  |  |  |  |  |  | - |  |  |  |  |  | 4 |  |  |  |  |  |  | 3 |  |  |  | (1) |
| D4 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Improved audit outcomes |  |  |  |  | Reduction of audit findings by 80% in the 2022/2023 financial year |  |  |  |  |  |  | 80% |  |  |  | 40% |  |  |  |  |  | (40%) |  |  |  |  |  | The municipality managed to reduce audit finding only by 40%. This is due to material statements on the audited AFS 2022-2023. |  |  |  |  |  |  |  | Frequent monitoring of the audit action |  |  |  |  |  | 80% |  |  |  |  |  |  | 53.43% |  |  |  | (26.57%) |
| D5 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Functional Internal Audit Unit (MFMA 62(1)) |  |  |  |  | No of quarterly reports prepared for Audit Committee |  |  |  |  |  |  | 4 |  |  |  | 3 |  |  |  |  |  | (1) |  |  |  |  |  | The Internal Audit division fell behind on the third-quarter audits, which caused the committee to be unable to meet as scheduled. |  |  |  |  |  |  |  | The vacancy of the Internal Audit has been filled. |  |  |  |  |  | 4 |  |  |  |  |  |  | 2 |  |  |  | (2) |
| D6 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Development of the Risk based audit plan |  |  |  |  | Risk based audit plan approved by Audit Committee by 30 Sep 2023 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | Appointment of the Audit and Performance Committee |  |  |  |  |  | 1 |  |  |  |  |  |  | 0 |  |  |  | (0) |
| D7 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Compilation of the draft Annual Report |  |  |  |  | Draft Annual Report approved by Council on or before 31 January 2024 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 0 |
| D8 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Compilation of the Oversight Report on Annual Report (MFMA 129(1) and MSA 46(2) |  |  |  |  | Oversight Report adopted by Council on or before 31 March 2024 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 0 |
| D9 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Mid- Year review of the performance of the municipality (MFMA S72) |  |  |  |  | Mid-year report submissions (Mayor, Provincial and National Treasury) by 25 January 2024 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 0 |
| D10 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Develop IDP / Budget (Time schedule of key deadlines (Process Plan) (MSA 28 / MFMA 21) |  |  |  |  | Approved IDP Framework and Process Plan on or before 31 Aug 2023 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 1 |
| D11 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | IDP and Budget Public Participation meetings |  |  |  |  | No. of meetings held before the approval of the IDP and Budget |  |  |  |  |  |  | 3 |  |  |  | 3 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 3 |  |  |  |  |  |  | 3 |  |  |  | 0 |
| D12 |  |  | Embed good governance through sound administrative practices and improved stakeholder relations | GG&PP |  | Compile final IDP (MSA 34) |  |  |  |  | Final IDP approved by Council on or before 30 June 2024 |  |  |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  | 0 |
| D13 |  |  | Embed financial viability and sustainability through good financial management | MFV&M |  | Sound Financial Management |  |  |  |  | No of monthly MFMA Sec 71 Reports presented to the Executive Mayor |  |  |  |  |  |  | 12 |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  | 12 |  |  |  |  |  |  | 12 |  |  |  | 0 |
| REF | IDP OBJECTIVE |  |  | KPA | KPI |  |  | UNIT OF MEASUREMENT |  |  |  |  |  | ANNUAL TARGET |  |  |  |  | ACTUAL |  |  |  |  | VARIANCE |  |  |  |  | REASON FOR DEVIATION |  |  |  |  |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  |  |  |  |  |  |  |  | PRIOR TARGET |  |  |  |  |  | PRIOR ACTUAL |  |  |  |  |  | PRIOR VARIANCE |  |  |  |
|  | FINANCIAL SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D14 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Production of annual Audit file |  |  | No of Audit files produced by mid-August 2023 |  |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |
| D15 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Closing of all municipal financial accounts at the end of each month in terms of sec 65 of the MFMA |  |  | No. of monthly reports on the closing of all municipal financial accounts |  |  |  |  | 12 |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 12 |  |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  |
| D16 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | No of creditors reconciliations done monthly (30 days) |  |  | No of creditors reconciliation reports submitted |  |  |  |  | 12 |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 12 |  |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  |
| D17 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Financial Viability: Cost coverage (Reg 796) |  |  | Cost coverage ((Available cash+ investments)/ Monthly fixed operating expenditure (SA8) |  |  |  |  | >1 |  |  |  |  |  | (0.02%) |  |  |  |  |  | (0.98) |  |  |  | The ratio shows that the municipality does not have sufficient cash to fund its operational |  |  |  |  |  |  | Cash flow management needs to be in place |  |  |  |  |  |  | >1 |  |  |  |  |  |  | 1.08% |  |  |  |  |  | 0.08% |  |  |  |
| D18 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Financial Viability: Debt coverage (Reg 796) |  |  | Debt coverage (Total operating revenue-operating grants received)/debt service payments due within the year) (SA8) |  |  |  |  | >1 |  |  |  |  |  | (0.09) |  |  |  |  |  | (0.91) |  |  |  | Insufficient funds to cover debts. The municipality does not generate own revenue, depends on grants |  |  |  |  |  |  | The municipality does not generate its own revenue, it depends on grants |  |  |  |  |  |  | >1 |  |  |  |  |  |  | 0.03% |  |  |  |  |  | (0.97%) |  |  |  |
| D19 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Monthly notification of awards over R 100 000 |  |  | List of awards |  |  |  |  | 12 |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 12 |  |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  |
| D20 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Effective management of payroll by providing the section 66 payroll report on a monthly basis |  |  | Monthly reports to management in terms of section 66 of the MFMA |  |  |  |  | 12 |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 12 |  |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  |
| D21 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Ensure the submission of IRP5’s |  |  | IRP5’s submitted not later than 30 May 2024 to SARS |  |  |  |  | 1 |  |  |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  |
| D22 | Embed financial viability and sustainability through good financial management |  |  | MFV&M | Monthly salary reconciliations |  |  | No of reconciliations done |  |  |  |  | 12 |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  |  | 12 |  |  |  |  |  |  | 12 |  |  |  |  |  | 0 |  |  |  |
| REF | IDP OBJECTIVE |  |  | KPA | KPI |  |  |  |  | UNIT OF MEASUREMENT |  |  |  |  |  | ANNUAL TARGET |  |  |  |  | ACTUAL |  |  |  |  | VARIANCE |  |  |  |  |  | REASON FOR DEVIATION |  |  |  |  |  | CORRECTIVE MEASURE |  |  |  |  |  |  | PRIOR TARGET |  |  |  |  |  | PRIOR ACTUAL |  |  |  |  |  | PRIOR VARIANCE |  |  |
|  | DIRECTORATE: CORPORATE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D23 | Oversee the achievement of good governance through the implementation of council resolutions |  |  | GG&PP | Draw quarterly resolution execution report for all directorates |  |  |  |  | No. of execution reports where Council resolutions are captured on every sitting of Council |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  | 0 |  |  |  | Council sat as planned in the year under review |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | 4 |  |  |  |  | 6 |  |  |  |  |  | 2 |  |
| D24 | Oversee the achievement of good governance through the implementation of council resolutions |  |  | GG&PP | Ensuring implementation of outstanding Council resolutions |  |  |  |  | Annual Resolution register submitted to Council on or before 30 June 2024 |  |  |  |  |  | 1 |  |  |  |  | 0 |  |  |  |  |  | (0) |  |  |  | Annual Resolution register was not submitted to Council as planned at the end of quarter 4 |  |  |  |  |  |  |  | Annual Resolution register will only be submitted to Council in the next sitting of Council(August 2024) |  |  |  |  |  |  |  | 1 |  |  |  |  | 0 |  |  |  |  |  | (1) |  |
| D25 | To maintain a skilled, capable and diverse workforce in a good working environment |  |  | MT&ID | Development of the Works Skills Plan |  |  |  |  | WSP approved by the LLF and submitted to the LGSETA on or before 30 April 2024 |  |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  |  | 0 |  |
| D26 | Sustain good corporate governance through effective and accountable clean administration |  |  | MT&ID | Provide secured Internet Services |  |  |  |  | Quarterly reports on the supplier’s performance on the effectiveness of Internet Service Provider(ISP) |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  | 0 |  |
| D27 | Sustain good corporate governance through effective and accountable clean administration |  |  | MT&ID | Labour Relations |  |  |  |  | No. of litigation cases instituted against the municipality at the end of the financial year |  |  |  |  |  | 0 |  |  |  |  | 4 |  |  |  |  |  | (4) |  |  |  | The municipality had 4 x litigation cases (as per the litigation register 2023-2024) |  |  |  |  |  |  |  | Maintenance of good relations between the municipality and its clients |  |  |  |  |  |  |  | 0 |  |  |  |  | 3 |  |  |  |  |  | (3) |  |
| D28 | Oversee the achievement of good governance through the implementation of council resolutions |  |  | GG&PP | Anti-fraud and Corruption |  |  |  |  | Number of disciplinary cases for misconduct relating to fraud and corruption |  |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | New KPI |  |  |  |  | New KPI |  |  |  |  |  | New KPI |  |
| D29 | Sustain good corporate governance through effective and accountable clean administration |  |  | MT&ID | Declaration of Interest |  |  |  |  | No. of councillors that have declared their financial interest on or before 30 Sep 2022 |  |  |  |  |  | 16 |  |  |  |  | 16 |  |  |  |  |  | 0 |  |  |  | - |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | 16 |  |  |  |  | 16 |  |  |  |  |  | 0 |  |
| D30 | Coordinate sustainable social livelihood through developmental programmes |  |  | S&CD | Social Responsibility |  |  |  |  | 100% utilization of the Social Responsibility grant by 30 June 2024 |  |  |  |  |  | 100% |  |  |  |  | 101% |  |  |  |  |  | 1% |  |  |  | The budget was overspent just with 1% which is not quite significant |  |  |  |  |  |  |  | - |  |  |  |  |  |  |  | 100% |  |  |  |  | 100% |  |  |  |  |  | 0 |  |
| REF | IDP OBJECTIVE |  |  | KPA | KPI |  | UNIT OF MEASUREMENT |  |  |  |  |  |  |  |  |  | ANNUAL TARGET |  |  |  |  |  | ACTUAL VARIANCE |  |  |  |  |  |  | REASON FOR DEVIATION |  |  |  |  |  |  | CORRECTIVE MEASURE/S TAKEN TO IMPROVE PERFORMANCE |  |  |  |  |  |  |  |  |  | PRIOR TARGET |  |  |  |  | PRIOR ACTUAL |  |  |  |  |  | PRIOR VARIANCE |  |
| PLANNING AND SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D31 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED | Implementation of the Expanded Public Works Programme (EPWP) |  |  |  | No. of quarterly reports on the EPWP progress, grant, staff and wages paid submitted to the MM/ Council |  |  |  |  |  | 4 |  |  |  |  | 3 |  |  |  |  |  |  |  | (2) |  |  |  |  | Although reports were compiled 1 x report was presented to management outside the SDBIP target dates |  |  |  |  |  |  | Line Managers to align their reporting with the approved SDBIP target dates and the schedule of the sitting of management |  |  |  |  |  | 4 |  |  |  |  |  |  | 3 |  |  |  |  |  | (1) |
| D32 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED | Report on the implementation of the EPWP |  |  |  | No. of EPWP steering committee meetings held quarterly |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  | 0 |
| D33 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED | Expenditure of the EPWP Grant |  |  |  | 100% Expenditure by end of June 2024 |  |  |  |  |  | 100% |  |  |  |  | 100% |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 100% |  |  |  |  |  |  | 100% |  |  |  |  |  | 0 |
| D34 |  | Facilitate investment and development of strategic infrastructure to unlock growth and job creation |  | LED | Making tourism awareness to schools and communities |  |  |  | No. of tourism awareness campaigns conducted quarterly |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  | 0 |
| D35 |  | Provide safe and healthy environment for the community |  | BSD&ID | Environmental Health services |  |  |  | No. of Health Education programmes/projects planned |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  | 0 |
| D36 |  | Provide safe and healthy environment for the community |  | BSD&ID | Water quality monitoring |  |  |  | No of quarterly water quality reports submitted to Management |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | Alignment of reporting time frames to the approved SDBIP and the sitting of management |  |  |  |  |  | 4 |  |  |  |  |  |  | 3 |  |  |  |  |  | (1) |
| D37 |  | Provide safe and healthy environment for the community |  | BSD&ID | Waste Management (NEMWA) |  |  |  | No. of quarterly reports to management on the compliance status of landfill sites |  |  |  |  |  | 1 |  |  |  |  | 0 |  |  |  |  |  |  |  | (1) |  |  |  |  | It could not be confirmed that the report on the compliance status of landfill sites was tabled before management |  |  |  |  |  |  | Line Managers to ensure that all their reports presented to management are captured correctly and reflects on the minutes of management |  |  |  |  |  | New KPI |  |  |  |  |  |  | New KPI |  |  |  |  |  | New KPI |
| D38 |  | Provide safe and healthy environment for the community |  | BSD&ID | Food monitoring as per R638 |  |  |  | No. of food premises inspected per local municipality on a quarterly basis |  |  |  |  |  | Kopanong 80 |  |  |  |  | 80 |  |  |  |  |  |  |  | 0 |  |  |  |  | No follow up inspections were done in the year under review |  |  |  |  |  |  | - |  |  |  |  |  | Kopanong 50 |  |  |  |  |  |  | 69 |  |  |  |  |  | 19 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Letsemeng 40 |  |  |  |  | 40 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Letsemeng 40 |  |  |  |  |  |  | 44 |  |  |  |  |  | 4 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Mohokare 40 |  |  |  |  | 40 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Mohokare 40 |  |  |  |  |  |  | 70 |  |  |  |  |  | 30 |
| D39 |  | Provide safe and healthy environment for the community |  | BSD&ID | Water quality monitoring |  |  |  | No of water quality samples collected per local municipality |  |  |  |  |  | Mohokare 72 |  |  |  |  | 66 |  |  |  |  |  |  |  | (6) |  |  |  |  | Water samples could not be taken as planned for the month of July 2023 due to the lapse of the contract of the Service Provider |  |  |  |  |  |  | Appointment of the service provider on time |  |  |  |  |  | Mohokare 72 |  |  |  |  |  |  | 72 |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Letsemeng 108 |  |  |  |  | 99 |  |  |  |  |  |  |  | (9) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Letsemeng 108 |  |  |  |  |  |  | 108 |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Kopanong 216 |  |  |  |  | 198 |  |  |  |  |  |  |  | (18) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Kopanong 216 |  |  |  |  |  |  | 216 |  |  |  |  |  | 0 |
| D40 |  | Provide safe and healthy environment for the community |  | BSD&ID | Improve service delivery to communities |  |  |  | No. of quarterly sanitation(waste water) reports submitted to Management |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 4 |  |  |  |  |  |  | 3 |  |  |  |  |  | (1) |
| D41 |  | Provide safe and healthy environment for the community |  | BSD&ID | Improve service delivery to communities |  |  |  | No of quarterly waste water samples taken per local municipality |  |  |  |  |  | Mohokare 12 |  |  |  |  | 12 |  |  |  |  |  |  |  | 0 |  |  |  |  | All the treatment plants in the 3 local municipalities were accessible in the 2023-2024 financial year hence waste water samples could be taken as planned |  |  |  |  |  |  | - |  |  |  |  |  | Mohokare 12 |  |  |  |  |  |  | 12 |  |  |  |  |  | 0 |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Kopanong 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Kopanong 4 |  |  |  |  |  |  | 3 |  |  |  |  |  | (1) |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Letsemeng 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Letsemeng 4 |  |  |  |  |  |  | 4 |  |  |  |  |  | 0 |
| D42 |  | Provide safe and healthy environment for the community |  | BSD&ID | Environmental Health services |  |  |  | No. of people reached for Health Education programmes |  |  |  |  |  | 200 |  |  |  |  | 1029 |  |  |  |  |  |  |  | 829 |  |  |  |  | More people showed interest in the Health Education programmes |  |  |  |  |  |  | - |  |  |  |  |  | 200 |  |  |  |  |  |  | 699 |  |  |  |  |  | 499 |
| D43 |  | Provide safe and healthy environment for the community |  | BSD&ID | Disaster Management |  |  |  | No. of municipal disaster management advisory forum meetings held (section 51 of the Disaster Management Act 2002) |  |  |  |  |  | 4 |  |  |  |  | 4 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 4 |  |  |  |  |  |  | 4 |  |  |  |  |  | 0 |
| D44 |  | Provide safe and healthy environment for the community |  | BSD&ID | Disaster Management |  |  |  | No. of Disaster Management awareness sessions held in the District |  |  |  |  |  | 2 |  |  |  |  | 2 |  |  |  |  |  |  |  | 0 |  |  |  |  | - |  |  |  |  |  |  | - |  |  |  |  |  | 2 |  |  |  |  |  |  | 2 |  |  |  |  |  | 0 |

The following abbreviations are used in the service delivery targets and performance indicators:

KPA 	-	Key Performance Area

KPI	-	Key Performance Indicator

GGPP	-	Good Governance and Public Participation

MFVM	-	Municipal Financial Viability and Management

MTID	-	Municipal Transformation and Institutional Development

LED	-	Local Economic Development

BSD&ID	-	Basic Service Delivery and Infrastructure Development

MFMA	-	Municipal Finance Management Act 56 of 2003

MSA	-	Municipal Systems Act 32 of 2000

EEA	-	Employment Equity Act 55 of 1998

SDA	-	Skills Development Act 97 of 1998

MPPR	-	Local Government: Municipal Planning and Performance Management Regulations, 2001

MPR	-	Local Government: Municipal Performance Regulations for Municipal Managers and Managers Directly

# CHAPTER 4 – ORGANISATIONAL DEVELOPMENT PERFORMANCE

# (PERFORMANCE REPORT PART II)

INTRODUCTION

Organization Development (OD) is about improving performance at the individual, group, and Municipal organizational levels. It is about improving the organization's ability to effectively respond to changes in its external environment, and it’s about increasing internal capabilities by ensuring the Xhariep District Municipal structures, human resources systems, job designs, communication systems, and leadership/managerial processes fully harness human motivation and help people function to their full potential.

Done well, such improvement can be transformational—producing fundamental changes in the way individuals, groups, and organizations functions.

T4.0.1

## COMPONENT A: INTRODUCTION TO THE MUNICIPAL PERSONNEL

### 4.1	EMPLOYEE TOTALS, TURNOVER AND VACANCIES

| Vacancy Rate: 2023-2024 |  |  |  |
| --- | --- | --- | --- |
| Designations | *Total Approved Posts | *Vacancies (Total time that vacancies exist using fulltime equivalents) | *Vacancies (as a proportion of total posts in each category) |
|  | No. | No. | % |
| Municipal Manager | 1 | 0 | 0% |
| CFO | 1 | 0 | 0% |
| Other S57 Managers (excluding Finance Posts) | 2 | 0 | 0% |
| Other S57 Managers (Finance posts) | 1 | 1 | 100% |
| Managers: Levels 0-3 (excluding Finance Posts) | 13 | 0 | 0% |
| Senior management: Levels 0-3 (Finance posts) | 3 | 0 | 0% |
| Highly skilled supervision: levels 9-12 (excluding Finance posts) | 10 | 2 | 0,2% |
| Highly skilled supervision: levels 9-12 (Finance posts) | 4 | 1 | 25% |
| Total | 35 | 4 | 11.4% |
|  |  |  | T4.1.2 |

| Turn-over Rate |  |  |  |
| --- | --- | --- | --- |
| Details | Total Appointments as of beginning of Financial Year | Terminations during the Financial Year | Turn-over Rate* |
|  | No. | No. |  |
| 2021/2022 | 11 | 10 | 11% |
| 2022/2023 | 4 | 5 | 5.92% |
| 2023/2024 | 13 | 8 | 5.68% |
|  |  |  | T4.1.3 |

## COMPONENT B: MANAGING THE MUNICIPAL WORKFORCE

### 4.3	INJURIES, SICKNESS AND SUSPENSIONS

| Number and Cost of Injuries on Duty |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Type of injury | Injury Leave Taken | Employees using injury leave | Proportion employees using sick leave | Average Injury Leave per employee | Total Estimated Cost |
|  | Days | No. | % | Days | R'000 |
| Required basic medical attention only | 0 | 0 | 0 | 0 | 0 |
| Temporary total disablement | 0 | 0 | 0 | 0 | 0 |
| Permanent disablement | 0 | 0 | 0 | 0 | 0 |
| Fatal | 0 | 0 | 0 | 0 | 0 |
| Total | 0 | 0 | 0 | 0 | 0 |
|  |  |  |  |  | T4.3.1 |

| Number of days and Cost of Sick Leave (excluding injuries on duty |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Salary band | Total sick leave | Proportion of sick leave without medical certification | Employees using sick leave | Total employees in post* | *Average sick leave per Employees | Estimated cost |
|  | Days | % | No. | No. | Days | R' 000 |
| Finance Interns | 14 | 0 | 4 | 5 | 3.5 | 5 384 |
| General Assistants/Maintenance (9-12) | 42 | 0 | 5 | 6 | 7 | 24 217 |
| Drivers/Admin/Clerks(5-8) | 252 | 0 | 4 | 17 | 16 | 317 488 |
| Accountants/Officers/Practitioners(4-6) | 154 | 0 | 3 | 26 | 14 | 577 809 |
| Middle Management (0-3) | 385 | 0 | 1 | 14 | 23 | 623027 |
| MM and S57 | 1 | 0 | 1 | 3 | 0.3 | 5 375 |
| Total | 848 | 0 | 18 | 71 | 14.6 | 1 553 300 |
|  |  |  |  |  |  | T4.3.2 |

| Number and Period of Suspensions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Position | Nature of Alleged Misconduct | Date of Suspension | Details of Disciplinary Action taken or Status of Case and Reasons why not Finalised | Date Finalised |
| Manager Communications | Insolence | 11/03/2024 | The case is finalized and closed with the sanction | 29/07/2024 |
|  |  |  |  | T4.3.5 |

| Disciplinary Action Taken on Cases of Financial Misconduct |  |  |  |
| --- | --- | --- | --- |
| Position | Nature of Alleged Misconduct and Rand value of any loss to the municipality | Disciplinary action taken | Date Finalised |
| No financial misconduct cases were reported in the 2023-2024 financial year |  |  |  |
|  |  |  | T4.3.6 |

### 4.5	SKILLS DEVELOPMENT AND TRAININg

| Financial Competency Development: Progress Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  | A. Total number of officials employed by municipality (Regulation 14(4)(a) and (c)) |  |  | B. Total number of officials employed by municipal entities (Regulation 14(4)(a) and (c) |  | Consolidated: Total of A and B |  | Consolidated: Competency assessments completed for A and B (Regulation 14(4)(b) and (d)) | Consolidated: Total number of officials whose performance agreements comply with Regulation 16 (Regulation 14(4)(f)) |  |  |  | Consolidated: Total number of officials that meet prescribed competency levels (Regulation 14(4)(e)) |  |  |  |
| Financial Officials |  | 12 |  |  | 0 |  | 12 |  | 0 | 0 |  |  |  | 12 |  |  |  |
| Chief financial officer |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  |
| Senior managers |  | 2 |  |  | 0 |  | 2 |  | 0 | 0 |  |  |  | 2 |  |  |  |
| Any other financial officials |  | 3 |  |  | 0 |  | 3 |  | 0 | 0 |  |  |  | 0 |  |  |  |
| Supply Chain Management Officials |  | 1 |  |  | 0 |  | 1 |  | 0 | 0 |  |  |  | 1 |  |  |  |
| Heads of supply chain management units |  | 1 |  |  | 0 |  | 1 |  | 0 | 0 |  |  |  | 1 |  |  |  |
| Supply chain management senior managers |  | 0 |  |  | 0 |  | 0 |  | 0 | 0 |  |  |  | 0 |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | T4.5.2 |  |  |  |
| R'000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management level | Gender |  | Employees as at the beginning of the financial year | Original Budget and Actual Expenditure on skills development 2023-2024 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Learnerships |  |  |  | Skills programmes & other short courses |  |  |  | Other forms of training |  |  | Total |  |  |
|  |  |  | No. | Original Budget |  | Actual |  | Original Budget |  |  | Actual | Original Budget | Actual |  | Original Budget | Actual |  |
| MM and S57 | Female |  | 1 | - |  | - |  | - |  |  | - |  | 20 650.00 |  |  |  |  |
|  | Male |  | 2 | - |  |  |  | - |  |  | - | - | 110 886.30 |  | - | - |  |
| Councillors | Female |  | 1 | - |  | - |  | - |  |  | - | - | 140 715.82 |  | - | - |  |
|  | Male |  | 1 | - |  | - |  | - |  |  | - | - | 54 650.07 |  | - | - |  |
| Managers | Female |  | 4 | - |  | - |  | 5 000.00 |  |  | - | - | 34 333.20 |  | - | - |  |
|  | Male |  | 3 | - |  | - |  | - |  |  | - | - | 116 976.00 |  | - | - |  |
| Professionals | Female |  | 5 | - |  | - |  | 10 000.00 |  |  | - | - | 98 718.40 |  | - | - |  |
|  | Male |  | 1 | - |  | - |  | - |  |  | - | - | 11 444.40 |  | - | - |  |
| Clerks | Female |  | 4 | - |  | - |  | 15 000.00 |  |  | - | - | 102 247.00 |  | - | - |  |
|  | Male |  | 5 | - |  | 35 000.00 |  | 15 000.00 |  |  | - | - | 42 414.40 |  | - | - |  |
| Elementary occupations | Female |  | 2 |  |  | 70 000.00 |  | - |  |  | - | - | - |  | - | - |  |
|  | Male |  | 2 | - |  | 70 000.00 |  | - |  |  | - | - | - |  | - | - |  |
| Sub total | Female |  | 3 | - |  | - |  | - |  |  | - | - | - |  | - | - |  |
|  | Male |  | 4 | - |  | - |  | - |  |  | - | - | - |  | - | - |  |
| Total |  |  | 17 | - |  | 130 000 |  | - |  |  | - | - | 212 000 |  | - | - |  |
| *% and *R value of municipal salaries (original budget) allocated for workplace skills plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  | %* | *R0 |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | T4.5.3 |  |

| Repair and Maintenance Expenditure: 2023-2024 |  |  |  |  |
| --- | --- | --- | --- | --- |
| R' 000 |  |  |  |  |
|  | Original Budget | Adjustment Budget | Actual | Budget variance |
| Repairs and Maintenance Expenditure | 90 | 664 | 633 | 31 |
|  |  |  |  | T5.3.4 |

## COMPONENT D: OTHER FINANCIAL MATTERS

### 5.12	SUPPLY CHAIN MANAGEMENT

SUPPLY CHAIN MANAGEMENT

The Supply Chain Management Policy of the municipality was reviewed to ensure that it is in line with the Municipal Supply Chain Management Regulations, other applicable legislations and guidelines of National Treasury. The reviewed SCM policy of the municipality for 2023/24 financial year was approved by the Council in June 2023. The municipality also developed the Preferential Procurement Policy in line with the new Preferential Procurement Regulation of 2022, which was also part of the policies approved by Council in June 2023.

The municipality (as far as the National Treasury SCM implementation check list is concerned, both quarterly and annually) does not have IT related projects above R10m, hence it has not yet utilized the services of SITA to procure such goods or service; and Lastly, an institutional delegation of powers has to be established in collaboration with Free State Provincial Treasury.

No Councillor is a member of any committee handling Supply Chain processes. All three (3) Officials in Supply Chain have the MFMA minimum competency requirements in 2016.

Non – compliance with Supply Chain Management Policy and other applicable legislations which resulted in irregular expenditure – As a remedial action to this problem, such expenditure to be investigated by MPAC, consequence management to be implemented and the SCM checklist to be reviewed and implemented effectively to ensure for an example, that all transactions, prior to awarding, are given to suppliers/service providers that are CSD compliant and/or comply with all the necessary bidding requirements.

T5.12.1

# CHAPTER 6 – AUDITOR GENERAL AUDIT FINDINGS

## COMPONENT A: AUDITOR-GENERAL OPINION OF FINANCIAL STATEMENTS 2023-2024

| Auditor-General Report on Financial Performance 2023-2024 |  |
| --- | --- |
| Audit Report Status*: | Unqualified Opinion ( 2023 – 2024) |
| Non-Compliance Issues | Remedial Action Taken |
| - Annual Financial Statement | Ensuring that AFS are represented accurately, objectively and in compliance with the applicable accounting framework and reporting standards. |
| - Expenditure Management | Strengthen/review internal controls and business processes to ensure that payments being made within a period of 30 days are adhered to. |
| - Consequence management | Management will engage with MPAC and Provincial Treasury to advise on historical UIFW. |
| - Procurement and Contract Management. | Monitor compliance with laws and regulations concerning SCM procurement and contract management to reduce irregular expenditure and non-compliance. |
| - Utilization of Conditional Grants | Monitoring of action plan on a monthly basis and provide evidence on progress made. |
|  | T6.1.1 |

| Auditor-General Report on Financial Performance 2023/2024 |  |
| --- | --- |
| Status of audit report: Unqualified |  |
| Annual financial statements: Unqualified (with findings on compliance matters) |  |
| Please refer to the report of the Auditor General below for more details | T6.2.1 |

## COMPONENT B: AUDITOR-GENERAL OPINION 2023-2024 (CURRENT YEAR)

Report of the auditor-general to the Free State Legislature and the council on the Xhariep District Municipality

## Report on the audit of the financial statementsOpinion

Report on the audit of the financial statements

- Opinion

1. I have audited the financial statements of the Xhariep District Municipality set out on pages xx to xx which comprise the statement of financial position as at 30 June 2024, statement of financial performance, statement of changes in net assets, cash flow statement and statement of comparison of budget and actual amounts for the year then ended, as well as notes to the financial statements, including a summary of significant accounting policies.

2. In my opinion, the financial statements present fairly, in all material respects, the financial position of the Xhariep District Municipality as at 30 June 2024 and its financial performance and cash flows for the year then ended in accordance with the Standards of Generally Recognised Accounting Practice (GRAP) and the requirements of the Municipal Finance Management Act 56 of 2003 (MFMA) and the Division of Revenue Act 5 of 2023 (Dora).

- Basis for opinion

3. I conducted my audit in accordance with the International Standards on Auditing (ISAs). My responsibilities under those standards are further described in the responsibilities of the auditor-general for the audit of the financial statements section of my report.

4. I am independent of the municipality in accordance with the International Ethics Standards Board for Accountants' International code of ethics for professional accountants (including International Independence Standards) (IESBA code) as well as other ethical requirements that are relevant to my audit in South Africa. I have fulfilled my other ethical responsibilities in accordance with these requirements and the IESBA code.

5. I believe that the audit evidence I have obtained is sufficient and appropriate to provide a basis for my opinion.

- Emphasis of matters

- 6. I draw attention to the matters below. My opinion is not modified in respect of these matters.

- Close calls relating to going concern

- 7. Note 35 in the financial statements, which deals with the possible effects of the future implications of continuing deterioration in operational results on the municipality’s prospects, performance, and cash flows.

- Unauthorised expenditure

- 8. As disclosed in note 37 to the financial statements unauthorised expenditure of R12 670 102 (2023: R6 724 033) was incurred, due to overspending of the budget.

- Irregular expenditure

- 9. As disclosed in note 39 to the financial statements, irregular expenditure of R4 168 088 (2023: R1 295 694) was incurred, due to non-compliance with supply chain management (SCM) requirements.

- Restatement of corresponding figures

- 10. As disclosed in note 46 to the financial statements, the corresponding figures for 30 June 2023 were restated as a result of errors in the financial statements of the municipality at, and for the year ended, 30 June 2024.

- Other matters

- 11. I draw attention to the matter below. My opinion is not modified with respect to this matter.

- Unaudited disclosure notes

- 12. In terms of section 125(2)(e) of the MFMA, the particulars of non-compliance with the MFMA should be disclosed in the financial statements. This disclosure requirement did not form part of the audit of the financial statements and, accordingly, I do not express an opinion on it.

- Responsibilities of the accounting officer for the financial statements

- 13. The accounting officer is responsible for the preparation and fair presentation of the financial statements in accordance with the Standards of GRAP and the requirements of the MFMA and Dora; and for such internal control as the accounting officer determines is necessary to enable the preparation of financial statements that are free from material misstatement, whether due to fraud or error.

- 14. In preparing the financial statements, the accounting officer is responsible for assessing the municipality’s ability to continue as a going concern; disclosing, as applicable, matters relating to going concern; and using the going concern basis of accounting unless the appropriate governance structure either intends to liquidate the municipality or to cease operations, or has no realistic alternative but to do so.

- Responsibilities of the auditor-general for the audit of the financial statements

- 15. My objectives are to obtain reasonable assurance about whether the financial statements as a whole are free from material misstatement, whether due to fraud or error; and to issue an auditor’s report that includes my opinion. Reasonable assurance is a high level of assurance but is not a guarantee that an audit conducted in accordance with the ISAs will always detect a material misstatement when it exists. Misstatements can arise from fraud or error and are considered material if, individually or in aggregate, they could reasonably be expected to influence the economic decisions of users taken on the basis of these financial statements.

- 16. A further description of my responsibilities for the audit of the financial statements is included in the annexure to this auditor’s report. This description, which is located at page 11, forms part of our auditor’s report.

- Report on the annual performance report

17.  In accordance with the Public Audit Act 25 of 2004 (PAA) and the general notice issued in terms thereof, I must audit and report on the usefulness and reliability of the reported performance information against predetermined objectives for the selected material performance indicators presented in the annual performance report. The accounting officer is responsible for the preparation of the annual performance report.

18.  I selected the following material performance indicators related to basic service delivery and infrastructure development presented in the annual performance report for the year ended 30 June 2024. I selected those indicators that measure the municipality's performance on its primary mandated functions and that are of significant national, community or public interest.

- Ensure that the water quality tests are done on quarterly basis.

- Total number of water samples tested.

- Number of water samples tests that complied with SANS 241 requirements

- Total waste water samples tested for all determinants over the municipal financial year

- Number of waste water samples tested per determinant that meet compliance to specified water use license requirements

- Percentage of RRAMS spent on quarterly basis

- Number of report to management/council on implementation of RRAMs project

- Number of reports on funeral parlours compliance status

- Number of food premises inspected per local municipality

- 19. Number of water quality samples collected per local municipality

- Number of quarterly waste water taken per local municipality

- 20. I evaluated the reported performance information for the selected material performance indicators against the criteria developed from the performance management and reporting framework, as defined in the general notice. When an annual performance report is prepared using these criteria, it provides useful and reliable information and insights to users on the municipality’s planning and delivery on its mandate and objectives.

- 21. I performed procedures to test whether:

- the indicators used for planning and reporting on performance can be linked directly to the municipality’s mandate and the achievement of its planned objectives

- all the indicators relevant for measuring the municipality’s performance against its primary mandated and prioritised functions and planned objectives are included

- the indicators are well defined to ensure that they are easy to understand and can be applied consistently, as well as verifiable so that I can confirm the methods and processes to be used for measuring achievements

- the targets can be linked directly to the achievement of the indicators and are specific, time bound and measurable to ensure that it is easy to understand what should be delivered and by when, the required level of performance as well as how performance will be evaluated

- the indicators and targets reported on in the annual performance report are the same as those committed to in the approved initial or revised planning documents

- the reported performance information is presented in the annual performance report in the prescribed manner.

- there is adequate supporting evidence for achievements reported and for the measures taken to improve performance.

- 22. I performed the procedures for the purpose of reporting material findings only; and not to express an assurance opinion or conclusion.

- 23. I did not identify any material findings on the reported performance information for the selected indicators.

- Other matters

- 24. I draw attention to the matters below.

- Achievement of planned targets

- 25. The annual performance report includes information on reported achievements against planned targets and provides measures taken to improve performance.

- 26. The table that follows provides information on the achievement of planned targets and lists the key service delivery indicators that were not achieved as reported in the annual performance report. The measures taken to improve performance are included in the annual performance report on pages xx to xx.

- Basic service delivery and infrastructure development

| Targets achieved: 35% Budget spent: Undeterminable/Unknown The budget spent is not available as the municipality's actual spending is not aligned with their key performance areas( programmes) |  |  |
| --- | --- | --- |
| Key service delivery indicator not achieved | Planned target | Reported achievement |
| Ensure that water quality tests are done on a quarterly basis | 4 | 3 |
| Total number of water samples tested | 396 | 363 |
| Number of water sample tests that complied with SANS 241 requirements | 396 | 306 |
| Number of wastewater samples tested per determinant that meet compliance to specified water use license requirements | 20 | 0 |
| No. of reports to Management/ Council on the implementation of the RRAMS project | 4 | 0 |
| No of water quality samples collected per local municipality (Mohokare) | 72 | 66 |
| No of water quality samples collected per local municipality (Letsemeng) | 108 | 99 |
| No of water quality samples collected per local municipality (Kopanong) | 216 | 198 |

- Material misstatements

- 27. I identified material misstatements in the annual performance report submitted for auditing. These material misstatements were in the reported performance information for basic service delivery and infrastructure development. Management subsequently corrected all the misstatements, and I did not include any material findings in this report.

- Report on compliance with legislation

- 28. In accordance with the PAA and the general notice issued in terms thereof, I must audit and report on compliance with applicable legislation relating to financial matters, financial management and other related matters. The accounting officer is responsible for the municipality’s compliance with legislation.

- 29. I performed procedures to test compliance with selected requirements in key legislation in accordance with the findings engagement methodology of the Auditor-General of South Africa (AGSA). This engagement is not an assurance engagement. Accordingly, I do not express an assurance opinion or conclusion.

- 30. Through an established AGSA process, I selected requirements in key legislation for compliance testing that are relevant to the financial and performance management of the municipality, clear to allow consistent measurement and evaluation, while also sufficiently detailed and readily available to report in an understandable manner. The selected legislative requirements are included in the annexure to this auditor’s report.

- 31. The material findings on compliance with the selected legislative requirements, presented per compliance theme, are as follows:

- Expenditure management

32. Reasonable steps were not taken to prevent irregular expenditure amounting to R4 168 088 (2023: R1 295 694) as disclosed in note 39 to the annual financial statements, as required by section 62(1)(d) of the MFMA. The majority of the irregular expenditure was caused by non compliance with SCM requirements.

33. Reasonable steps were not taken to prevent unauthorised expenditure amounting to

R12 670 102 (2023: R6 724 033) as disclosed in note 37 to the annual financial statements, as required by section 62(1)(d) of the MFMA. The majority of the unauthorised expenditure was caused by overspending of the budget.

34. Reasonable steps were not taken to prevent fruitless and wasteful expenditure amounting to R255 704 (2023: R398 286) as disclosed in note 38 to the annual financial statements, as required by section 62(1)(d) of the MFMA. The majority of the disclosed fruitless and wasteful expenditure was caused by interest and penalties charged on late payments. ts.

35. Payments were made from the municipality's bank accounts without the approval of a properly authorised official, as required by section 11(1) of the MFMA.

36. Money owed by the municipality was not always paid within 30 days, as required by section 65(2)(e) of the MFMA.

- Annual financial statements and annual report

37. The financial statements submitted for auditing were not fully prepared in all material respects in accordance with the requirements of section 122(1) of the MFMA. Material misstatements of current assets, current liabilities, revenue, expenditure and disclosure items identified by the auditors in the submitted financial statement were subsequently corrected and the supporting records were provided subsequently, resulting in the financial statements receiving an unqualified audit opinion.

- Consequence management

38. Unauthorised expenditure incurred by the municipality was not investigated to determine if any person is liable for the expenditure, as required by section 32(2)(a) of the MFMA.

39. Irregular expenditure incurred by the municipality were not investigated to determine if any person is liable for the expenditure, as required by section 32(2)(b) of the MFMA.

40. Fruitless and wasteful expenditure incurred by the municipality were not investigated to determine if any person is liable for the expenditure, as required by section 32(2)(b) of the MFMA.

- Utilisation of conditional grants

- 41. Performance in respect of programmes funded by Integrated National Electrification Program (INEP) was not evaluated within two months after the end of the financial year, as required by section 12(5) DORA.

- 42. The Rural Roads Asset Management System (RRAMS) grant was not spent for its intended purposes in accordance with the applicable grant framework, as required by section 16(1) of DORA.

- 43. The Municipal Infrastructure Grant was not spent for its intended purposes in accordance with the applicable grant framework, as required by section 16(1) of DORA.

- Procurement and contract management

- 44. Some of the contracts were awarded to bidders based on points given for legislative requirement that differed from those stipulated in the original invitation for bidding, in contravention of SCM regulations 21(b) and 28(1)(a)(i )and the Preferential Procurement Regulations.

- 45. Sufficient appropriate audit evidence could not be obtained that the performance of contractors or providers was monitored monthly as required by section 116(2) of the MFMA.

- 46. Sufficient appropriate audit evidence could not be obtained that contract performance and monitoring measures were in place to ensure effective contract management as required by section 116(2)(c)(ii) of the MFMA.

- Other information in the annual report

47. The accounting officer is responsible for the other information included in the annual report. The other information referred to does not include the financial statements, the auditor's report and those selected material indicators in the scoped-in key performance area (KPA) presented in the annual performance report that has been specifically reported on in this auditor's report.

- 48. My opinion on the financial statements, the report on the audit of the annual performance report and the report on compliance with legislation do not cover the other information included in the annual report and I do not express an audit opinion or any form of assurance conclusion on it.

- 49. My responsibility is to read this other information and, in doing so, consider whether it is materially inconsistent with the financial statements and the selected material indicators in the scoped-in KPA presented in the annual performance report or my knowledge obtained in the audit, or otherwise appears to be materially misstated.

- 50. I did not receive the other information before the date of this auditor’s report. When I do receive and read this information, if I conclude that there is a material misstatement therein, I am required to communicate the matter to those charged with governance and request that the other information be corrected. If the other information is not corrected, I may have to retract this auditor’s report and re-issue an amended report as appropriate. However, if it is corrected this will not be necessary.

- Internal control deficiencies

- 51. I considered internal control relevant to my audit of the financial statements, annual performance report and compliance with applicable legislation; however, my objective was not to express any form of assurance on it.

- 52. The matters reported below are limited to the significant internal control deficiencies that resulted in the basis for the opinion and the material findings on the selected material indicators included in the annual performance report and the material findings on compliance with legislation included in this report.

53.  Management did not review compliance with the relevant laws and regulations, which resulted in material non compliance being reported.

- Lack of adequate controls over daily and monthly processing and reconciling transactions.

54. Management did not prepare financial statements that were accurate, and were evidenced by the reliable supporting documentation, in addition to this, management did not review internal controls effectiveness in detection, correction and prevention of these deficiencies and this resulted in repeat findings due to non-adherence to the audit action plan.

The audit committee did not ensure that the internal audit unit is adequately resourced which resulted in the unit not being able to enhance the internal controls of the municipality as they could not perform all planned audits per the audit plan.

ANNEXURE TO THE AUDITOR’S REPORT

- The annexure includes the following:

  - The auditor-general's responsibility for the audit

  - The selected legislative requirements for compliance testing

Auditor-General’s responsibility for the audit

Professional judgement and professional scepticism

- As part of an audit in accordance with the ISAs, I exercise professional judgement and maintain professional scepticism throughout my audit of the financial statements and the procedures performed on reported performance information for selected material performance indicators and on the municipality's compliance with selected requirements in key legislation.

Financial Statements

- In addition to my responsibility for the audit of the financial statements as described in this auditor's report, I also:

  - identify and assess the risks of material misstatement of the financial statements, whether due to fraud or error; design and perform audit procedures responsive to those risks; and obtain audit evidence that is sufficient and appropriate to provide a basis for my opinion. The risk of not detecting a material misstatement resulting from fraud is higher than for one resulting from error, as fraud may involve collusion, forgery, intentional omissions, misrepresentations, or the override of internal control

  - obtain an understanding of internal control relevant to the audit in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the municipality's internal control

  - evaluate the appropriateness of accounting policies used and the reasonableness of accounting estimates and related disclosures made

  - conclude on the appropriateness of the use of the going concern basis of accounting in the preparation of the financial statements. I also conclude, based on the audit evidence obtained, whether a material uncertainty exists relating to events or conditions that may cast significant doubt on the ability of the municipality to continue as a going concern. If I conclude that a material uncertainty exists, I am required to draw attention in my auditor's report to the related disclosures in the financial statements about the material uncertainty or, if such disclosures are inadequate, to modify my opinion on the financial statements. My conclusions are based on the information available to me at the date of this auditor's report. However, future events or conditions may cause a municipality to cease operating as a going concern

  - evaluate the overall presentation, structure and content of the financial statements, including the disclosures, and determine whether the financial statements represent the underlying transactions and events in a manner that achieves fair presentation.

Communication with those charged with governance

- I communicate with the accounting officer regarding, among other matters, the planned scope and timing of the audit and significant audit findings, including any significant deficiencies in internal control that I identify during my audit.

- I also provide the accounting officer with a statement that I have complied with relevant ethical requirements regarding independence and communicate with them all relationships and other matters that may reasonably be thought to bear on my independence and, where applicable, actions taken to eliminate threats or safeguards applied.

Compliance with legislation - selected legislative requirements

The selected legislative requirements are as follows:

| Legislation | Sections or regulations |  |
| --- | --- | --- |
| Municipal Finance Management Act 56 of 2003 | Sections: 1, 11(1), 13(2), 14(1), 14(2)(a), 14(2)(b), 15, 24(2)(c)(iv), 28(1), 29(1), Sections: 29(2)(b), 32(2), 32(2)(a), 32(2)(a)(i), 32(2)(a)(ii), 32(2)(b), 32(6)(a), Sections: 32(7), 53(1)(c)(ii), 54(1)(c), 62(1)(d), 63(2)(a), 63(2)(c), 64(2)(b), Sections :64(2)(c), 64(2)(e), 64(2)(f), 64(2)(g), 65(2)(a), 65(2)(b), 65(2)(e), Sections: 72(1)(a)(ii), 112(1)U), 116(2)(b), 116(2)(c)(ii), 117, 122(1), 122(2), Sections: 126(1)(a) 126(1)(b), 127(2), 127(5)(a)(i), 127(5)(a)(ii), 129(1), 129(3), Sections: 133(1)(a), 133(1)(c)(i), 133(1)(c)(ii), 170, 171(4)(a), 171(4)(b) |  |
| MFMA: Municipal Budget and Reporting Regulations, 2009 | Regulations 71(1)(a), 71(1)(a)(b), 71(2)(a), 71(2)(b), 71(2)(d), 72(a), 72(b), 72(c) |  |
| MFMA: Municipal Investment Regulations, 2005 | Regulations 3(1)(a), 3(3), 6, 7, 12(2), 12(3) |  |
| MFMA: Municipal Regulations on Financial Misconduct Procedures and Criminal Proceedings, 2014 | Regulations 5(4), 6(8)(a), 6(8)(b), 10(1) |  |
| MFMA: Municipal Supply Chain Management Regulations, 2017 | Regulations 5, 12(1)(c), 12(3), 13(b), 13(c), 16(a), 17(1)(a), 17(1)(b), 17(1)(c), Regulations: 19(a), 21(b), 22(1)(b)(i), 22(2), 27(2)(a), 27(2)(e), 28(1)(a)(i), Regulations: 29(1)(a), 29(1)(b), 29(5)(a)(ii), 29(5)(b)(ii), 32, 36(1), 36(1)(a), Regulations: 38(1)(c), 38(1)(d)(ii), 38(1)(e), 38(1)(g)(i) , 38(1)(g)(ii), 38(1)(g)(iii), Regulations: 43, 44, 46(2)(e), 46(2)(f) |  |
| MSA: Municipal Staff Regulations | Regulations 7(1), 31 |  |
| Municipal Systems Act 32 of 2000 (MSA) | Sections 25(1), 26(a), 26(c), 26(h), 26(i), 29(1)(b)(ii), 34(a), 34(b), 38(a), Sections: 41(1)(a), 41(1)(b), 41(1)(c)(ii), 42, 43(2), 54A(1)(a), 56(1)(a), 57(2)(a), Sections: 57(6)(a), 66(1)(a), 66(1)(b), 67(1)(d), 74(1), 96(b) |  |
| MSA: Municipal Planning and Performance Management Regulations, 2001 | Regulations 2(1)(e), 2(3)(a), 3(3), 3(4)(b), 7(1), 8, 9(1)(a), 10(a), 12(1) Regulations 15(1)(a)(i), 15(1)(a)(ii) |  |
| Legislation |  | Sections or regulations |
| MSA: Municipal Performance Regulations for Municipal Managers and Managers Directly Accountable to Municipal Managers, 2006 |  | Regulations 2(3)(a), 4(4)(b), 8(1), 8(2), 8(3) |
| MSA: Regulations on Appointment and Conditions of Employment of Senior Managers, 2014 |  | Regulations 17(2), 36(1)(a) |
| MSA: Disciplinary Regulations for Senior Managers, 2011 |  | Regulations 5(2), 5(3), 5(6), 8(4) |
| Division of Revenue Act 5 of2023 |  | Sections 11(6)(b), 12(5), 16(1); 16(3) |
| Construction Industry Development Board Act 38 of2000 |  | Section 18(1) |
| Construction Industry Development Board Regulations, 2004 |  | Regulations 17, 25(7A) |
| Municipal Property Rates Act 6 of 2004 |  | Section 3(1) |
| Preferential Procurement Policy Framework Act 5 of 2000 |  | Sections 2(1)(a), 2(1)(f) |
| Preferential Procurement Regulations, 2017 |  | Regulations 4(1), 4(2), 5(1), 5(3), 5(6), 5(7), 6(1), 6(2), 6(3), 6(6), 6(8), 7(1) Regulations 7(2), 7(3), 7(6), 7(8), 8(2), 8(5), 9(1), 10(1), 10(2), 11(1), 11(2) |
| Preferential Procurement Regulations, 2022 |  | Regulations 4(1), 4(2), 4(3), 4(4), 5(1), 5(2), 5(3), 5(4) |
| Prevention and Combating of Corrupt Activities Act 12 of 2004 |  | Section 34(1) |

# GLOSSARY

| Accessibility indicators | Explore whether the intended beneficiaries are able to access services or outputs. |
| --- | --- |
| Accountability documents | Documents used by executive authorities to give “full and regular” reports on the matters under their control to Parliament and provincial legislatures as prescribed by the Constitution. This includes plans, budgets, in-year and Annual Reports. |
| Activities | The processes or actions that use a range of inputs to produce the desired outputs and ultimately outcomes. In essence, activities describe "what we do". |
| Adequacy indicators | The quantity of input or output relative to the need or demand. |
| Annual Report | A report to be prepared and submitted annually based on the regulations set out in Section 121 of the Municipal Finance Management Act. Such a report must include annual financial statements as submitted to and approved by the Auditor-General. |
| Approved Budget | The annual financial statements of a municipality as audited by the Auditor General and approved by council or a provincial or national executive. |
| Baseline | Current level of performance that a municipality aims to improve when setting performance targets. The baseline relates to the level of performance recorded in a year prior to the planning period. |
| Basic municipal service | A municipal service that is necessary to ensure an acceptable and reasonable quality of life to citizens within that particular area. If not provided it may endanger the public health and safety or the environment. |
| Budget year | The financial year for which an annual budget is to be approved – means a year ending on 30 June. |
| Cost indicators | The overall cost or expenditure of producing a specified quantity of outputs. |
| Distribution indicators | The distribution of capacity to deliver services. |
| Financial Statements | Includes at least a statement of financial position, statement of financial performance, cash-flow statement, notes to these statements and any other statements that may be prescribed. |
| General Key performance indicators | After consultation with MECs for local government, the Minister may prescribe general key performance indicators that are appropriate and applicable to local government generally. |
| Impact | The results of achieving specific outcomes, such as reducing poverty and creating jobs. |
| Inputs | All the resources that contribute to the production and delivery of outputs. Inputs are "what we use to do the work". They include finances, personnel, equipment and buildings. |
| Integrated Development Plan (IDP) | Set out municipal goals and development plans. |
| National Key performance areas | - Service delivery & infrastructure - Economic development - Municipal transformation and institutional development - Financial viability and management - Good governance and community participation |
| Outcomes | The medium-term results for specific beneficiaries that are the consequence of achieving specific outputs. Outcomes should relate clearly to an institution's strategic goals and objectives set out in its plans. Outcomes are "what we wish to achieve". |
| Outputs | The final products, or goods and services produced for delivery. Outputs may be defined as "what we produce or deliver". An output is a concrete achievement (i.e. a product such as a passport, an action such as a presentation or immunization, or a service such as processing an application) that contributes to the achievement of a Key Result Area. |
| Performance Indicator | Indicators should be specified to measure performance in relation to input, activities, outputs, outcomes and impacts. An indicator is a type of information used to gauge the extent to which an output has been achieved (policy developed, presentation delivered, service rendered) |
| Performance Information | Generic term for non-financial information about municipal services and activities. Can also be used interchangeably with performance measure. |
| Performance Standards: | The minimum acceptable level of performance or the level of performance that is generally accepted. Standards are informed by legislative requirements and service-level agreements. Performance standards are mutually agreed criteria to describe how well work must be done in terms of quantity and/or quality and timeliness, to clarify the outputs and related activities of a job by describing what the required result should be. In this EPMDS performance standards are divided into indicators and the time factor. |
| Performance Targets: | The level of performance that municipalities and its employees strive to achieve. Performance Targets relate to current baselines and express a specific level of performance that a municipality aims to achieve within a given time period. |
| Service Delivery Budget Implementation Plan | Detailed plan approved by the mayor for implementing the municipality’s delivery of services; including projections of the revenue collected and operational and capital expenditure by vote for each month. Service delivery targets and performance indicators must also be included. |
| Vote: | One of the main segments into which a budget of a municipality is divided for appropriation of money for the different departments or functional areas of the municipality. The Vote specifies the total amount that is appropriated for the purpose of a specific department or functional area. Section 1 of the MFMA defines a “vote” as: a) one of the main segments into which a budget of a municipality is divided for the appropriation of money for the different departments or functional areas of the municipality; and b) which specifies the total amount that is appropriated for the purposes of the department or functional area concerned |

# APPENDICES

## APPENDIX A – COUNCILLORS; COMMITTEE ALLOCATION AND COUNCIL ATTENDANCE

| Councillors, Committees Allocated and Council Attendance |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Council Members | Full Time / Part Time | Committees Allocated | *Ward and/ or Party Represented | Percentage Council Meetings Attendance |  |
|  | FT/PT |  |  | % |  |
| Cllr AM Shasha | FT | Speaker | ANC | 100% |  |
| Cllr.NI Mehlomakulu | FT | Executive Mayor | ANC | 100% |  |
| Cllr NJ Garekoe | FT | Chairperson of Corporate Services Committee | ANC | 80% |  |
| Cllr AM Molai | FT | Budget and Treasury Committee Member | EFF | 100% |  |
| Cllr TI Phatsoane | FT | Chairperson of MPAC | ANC | 100% |  |
| Cllr AJJ Van Rensburg | FT | Planning and Social Development Committee Member | DA | 60% |  |
| Cllr AM Lebaka | FT | Chairperson of Budget and Treasury Committee Member | ANC | 90% |  |
| Cllr MG Mokheseng | PT | Corporate Services Committee member | ANC | 100% |  |
| Cllr RW Van Wyk | PT | Planning and Social Development Committee member | DA | 80% |  |
| Cllr MV Malgas | PT | Budget and Treasury Committee member | ANC | 80% |  |
| Cllr ME Lekoenea | PT | Corporate Services committee member | EEF | 60% |  |
| Cllr AN November | FT | MPAC Member | DA | 60% |  |
| Cllr TD Mochechepa | FT | Chairperson of Planning and Social Development | ANC | 90% |  |
| Cllr MM Potgieter | PT | Corporate Services committee member | DA | 100% |  |
| Cllr S Riddle | PT | MPAC member | DA | 80% |  |
| Cllr NA Adoons | PT | Planning and Social Development committee member | ANC | 100% |  |
| Note: * Councillors appointed on a proportional basis do not have wards allocated to them |  |  |  |  | T A |

## APPENDIX B – COMMITTEES AND COMMITTEE PURPOSES

| Committees (other than Mayoral / Executive Committee) and Purposes of Committees |  |  |
| --- | --- | --- |
| Municipal Committees | Purpose of Committee |  |
| Oversight Committee | Playing an oversight Role over the finances and the administration of the Municipality |  |
| Audit Committee | Performing duties as stipulated in Section 166 of the MFMA |  |
| MPAC | Playing an oversight Role over the finances and the administration of the Municipality |  |
|  |  | T B |

## APPENDIX D – FUNCTIONS OF MUNICIPALITY / ENTITY

| Municipal / Entity Functions |  |  |
| --- | --- | --- |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No)* | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 4, Part B functions: |  |  |
| Air pollution | Yes |  |
| Building regulations | No |  |
| Child care facilities | Yes |  |
| Electricity and gas reticulation | No |  |
| Firefighting services | No |  |
| Local tourism | Yes |  |
| Municipal airports | No |  |
| Municipal planning | Yes |  |
| Municipal health services | Yes |  |
| Municipal public transport | No |  |
| Municipal public works only in respect of the needs of municipalities in the discharge of their responsibilities to administer functions specifically assigned to them under this Constitution or any other law | No |  |
| Pontoons, ferries, jetties, piers and harbours, excluding the regulation of international and national shipping and matters related thereto | No |  |
| Storm water management systems in built-up areas | No |  |
| Trading regulations | No |  |
| Water and sanitation services limited to potable water supply systems and domestic waste-water and sewage disposal systems | Yes |  |
| Continued next page |  |  |
| Continued from previous page |  |  |
| Municipal / Entity Functions |  |  |
| MUNICIPAL FUNCTIONS | Function Applicable to Municipality (Yes / No)* | Function Applicable to Entity (Yes / No) |
| Constitution Schedule 5, Part B functions: |  |  |
| Beaches and amusement facilities | No |  |
| Billboards and the display of advertisements in public places | No |  |
| Cemeteries, funeral parlours and crematoria | Yes |  |
| Cleansing | No |  |
| Control of public nuisances | No |  |
| Control of undertakings that sell liquor to the public | No |  |
| Facilities for the accommodation, care and burial of animals | No |  |
| Fencing and fences | No |  |
| Licensing of dogs | No |  |
| Licensing and control of undertakings that sell food to the public | No |  |
| Local amenities | No |  |
| Local sport facilities | No |  |
| Markets | No |  |
| Municipal abattoirs | No |  |
| Municipal parks and recreation | No |  |
| Municipal roads | Yes |  |
| Noise pollution | Yes |  |
| Pounds | No |  |
| Public places | No |  |
| Refuse removal, refuse dumps and solid waste disposal | No |  |
| Street trading | No |  |
| Street lighting | No |  |
| Traffic and parking | No |  |
| * If municipality: indicate (yes or No); * If entity: Provide name of entity |  | T D |

## APPENDIX G – RECOMMENDATIONS OF THE MUNICIPAL AUDIT COMMITTEE 2023-2024

| Municipal Audit Committee Recommendations |  |  |
| --- | --- | --- |
| Date of Committee | Committee recommendations during 2022-2023 | Recommendations adopted (enter Yes) If not adopted (provide explanation) |
| 25 August 2023 29 September 2023 27 November 2023 18 April 2023 | - After that, the Audit Committee resolved that the 2nd set of AFS be submitted to Audit Committee Members and final AFS be reviewed by the Internal Audit Unit and Members prior to submission to AGSA on the 31st August 2023FSPT proposed that Municipality write a letter to them requesting a reviewer. - After that, the Audit Committee resolved to have MS-Teams meeting with Management regarding the APR The Committee resolved that going forward, in the next review of the strategic documents there should be a note where changes took place. - Audit Committee Members approves the Three Year Rolling Plan and Annual Internal Audit Plan for 2023 – 2024 pending finalization of the inputs made and be circulated to Audit Committee Members. - The Audit Committee recommended that the Audit Committee Charter be approved subjected to changes made and be Audit Committee Charter be submitted to Council for approval with those changes. - Audit Committee members approves the Internal Audit Charter for 2023 – 2024. - Audit Committee members approves Policies and Procedure Manual for 2023 – 2024. - Audit Committee members approves Combined Assurance for 2023 – 2024. - Audit Committee members approves Quality Assurance Improvement Program for 2023 – 2024 - Audit Committee members approves Internal Audit Methodology for 2023 – 2024. - Audit Committee members approves Audit Committee Schedule for the Audit Committee for 2023 – 2024 with changes made. - Audit Committee approves the Progress report for Internal Audit Activities with changes proposed for the 1st Quarter of 2023 – 2024. - Audit Committee Approves the 4th Quarter Report on PMS. - Audit Committee approves the Annual Performance Report for municipality. - Audit Committee resolved that Risk Champion to be appointed and be reported in the Next Audit Committee meeting and Internal Audit Manager performs a follow up audit on that finding. - Audit Committee member noted the report of Risk Management Committee and the report will be presented to Council in December 2023. - The Committee resolved that Management must submit the Budget and ensure that Cash Flow Statement is addressed adequately. - The Committee resolved that all minutes be signed by the Chairperson. - Audit Committee resolved that Management should appoint the Intern Internal Audit would be appointed before financial year end. - Audit Committee need management to be fully engaged so that all work done by auditors can be concluded on time. - The Audit Committee resolved that the additional of the Audit Committee be appointed. - The Audit Committee Members approved all Internal Audit Reports with changes made by FSPT. - The Audit Committee approved the Strategic Documents for 2024 -2025 with changes proposed and a report be tabled to Council. - The Audit Committee resolved that INEP & MIG should be separated from total revenue collected. - The Audit Committee Members noted the Functionality Report and that the Chairperson to cover IT Governance in reporting as part of MFMA. |  |
|  |  | T G |

## APPENDIX H – LONG TERM CONTRACTS

| Long Term Contracts (Largest Contracts Entered into 2023-2024 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| R' 000 |  |  |  |  |  |
| Name of Service Provider (Entity or Municipal Department) | Description of Services Rendered by the Service Provider | Start Date of Contract | Expiry date of Contract | Project manager | Contract Value |
| Purim Consulting | Rural roads asset management system | 06 Oct 23 | 30 Sep 2026 | Mr SL Majenge | 7 078 407.08 |
| LQ Technologies | Internet Service Provision | 16 Sep 2020 | Contract ended on the 30th of November 2023 | Mr A. Tyhokolo | 1,315,887.35 |
| University of the Free State Ground Water Testing | Waste and Drinking Water Analysis | 04 Aug 23 | 31 Jul 2024 | Me Portia Mancoe | 237 929.00 |
| Musar Consulting PTY LTD | Internet Service Provision | 05 Dec 2023 | 30 Nov 2026 | Mr A Tyhokolo | 1,537,744.88 |
| Lobamaba Enterprise (PTY)LTD | Supply and Maintenance of Telephone Systems | 25 Feb 2022 | Feb 25 | Mr A. Tyhokolo | 974,581.00 |
| Kunene Makopo Risk Solutions (PTY) LTD | Insurance Service for the Municipality | 01 Mar 2022 | Feb 2024 | Mr TS Matsiliso | 545,357.61 |
|  |  |  |  |  | T H.1 |

## APPENDIX I – MUNICIPAL ENTITY/ SERVICE PROVIDER PERFORMANCE SCHEDULE

| Service Provider | Project Name | Contract Amount | Project Status | End User Remarks |
| --- | --- | --- | --- | --- |
| Musar Consulting PTY LTD | Internet Service Provision | 1,537,744.88 | Ongoing | Excellent Service |
| Lobamba Enterprise (PTY)LTD | Supply and Maintenance of Telephone Systems | 974,581.00 | Incomplete | Not Satisfactory |
| Kunene Makopo Risk Solutions (PTY) LTD | Insurance Service for the Municipality | 545,357.61 | Complete | Satisfactory |
| University of the Free State Ground Water Testing | Waste and Drinking Water Analysis | 237 929.00 | Complete | Excellent Service |
| Purim Consulting | Rural roads asset management system | 7 078 407.08 | Ongoing | Satisfactory |
| LQ Technologies | Internet Service Provision | 1,315,887.35 | Complete | Excellent service |

## APPENDIX J – DISCLOSURES OF FINANCIAL INTERESTS

| Disclosures of Financial Interests |  |  |
| --- | --- | --- |
| Period 1 July to 30 June of 2023-2024 (Current Year) |  |  |
| Position | Name | Description of Financial interests* (Nil / Or details) |
| (Executive) Mayor | Cllr NI Mehlomakulu | Nil |
| Member of MayCo / Exco |  |  |
|  | MA Lebaka | Employment and Remuneration, Pension Fund(SALA) |
|  | NJ Garekoe | Bond 100% |
|  | TD Mochechepa | Nil |
| Speaker | AM Shasha | Nil |
| Councillor | NA Adoons | Employed at Department of Education, Pension(GEPF) |
|  | M Mokheseng | Nil |
|  | AN November | SALA , employment: Letsemeng local municipality |
|  | MV Malgas | Nil |
|  | MA Molai | Nil |
|  | ME Lekoenea | Nil |
|  | AJJ van Rensburg | OVK R10 000 BKB R10 000 Circle R Ranches: R100 000 Rustfontein Farm R2,500.000 Old Mutual Wealth R350 000 |
|  | RW Van Wyk | Nil |
|  | TI Phatsoane | Employment and Remuneration |
|  | MM Potgieter | Click Photography MSB Art Box SALGA( as gazetted) Remuneration: Letsemeng Local Municipality(As gazetted) Remuneration: Xhariep District Municipality(as gazette) |
|  | J. Riddle | Nicks place(50% shareholder) Nicks Place Owner 2 million Porperty 2 million Old Mutual 1.5 million Dummer Trust (Trustee) Old Mutual Pension (R4000 000) Property(1.5 Million) |
| Municipal Manager | LY Moletsane | GEPF(pension fund) Erf R40 000( Trompsburg) Residential Property 1.5 million |
| Chief Financial Officer | PV Litabe | Share Holder: Calaria(PTY)Ltd (50%) Diabo Accountants & Consulting (80%) Property: 1.5 million(Business) Property: 1.3 million(Business) Residential Property: R760, 000 |
| Director: Corporate Services | MA Jafta | Mbuyando Trading CC 30% shares Bethulie Partners(PTY LTD) 15% shares |
| Director: Planning and Social Development | OA Kale | Nil |
| * Financial intersests to be disclosed even if they incurred for only part of the year. See MBRR SA34A T J |  |  |

## APPENDIX K (ii): REVENUE COLLECTION PERFORMANCE BY SOURCE

| Revenue Collection Performance by Source |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| R '000 |  |  |  |  |  |  |
| Description | 2022-2023 | 2023-2024 |  |  | 2023-2024 Variance |  |
|  | Actual | Original Budget | Adjustments Budget | Actual | Original Budget | Adjustments Budget |
| Agency services |  |  |  |  |  |  |
| Transfers recognized - operational | 70 979 |  |  |  |  |  |
| Other revenue | 1 150 |  |  |  |  |  |
| Total Revenue (excluding capital transfers and contributions) | 72, 129 |  |  |  |  |  |
| Variances are calculated by dividing the difference between actual and original/adjustments budget by the actual. This table is aligned to MBRR table A4. |  |  |  |  |  | T K.2 |

## APPENDIX T – NATIONAL AND PROVINCIAL OUTCOMES FOR LOCAL GOVERNMENT

| National and Provincial Outcomes for Local Government |  |  |
| --- | --- | --- |
| Outcome/Output | Progress to date | Number or Percentage Achieved |
| Output: Improving access to basic services | N/A |  |
| Output: Implementation of the Community Work Programme | N/A |  |
| Output: Deepen democracy through a refined Ward Committee model | N/A |  |
| Output: Administrative and financial capability | N/A |  |
| * Note: Some of the outputs detailed on this table might have been reported for in other chapters, the information thereof should correspond with previously reported information. |  |  |
| T T |  |  |

## VOLUME II: ANNUAL FINANCIAL STATEMENTS